## SOV
KENNY SENG CONSTRUCTION, INC.
SCHEDULE OF VALUES
Payment Request #5 |  | Date: | 2025-12-22 | Job: Treasure Mountain Sports Complex
ITEM | DESCRIPTION OF WORK | SCHEDULED | WORK COMPLETED |  | MATERIALS | TOT COMPLETED | % COMPLETE | BALANCE TO
|  | VALUE | PREVIOUS | THIS PERIOD | ON SITE |  |  | FINISH
ONSITE
1 | Temporary Erosion & Sediment Control | 40400 | 12120 | 2020 | 0 | 14140 | 35% | 26260
2 | Site Demolition | 582300 | 8086.3132 | 57531.7479 | 0 | 65618.0612 | 11.27% | 516681.9388
3 | Site Earthwork | 1267100 | 509852.5382 | 0 | 0 | 509852.5382 | 40.24% | 757247.4618
4 | Utilities (CW,FL,SD,SS,IRR) | 1215500 | 425292.359 | 0 | 0 | 425292.359 | 34.99% | 790207.641
5 | Building Earthwork | 748900 | 387693.9537 | 99267.64 | 0 | 486961.5937 | 65.02% | 261938.4063
6 | Structural Concrete | 317600 | 103643.9129 | 61201.9613 | 0 | 164845.8742 | 51.9% | 152754.1258
7 | Site Concrete Prep | 261500 | 10633.2726 | 0 | 0 | 10633.2726 | 4.066% | 250866.7274
8 | Site Concrete | 1367500 | 172106.4365 | 0 | 0 | 172106.4365 | 12.59% | 1195393.5635
9 | Hot-Mix Asphalt (Prep) | 130300 | 0 | 0 | 0 | 0 | 0% | 130300
10 | Hot-Mix Asphalt Paving | 230200 | 0 | 0 | 0 | 0 | 0% | 230200
11 | Pavement Markings - Striping | 2910 | 0 | 0 | 0 | 0 | 0% | 2910
12 | Exterior Sports Equipment | 818500 | 236740.89 | 0 |  | 236740.89 | 28.92% | 581759.11
13 | Turf Field Prep | 2424100 | 1091650.772 | 0 | 0 | 1091650.772 | 45.03% | 1332449.228
14 | Segmented Retaining Wall | 63300 | 63300 | 0 | 0 | 63300 | 100% | 0
15 | Concrete Sign Wall - Tilt Panel | 24700 | 0 | 0 | 0 | 0 | 0% | 24700
16 | Baseball & Softball Scoreboards | 63000 | 0 | 0 | 0 | 0 | 0% | 63000
17 | Soccer Scoreboards | 65000 | 0 | 0 | 0 | 0 | 0% | 65000
18 | Building Demo (Concrete Slabs And Footings) | 398000 | 0 | 9045.4545 | 0 | 9045.4545 | 2.273% | 388954.5455
19 | Hazwoper Training | 100000 | 35000 | 15000 | 0 | 50000 | 50% | 50000
| SUBTOTAL | 10120810 | 3056120.4482 | 244066.8038 | 0 | 3300187.252 | 32.61% | 6820622.748
Change Orders
|  | 0 | 0 | 0 | 0 | 0 |  | 0
|  | 0 | 0 | 0 | 0 | 0 |  | 0
| SUBTOTAL | 0 | 0 | 0 | 0 | 0 |  | 0
| TOTALS | 10120810 | 3056120.4482 | 244066.8038 | 0 | 3300187.252 | 32.61% | 6820622.748
|  | 10120810 | 2411787.8271 | 532332.6217 | 0 | 2944120.4487 | 29.09% | 7176689.5513

## Detail
ITEM | PHASE | DESCRIPTION OF WORK | SCHEDULED VALUE | COST | PRICE | QTY | UOM | UNIT PRICE | 2025-12-25 |  |  |  |  | 2025-11-25 |  |  |  |  | 2025-10-25 |  |  |  |  | 2025-09-25 |  |  |  |  | 2025-08-25
[9 empty] | QTY | AMT | REM | Rem Qty | % Com | QTY | AMT | REM | Rem Qty | % Com | QTY | AMT | REM | Rem Qty | % Com | QTY | AMT | REM | Rem Qty | % Com | QTY | AMT | REM | Rem Qty | % Com
1 |  | Temporary Erosion & Sediment Control | 40400 | 29138.08 | 40400 |  |  |  |  | 2020 | 26260 |  |  |  | 2020 | 28280 |  |  |  | 2020 | 30300 |  |  |  | 2020 | 32320 |  |  |  | 6060 | 34340
|  | SWPPP |  | 29138.08 | 40400 | 1 | LS | 40400 | 0.05 | 2020 | 26260 | 0.65 | 35% | 0.05 | 2020 | 28280 | 0.7 | 30% | 0.05 | 2020 | 30300 | 0.75 | 25% | 0.05 | 2020 | 32320 | 0.8 | 20% | 0.15 | 6060 | 34340 | 0.85 | 15%
| 2100 | SWPPP |  | 29138.08 | 40400 | 1 | LS | 40400 | 0.05 |  | 0 |  |  | 0.05 |  | 0 |  |  | 0.05 |  | 0 |  |  | 0.05 |  | 0 |  |  | 0.15
2 |  | Site Demolition | 582300 | 422513.36 | 582299.9862 |  |  |  |  | 57531.7479 | 516681.9251 |  |  |  | 0 | 574213.673 |  |  |  | 0 | 574213.673 |  |  |  | 1164.5632 | 574213.673 |  |  |  | 6921.7501 | 575378.2362
|  | Tree Removal |  | 16900 | 23291.2635 | 1 | LS | 23291.2635 | 0.75 | 17468.4476 | 1164.5632 | 0.05 | 95% |  | 0 | 18633.0108 | 0.8 | 20% |  | 0 | 18633.0108 | 0.8 | 20% | 0.05 | 1164.5632 | 18633.0108 | 0.8 | 20% | 0.15 | 3493.6895 | 19797.574 | 0.85 | 15%
| 2402 | Tree Removal |  | 16900 | 23291.2635 | 1 | LS | 23291.2635 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0.15
|  | Remove Concrete Flatwork 04" |  | 16075.12 | 22154.4293 | 17303 | SF | 1.2804 | 8003 | 10246.8877 | 11907.5416 | 9300 | 46.25% | 0 | 0 | 22154.4293 | 17303 | 0% | 0 | 0 | 22154.4293 | 17303 | 0% | 0 | 0 | 22154.4293 | 17303 | 0% | 0 | 0 | 22154.4293 | 17303 | 0%
| 2420 | Remove Concrete Flatwork |  | 6663.73 | 9183.8279 | 17303 | SF | 0.53077 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 2850.67 | 3928.74 | 432.58 | TON | 9.0821 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 6560.72 | 9041.8614 | 432.58 | TON | 20.9022 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Asphalt SF (03") |  | 98784.18 | 136142.5069 | 147064 | SF | 0.92574 | 25731 | 23820.1249 | 112322.382 | 121333 | 17.5% |  | 0 | 136142.5069 | 147064 | 0% |  | 0 | 136142.5069 | 147064 | 0% |  | 0 | 136142.5069 | 147064 | 0% |  | 0 | 136142.5069 | 147064 | 0%
| 2410 | Remove Asphalt |  | 39646.07 | 54639.4712 | 147064 | SF | 0.37154 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 17316.79 | 23865.6757 | 2757.45 | TON | 8.655 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 41821.33 | 57637.3738 | 2757.45 | TON | 20.9024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Curb/Gutter 24" |  | 11787.9 | 16245.863 | 1634 | LF | 9.9424 |  | 0 | 16245.863 | 1634 | 0% |  | 0 | 16245.863 | 1634 | 0% |  | 0 | 16245.863 | 1634 | 0% |  | 0 | 16245.863 | 1634 | 0% |  | 0 | 16245.863 | 1634 | 0%
| 2421 | Remove Curb And Gutter |  | 7521.86 | 10366.4866 | 1634 | LF | 6.3442 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 1292.17 | 1780.8445 | 196.08 | TON | 9.0822 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 2973.88 | 4098.5457 | 196.08 | TON | 20.9024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Chain Link Fence |  | 2487.38 | 3428.0605 | 811 | LF | 4.227 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 811 | 3428.0605 | 0 | 0 | 100%
| 2401 | Remove Fence |  | 2421.99 | 3337.9413 | 811 | LF | 4.1158 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 811
| 2490 | Dump Fees |  | 50.69 | 69.86 | 2.03 | TON | 34.4138 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2.03
| 2150 | Export Trucking |  | 14.71 | 20.273 | 2.03 | TON | 9.9867 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2.03
|  | Remove PVC Pipe (08") WATER |  | 159088.02 | 219252.1298 | 3367 | LF | 65.1179 | 0 | 0 | 219252.1298 | 3367 | 0% | 0 | 0 | 219252.1298 | 3367 | 0% | 0 | 0 | 219252.1298 | 3367 | 0% | 0 | 0 | 219252.1298 | 3367 | 0% | 0 | 0 | 219252.1298 | 3367 | 0%
| 2450 | Remove Pipe |  | 130624.04 | 180023.6056 | 3367 | LF | 53.4671 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 480.64 | 662.409 | 19.23 | TON | 34.4466 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 139.46 | 192.2012 | 19.23 | TON | 9.9949 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2172 | Import Efill |  | 8464.11 | 11665.0779 | 971.1 | TON | 12.0122 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 8233.24 | 11346.8972 | 971.1 | TON | 11.6846 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 8233.24 | 11346.8972 | 971.1 | TON | 11.6846 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 2913.3 | 4015.0555 | 971.1 | TON | 4.1345 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove PVC Pipe (08") SEWER |  | 63206.44 | 87109.9319 | 691 | LF | 126.0636 |  | 0 | 87109.9319 | 691 | 0% |  | 0 | 87109.9319 | 691 | 0% |  | 0 | 87109.9319 | 691 | 0% |  | 0 | 87109.9319 | 691 | 0% |  | 0 | 87109.9319 | 691 | 0%
| 2450 | Remove Pipe |  | 40211.41 | 55418.6122 | 691 | LF | 80.2006 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 98.64 | 135.9438 | 3.95 | TON | 34.4162 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 28.62 | 39.4435 | 3.95 | TON | 9.9857 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2172 | Import Efill |  | 6951.45 | 9580.3582 | 797.55 | TON | 12.0122 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 6761.84 | 9319.0413 | 797.55 | TON | 11.6846 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 6761.84 | 9319.0413 | 797.55 | TON | 11.6846 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 2392.65 | 3297.5054 | 797.55 | TON | 4.1345 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Pipe RCP 15" |  | 32782 | 45179.5385 | 1069 | LF | 42.2634 |  | 0 | 45179.5385 | 1069 | 0% |  | 0 | 45179.5385 | 1069 | 0% |  | 0 | 45179.5385 | 1069 | 0% |  | 0 | 45179.5385 | 1069 | 0% |  | 0 | 45179.5385 | 1069 | 0%
| 2450 | Remove Pipe |  | 31104.19 | 42867.2121 | 1069 | LF | 40.1003 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 648.27 | 893.4336 | 67.88 | TON | 13.162 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 1029.54 | 1418.8927 | 67.88 | TON | 20.903 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Light Pole/Base |  | 2652.02 | 3654.9643 | 12 | EACH | 304.5804 | 6 | 1827.4821 | 1827.4821 | 6 | 50% |  | 0 | 3654.9643 | 12 | 0% |  | 0 | 3654.9643 | 12 | 0% |  | 0 | 3654.9643 | 12 | 0% |  | 0 | 3654.9643 | 12 | 0%
| 2435 | Remove Pole Base |  | 2577.87 | 3552.7722 | 12 | EACH | 296.0643 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 28.65 | 39.4849 | 3 | TON | 13.1616 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 45.5 | 62.7072 | 3 | TON | 20.9024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Fire Hydrant |  | 2446.81 | 3372.1477 | 5 | EACH | 674.4295 | 1 | 674.4295 | 2697.7182 | 4 | 20% |  | 0 | 3372.1477 | 5 | 0% |  | 0 | 3372.1477 | 5 | 0% |  | 0 | 3372.1477 | 5 | 0% |  | 0 | 3372.1477 | 5 | 0%
| 2400 | Misc. Demolition |  | 2418.18 | 3332.6904 | 1 | LS | 3332.6904 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 25 | 34.4545 | 0.5 | TON | 68.9091 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 3.63 | 5.0028 | 0.5 | TON | 10.0056 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Concrete Greast Trap |  | 1253 | 1726.8611 | 1 | EACH | 1726.8611 |  | 0 | 1726.8611 | 1 | 0% |  | 0 | 1726.8611 | 1 | 0% |  | 0 | 1726.8611 | 1 | 0% |  | 0 | 1726.8611 | 1 | 0% |  | 0 | 1726.8611 | 1 | 0%
| 2456 | Remove Catch Basin |  | 808.75 | 1114.6041 | 1 | EACH | 1114.6041 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 32.95 | 45.4111 | 5 | TON | 9.0822 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 75.83 | 104.5075 | 5 | TON | 20.9015 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2172 | Import Efill |  | 101.98 | 140.5469 | 11.7 | TON | 12.0126 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 99.2 | 136.7156 | 11.7 | TON | 11.6851 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 99.2 | 136.7156 | 11.7 | TON | 11.6851 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 35.1 | 48.3742 | 11.7 | TON | 4.1345 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Catch Basin 2020 |  | 2601.67 | 3585.5729 | 7 | EACH | 512.2247 | 0 | 0 | 3585.5729 | 7 | 0% | 0 | 0 | 3585.5729 | 7 | 0% | 0 | 0 | 3585.5729 | 7 | 0% | 0 | 0 | 3585.5729 | 7 | 0% | 0 | 0 | 3585.5729 | 7 | 0%
| 2456 | Remove Catch Basin |  | 2255.64 | 3108.6808 | 7 | EACH | 444.0973 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 133.7 | 184.2628 | 7 | TON | 26.3233 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 212.33 | 292.6292 | 7 | TON | 41.8042 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Manhole 60" |  | 5217.8 | 7191.0742 | 5 | EACH | 1438.2148 |  | 0 | 7191.0742 | 5 | 0% |  | 0 | 7191.0742 | 5 | 0% |  | 0 | 7191.0742 | 5 | 0% |  | 0 | 7191.0742 | 5 | 0% |  | 0 | 7191.0742 | 5 | 0%
| 2455 | Remove Manhole |  | 4043.76 | 5573.0343 | 5 | EACH | 1114.6069 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 453.63 | 625.1844 | 47.5 | TON | 13.1618 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 720.42 | 992.8694 | 47.5 | TON | 20.9025 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Water Meter 2020 |  | 1298.54 | 1789.6235 | 2 | EACH | 894.8118 |  | 0 | 1789.6235 | 2 | 0% |  | 0 | 1789.6235 | 2 | 0% |  | 0 | 1789.6235 | 2 | 0% |  | 0 | 1789.6235 | 2 | 0% |  | 0 | 1789.6235 | 2 | 0%
| 2400 | Misc. Demolition |  | 725.45 | 999.8016 | 1 | LS | 999.8016 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 200 | 275.6363 | 4 | TON | 68.9091 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 29.01 | 39.981 | 4 | TON | 9.9953 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2172 | Import Efill |  | 104.59 | 144.144 | 12 | TON | 12.012 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 101.74 | 140.2162 | 12 | TON | 11.6847 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 101.74 | 140.2162 | 12 | TON | 11.6847 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 36 | 49.6145 | 12 | TON | 4.1345 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Remove Basketball Standard |  | 991.42 | 1366.3565 | 4 | EACH | 341.5891 | 4 | 1366.3565 | 0 | 0 | 100% |  | 0 | 1366.3565 | 4 | 0% |  | 0 | 1366.3565 | 4 | 0% |  | 0 | 1366.3565 | 4 | 0% |  | 0 | 1366.3565 | 4 | 0%
| 2435 | Remove Pole Base |  | 966.7 | 1332.2878 | 4 | EACH | 333.072 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 9.55 | 13.1616 | 1 | TON | 13.1616 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 15.17 | 20.907 | 1 | TON | 20.907 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Demo Bollard |  | 4941.05 | 6809.6626 | 32 | EACH | 212.802 | 10 | 2128.0196 | 4681.643 | 22 | 31.25% |  | 0 | 6809.6626 | 32 | 0% |  | 0 | 6809.6626 | 32 | 0% |  | 0 | 6809.6626 | 32 | 0% |  | 0 | 6809.6626 | 32 | 0%
| 2400 | Misc. Demolition |  | 4833.51 | 6661.453 | 1 | LS | 6661.453 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
| 2490 | Dump Fees |  | 61.12 | 84.2344 | 6.4 | TON | 13.1616 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
| 2150 | Export Trucking |  | 46.42 | 63.9752 | 6.4 | TON | 9.9961 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
3 |  | Site Earthwork | 1267100 | 912203.67 | 1267099.9861 |  |  |  |  | 0 | 757247.4479 |  |  |  | 30233.3187 | 757247.4479 |  |  |  | 88343.9158 | 787480.7665 |  |  |  | 28441.6758 | 875824.6823 |  |  |  | 362833.628 | 904266.3581
|  | Strip & Stockpile Topsoil Onsite Phase 1 |  | 16412.94 | 22798.4571 | 4500 | CY | 5.0663 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 4500 | 22798.4571 | 0 | 0 | 100%
| 2120 | Strip Topsoil |  | 16412.94 | 22798.4571 | 4500 | CY | 5.0663 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 4500
|  | KSC Cut To Fill (D8/D6/621/563) Phase 1 |  | 29598.11 | 41113.368 | 3033 | CY | 13.5553 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 533 | 7225 | 0 | 0 | 100% | 500 | 6777.6736 | 7225 | 533 | 82.43% | 2000 | 27110.6944 | 14002.6736 | 1033 | 65.94%
| 2130 | Cut To Fill |  | 29598.11 | 41113.368 | 3033 | CY | 13.5553 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2000
|  | Import A1A Compacted CY Phase 1 |  | 336393.34 | 467268.4567 | 9706 | CY | 48.1422 |  | 0 | 30233.3187 | 628 | 93.53% | 628 | 30233.3187 | 30233.3187 | 628 | 93.53% | 1500 | 72213.3407 | 60466.6373 | 1256 | 87.06% | 450 | 21664.0022 | 132679.978 | 2756 | 71.61% | 6500 | 312924.4765 | 154343.9803 | 3206 | 66.97%
| 2129 | Place Fill |  | 35995.8 | 50000.1038 | 17470.8 | TON | 2.8619 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11700
| 2172 | Import Efill |  | 152275.55 | 211518.9357 | 17470.8 | TON | 12.107 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11700
| 2149 | Import Trucking |  | 148122 | 205749.4312 | 17470.8 | TON | 11.7768 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 11700
|  | Fine Grade Roadway (140/563) Phase 1 |  | 28753.24 | 39939.7981 | 309531 | SF | 0.12903 |  | 0 | 39939.7981 | 309531 | 0% |  | 0 | 39939.7981 | 309531 | 0% |  | 0 | 39939.7981 | 309531 | 0% |  | 0 | 39939.7981 | 309531 | 0% |  | 0 | 39939.7981 | 309531 | 0%
| 2135 | Fine Grade |  | 28103.22 | 39036.8853 | 309531 | SF | 0.12612 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 1410 | Construction Water |  | 650.02 | 902.9128 | 185.72 | MGAL | 4.8617 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | KSC Cut To Fill (D8/D6/621/563) Phase 2 |  | 14824.06 | 20591.4173 | 1733 | CY | 11.8819 |  | 0 | 20591.4173 | 1733 | 0% |  | 0 | 20591.4173 | 1733 | 0% |  | 0 | 20591.4173 | 1733 | 0% |  | 0 | 20591.4173 | 1733 | 0% |  | 0 | 20591.4173 | 1733 | 0%
| 2130 | Cut To Fill |  | 14824.06 | 20591.4173 | 1733 | CY | 11.8819 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | KSC Cut To Stockpile Phase 2 |  | 143821.35 | 199775.5968 | 18818 | CY | 10.6162 |  | 0 | 199775.5968 | 18818 | 0% |  | 0 | 199775.5968 | 18818 | 0% |  | 0 | 199775.5968 | 18818 | 0% |  | 0 | 199775.5968 | 18818 | 0% |  | 0 | 199775.5968 | 18818 | 0%
| 2130 | Cut To Fill |  | 143821.35 | 199775.5968 | 18818 | CY | 10.6162 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Load & Export Spoils |  | 301617.38 | 418962.7764 | 18818 | CY | 22.2639 |  | 0 | 410057.2014 | 18418 | 2.126% |  | 0 | 410057.2014 | 18418 | 2.126% | 400 | 8905.575 | 410057.2014 | 18418 | 2.126% |  | 0 | 418962.7764 | 18818 | 0% |  | 0 | 418962.7764 | 18818 | 0%
| 2500 | Loading Trucks |  | 22415.53 | 31136.3778 | 32931.5 | TON | 0.94549 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
| 2150 | Export Trucking |  | 279201.85 | 387826.3986 | 32931.5 | TON | 11.7768 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
|  | Fine Grade Roadway (140/563) Phase 2 |  | 40783.24 | 56650.1157 | 439035 | SF | 0.12903 |  | 0 | 56650.1157 | 439035 | 0% |  | 0 | 56650.1157 | 439035 | 0% |  | 0 | 56650.1157 | 439035 | 0% |  | 0 | 56650.1157 | 439035 | 0% |  | 0 | 56650.1157 | 439035 | 0%
| 2135 | Fine Grade |  | 39861.27 | 55369.4497 | 439035 | SF | 0.12612 |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0
| 1410 | Construction Water |  | 921.97 | 1280.666 | 263.42 | MGAL | 4.8617 |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0
4 |  | Utilities (CW,FL,SD,SS,IRR) | 1215500 | 921076.22 | [5 empty] | 0 | 790207.641 |  |  |  | 49758.7416 | 790207.641 |  |  |  | 141104.8667 | 839966.3825 |  |  |  | 207557.3385 | 981071.2493 |  |  |  | 26871.4122 | 1188628.5878
|  | Sewer |  | 234127.95 | 308967.3982 |  |  |  |  | 0 | 111190.4095 |  |  |  | 0 | 111190.4095 |  |  |  | 59567.6347 | 111190.4095 |  |  |  | 138209.354 | 170758.0442 |  |  |  | 0 | 308967.3982
|  | Sewer Wye Connection 24 FT Deep |  | 14472.04 | 19098.0553 | 1 | EACH | 19098.0553 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 1 | 19098.0553 | 0 | 0 | 100% |  | 0 | 19098.0553 | 1 | 0%
| 4410 | Sewer Fittings & Connections |  | 14472.04 | 19098.0553 | 1 | EACH | 19098.0553 |  | 0 | -19098.0553 | -1 |  |  | 0 | -19098.0553 | -1 |  |  | 0 | -19098.0553 | -1 |  | 1 | 19098.0553 | -19098.0553 | -1 |  | 0
|  | SS Lateral Pipe SDR-35 06" |  | 110918.55 | 146373.8772 | 732 | LF | 199.9643 |  | 0 | 32394.2187 | 162 | 77.87% |  | 0 | 32394.2187 | 162 | 77.87% | 170 | 33993.9332 | 32394.2187 | 162 | 77.87% | 400 | 79985.7252 | 66388.152 | 332 | 54.64% |  | 0 | 146373.8772 | 732 | 0%
| 4006 | 6" Sanitary Sewer |  | 98623.54 | 130148.7437 | 732 | LF | 177.7988 |  | 0 | -130148.7437 | -732 |  |  | 0 | -130148.7437 | -732 |  |  | 0 | -130148.7437 | -732 |  | 732 | 130148.7437 | -130148.7437 | -732 |  | 0
| 2185 | Import Bedding Gravel |  | 6297.78 | 8310.8775 | 318.87 | TON | 26.0635 |  | 0 | -8310.8775 | -318.87 |  |  | 0 | -8310.8775 | -318.87 |  |  | 0 | -8310.8775 | -318.87 |  | 318.87 | 8310.8775 | -8310.8775 | -318.87 |  | 0
| 2149 | Import Trucking |  | 2703.37 | 3567.5074 | 318.86 | TON | 11.1883 |  | 0 | -3567.5074 | -318.86 |  |  | 0 | -3567.5074 | -318.86 |  |  | 0 | -3567.5074 | -318.86 |  | 318.86 | 3567.5074 | -3567.5074 | -318.86 |  | 0
| 4490 | Sewer Line Testing |  | 570.96 | 753.4685 | 732 | LF | 1.0293 |  | 0 | -753.4685 | -732 |  |  | 0 | -753.4685 | -732 |  |  | 0 | -753.4685 | -732 |  | 732 | 753.4685 | -753.4685 | -732 |  | 0
| 2150 | Export Trucking |  | 2011.23 | 2654.1235 | 237.22 | TON | 11.1884 |  | 0 | -2654.1235 | -237.22 |  |  | 0 | -2654.1235 | -237.22 |  |  | 0 | -2654.1235 | -237.22 |  | 237.22 | 2654.1235 | -2654.1235 | -237.22 |  | 0
| 2490 | Dump Fees |  | 711.67 | 939.1567 | 237.22 | TON | 3.959 |  | 0 | -939.1567 | -237.22 |  |  | 0 | -939.1567 | -237.22 |  |  | 0 | -939.1567 | -237.22 |  | 237.22 | 939.1567 | -939.1567 | -237.22 |  | 0
|  | SS Lateral Pipe SDR-35 04" |  | 23177.34 | 30586.0212 | 298 | LF | 102.6377 |  | 0 | 30586.0212 | 298 | 0% |  | 0 | 30586.0212 | 298 | 0% |  | 0 | 30586.0212 | 298 | 0% |  | 0 | 30586.0212 | 298 | 0% |  | 0 | 30586.0212 | 298 | 0%
| 4404 | 4" Sanitary Sewer |  | 18749.6 | 24742.9456 | 298 | LF | 83.03 |  | 0 | -24742.9456 | -298 |  |  | 0 | -24742.9456 | -298 |  |  | 0 | -24742.9456 | -298 |  | 298 | 24742.9456 | -24742.9456 | -298 |  | 0
| 2185 | Import Bedding Gravel |  | 2271.71 | 2997.8665 | 115.02 | TON | 26.0639 |  | 0 | -2997.8665 | -115.02 |  |  | 0 | -2997.8665 | -115.02 |  |  | 0 | -2997.8665 | -115.02 |  | 115.02 | 2997.8665 | -2997.8665 | -115.02 |  | 0
| 2185 | Import Trucking |  | 975.2 | 1286.9246 | 115.02 | TON | 11.1887 |  | 0 | -1286.9246 | -115.02 |  |  | 0 | -1286.9246 | -115.02 |  |  | 0 | -1286.9246 | -115.02 |  | 115.02 | 1286.9246 | -1286.9246 | -115.02 |  | 0
| 4490 | Sewer Line Testing |  | 232.44 | 306.7399 | 298 | LF | 1.0293 |  | 0 | -306.7399 | -298 |  |  | 0 | -306.7399 | -298 |  |  | 0 | -306.7399 | -298 |  | 298 | 306.7399 | -306.7399 | -298 |  | 0
| 2150 | Export Trucking |  | 700.51 | 924.4294 | 82.62 | TON | 11.1889 |  | 0 | -924.4294 | -82.62 |  |  | 0 | -924.4294 | -82.62 |  |  | 0 | -924.4294 | -82.62 |  | 82.62 | 924.4294 | -924.4294 | -82.62 |  | 0
| 2490 | Dump Fees |  | 247.87 | 327.1021 | 82.62 | TON | 3.9591 |  | 0 | -327.1021 | -82.62 |  |  | 0 | -327.1021 | -82.62 |  |  | 0 | -327.1021 | -82.62 |  | 82.62 | 327.1021 | -327.1021 | -82.62 |  | 0
|  | SD Cleanout 06" |  | 10584.25 | 13967.5258 | 12 | EACH | 1163.9605 |  | 0 | 8147.7234 | 7 | 41.67% |  | 0 | 8147.7234 | 7 | 41.67% | 3 | 3491.8815 | 8147.7234 | 7 | 41.67% | 2 | 2327.921 | 11639.6048 | 10 | 16.67% |  | 0 | 13967.5258 | 12 | 0%
| 4410 | Sewer Fittings & Connections |  | 3669.82 | 4842.885 | 12 | EACH | 403.5738 |  | 0 | -4842.885 | -12 |  |  | 0 | -4842.885 | -12 |  |  | 0 | -4842.885 | -12 |  | 12 | 4842.885 | -4842.885 | -12 |  | 0
| 2185 | Iimport Bedding Gravel |  | 23.7 | 31.2758 | 1.2 | TON | 26.0631 |  | 0 | -31.2758 | -1.2 |  |  | 0 | -31.2758 | -1.2 |  |  | 0 | -31.2758 | -1.2 |  | 1.2 | 31.2758 | -31.2758 | -1.2 |  | 0
| 2149 | Import Trucking |  | 10.17 | 13.4209 | 1.2 | TON | 11.1841 |  | 0 | -13.4209 | -1.2 |  |  | 0 | -13.4209 | -1.2 |  |  | 0 | -13.4209 | -1.2 |  | 1.2 | 13.4209 | -13.4209 | -1.2 |  | 0
| 6480 | Waterworks Materials |  | 2080.56 | 2745.615 | 1 | LS | 2745.615 |  | 0 | -2745.615 | -1 |  |  | 0 | -2745.615 | -1 |  |  | 0 | -2745.615 | -1 |  | 1 | 2745.615 | -2745.615 | -1 |  | 0
| 3290 | Concrete Collars |  | 4800 | 6334.3292 | 12 | EACH | 527.8608 |  | 0 | -6334.3292 | -12 |  |  | 0 | -6334.3292 | -12 |  |  | 0 | -6334.3292 | -12 |  | 12 | 6334.3292 | -6334.3292 | -12 |  | 0
|  | SD Cleanout 04" |  | 7774.21 | 10259.2511 | 10 | EACH | 1025.9251 |  | 0 | 10259.2511 | 10 | 0% |  | 0 | 10259.2511 | 10 | 0% |  | 0 | 10259.2511 | 10 | 0% |  | 0 | 10259.2511 | 10 | 0% |  | 0 | 10259.2511 | 10 | 0%
| 4410 | Sewer Fittings & Connections |  | 3058.18 | 4035.7331 | 10 | EACH | 403.5733 |  | 0 | -4035.7331 | -10 |  |  | 0 | -4035.7331 | -10 |  |  | 0 | -4035.7331 | -10 |  | 10 | 4035.7331 | -4035.7331 | -10 |  | 0
| 2185 | Import Bedding Gravel |  | 19.75 | 26.0631 | 1 | TON | 26.0631 |  | 0 | -26.0631 | -1 |  |  | 0 | -26.0631 | -1 |  |  | 0 | -26.0631 | -1 |  | 1 | 26.0631 | -26.0631 | -1 |  | 0
| 2149 | Import Trucking |  | 8.48 | 11.1906 | 1 | TON | 11.1906 |  | 0 | -11.1906 | -1 |  |  | 0 | -11.1906 | -1 |  |  | 0 | -11.1906 | -1 |  | 1 | 11.1906 | -11.1906 | -1 |  | 0
| 6480 | Waterworks Materials |  | 687.8 | 907.6566 | 1 | LS | 907.6566 |  | 0 | -907.6566 | -1 |  |  | 0 | -907.6566 | -1 |  |  | 0 | -907.6566 | -1 |  | 1 | 907.6566 | -907.6566 | -1 |  | 0
| 3290 | Concrete Collars |  | 4000 | 5278.6077 | 10 | EACH | 527.8608 |  | 0 | -5278.6077 | -10 |  |  | 0 | -5278.6077 | -10 |  |  | 0 | -5278.6077 | -10 |  | 10 | 5278.6077 | -5278.6077 | -10 |  | 0
|  | SS (WYE) 06x04" |  | 315.63 | 416.5217 | 4 | EACH | 104.1304 |  | 0 | 104.1304 | 1 | 75% |  | 0 | 104.1304 | 1 | 75% |  | 0 | 104.1304 | 1 | 75% | 3 | 312.3913 | 104.1304 | 1 | 75% |  | 0 | 416.5217 | 4 | 0%
| 4410 | Sewer Fittings & Connections |  | 275.63 | 363.7357 | 4 | EACH | 90.9339 |  | 0 | -363.7357 | -4 |  |  | 0 | -363.7357 | -4 |  |  | 0 | -363.7357 | -4 |  | 4 | 363.7357 | -363.7357 | -4 |  | 0
| 6480 | Waterworks Materials |  | 40 | 52.7861 | 1 | EACH | 52.7861 |  | 0 | -52.7861 | -1 |  |  | 0 | -52.7861 | -1 |  |  | 0 | -52.7861 | -1 |  | 1 | 52.7861 | -52.7861 | -1 |  | 0
|  | SS (WYE) 04x04" 2021 |  | 216.72 | 285.995 | 3 | EACH | 95.3317 |  | 0 | 95.3317 | 1 | 66.67% |  | 0 | 95.3317 | 1 | 66.67% | 2 | 190.6633 | 95.3317 | 1 | 66.67% |  | 0 | 285.995 | 3 | 0% |  | 0 | 285.995 | 3 | 0%
| 4410 | Sewer Fittings & Connections |  | 206.72 | 272.7984 | 3 | EACH | 90.9328 |  | 0 | -272.7984 | -3 |  |  | 0 | -272.7984 | -3 |  |  | 0 | -272.7984 | -3 |  | 3 | 272.7984 | -272.7984 | -3 |  | 0
| 6480 | Waterworks Materials |  | 10 | 13.1965 | 1 | EACH | 13.1965 |  | 0 | -13.1965 | -1 |  |  | 0 | -13.1965 | -1 |  |  | 0 | -13.1965 | -1 |  | 1 | 13.1965 | -13.1965 | -1 |  | 0
|  | SS Connect To Exist Stub |  | 1249.97 | 1649.5253 | 2 | EACH | 824.7627 |  | 0 | 1649.5253 | 2 | 0% |  | 0 | 1649.5253 | 2 | 0% |  | 0 | 1649.5253 | 2 | 0% |  | 0 | 1649.5253 | 2 | 0% |  | 0 | 1649.5253 | 2 | 0%
| 4410 | Sewer Fittings & Connections |  | 1249.97 | 1649.5253 | 2 | EACH | 824.7627 |  | 0 | -1649.5253 | -2 |  |  | 0 | -1649.5253 | -2 |  |  | 0 | -1649.5253 | -2 |  | 2 | 1649.5253 | -1649.5253 | -2 |  | 0
|  | SS Grease Interceptor (600 Gal) |  | 10123.96 | 13360.1032 | 1 | EACH | 13360.1032 |  | 0 | 13360.1032 | 1 | 0% |  | 0 | 13360.1032 | 1 | 0% |  | 0 | 13360.1032 | 1 | 0% |  | 0 | 13360.1032 | 1 | 0% |  | 0 | 13360.1032 | 1 | 0%
| 4430 | Grease Interceptor |  | 3717.18 | 4905.3837 | 1 | EACH | 4905.3837 |  | 0 | -4905.3837 | -1 |  |  | 0 | -4905.3837 | -1 |  |  | 0 | -4905.3837 | -1 |  | 1 | 4905.3837 | -4905.3837 | -1 |  | 0
| 5490 | Precast Materials |  | 4370 | 5766.8789 | 1 | LS | 5766.8789 |  | 0 | -5766.8789 | -1 |  |  | 0 | -5766.8789 | -1 |  |  | 0 | -5766.8789 | -1 |  | 1 | 5766.8789 | -5766.8789 | -1 |  | 0
| 2185 | Import Bedding Gravel |  | 158 | 208.505 | 8 | TON | 26.0631 |  | 0 | -208.505 | -8 |  |  | 0 | -208.505 | -8 |  |  | 0 | -208.505 | -8 |  | 8 | 208.505 | -208.505 | -8 |  | 0
| 2149 | Import Trucking |  | 1356.52 | 1790.1342 | 8 | TON | 223.7668 |  | 0 | -1790.1342 | -8 |  |  | 0 | -1790.1342 | -8 |  |  | 0 | -1790.1342 | -8 |  | 8 | 1790.1342 | -1790.1342 | -8 |  | 0
| 2150 | Export Trucking |  | 385.76 | 509.0689 | 45.5 | TON | 11.1883 |  | 0 | -509.0689 | -45.5 |  |  | 0 | -509.0689 | -45.5 |  |  | 0 | -509.0689 | -45.5 |  | 45.5 | 509.0689 | -509.0689 | -45.5 |  | 0
| 2490 | Dump Fees |  | 136.5 | 180.1325 | 45.5 | TON | 3.959 |  | 0 | -180.1325 | -45.5 |  |  | 0 | -180.1325 | -45.5 |  |  | 0 | -180.1325 | -45.5 |  | 45.5 | 180.1325 | -180.1325 | -45.5 |  | 0
|  | Dewatering (4in Submersible Pump At Wellpoint 24/7) |  | 26582.08 | 35079.0928 | 20 | DY | 1753.9546 |  | 0 | 7015.8186 | 4 | 80% |  | 0 | 7015.8186 | 4 | 80% | 6 | 10523.7279 | 7015.8186 | 4 | 80% | 10 | 17539.5464 | 17539.5464 | 10 | 50% |  | 0 | 35079.0928 | 20 | 0%
| 2600 | Dewatering (4in Submersible Pump At Wellpoint 24/7) |  | 26582.08 | 35079.0928 | 20 | DY | 1753.9546 |  | 0 | -35079.0928 | -20 |  |  | 0 | -35079.0928 | -20 |  |  | 0 | -35079.0928 | -20 |  | 20 | 35079.0928 | -35079.0928 | -20 |  | 0
|  | Well Point ADS Perf 08" |  | 28713.2 | 37891.4294 | 40 | EACH | 947.2857 |  | 0 | 7578.2859 | 8 | 80% |  | 0 | 7578.2859 | 8 | 80% | 12 | 11367.4288 | 7578.2859 | 8 | 80% | 20 | 18945.7147 | 18945.7147 | 20 | 50% |  | 0 | 37891.4294 | 40 | 0%
| 2105 | Potholing |  | 12457.49 | 16439.5506 | 40 | EACH | 410.9888 | #REF! |  | 0 | #REF! |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2187 | Import 2" Rock |  | 8160 | 10768.3596 | 40 | EACH | 269.209 | #REF! |  | 0 | #REF! |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 3391.3 | 4475.3355 | 40 | EACH | 111.8834 | #REF! |  | 0 | #REF! |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6480 | Waterworks Materials |  | 113.1 | 149.2526 | 1 | LS | 149.2526 | #REF! |  | 0 | #REF! |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 3391.3 | 4475.3355 | 400 | TON | 11.1883 | #REF! |  | 0 | #REF! |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 1200 | 1583.5823 | 400 | TON | 3.959 | #REF! |  | 0 | #REF! |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Storm Drain |  | 246594.95 | 325419.4986 |  |  |  |  | 0 | 240500.1588 | 0 |  |  | 49758.7416 | 240500.1588 | 0 |  |  | 32216.2974 | 290258.9003 | 0 |  |  | 2944.3141 | 322475.1977 | 0 |  |  | 0 | 325419.5118
|  | SD PVC SDR 04" |  | 1790.83 | 2363.2722 | 25 | LF | 94.5309 |  | 0 | 2363.2722 | 25 | 0% |  | 0 | 2363.2722 | 25 | 0% |  | 0 | 2363.2722 | 25 | 0% |  | 0 | 2363.2722 | 25 | 0% |  | 0 | 2363.2722 | 25 | 0%
| 5004 | 4" Storm Drain |  | 1438.88 | 1898.8208 | 25 | LF | 75.9528 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 190.58 | 251.4993 | 9.65 | TON | 26.0621 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 81.81 | 107.9607 | 9.65 | TON | 11.1876 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 58.77 | 77.5559 | 6.93 | TON | 11.1913 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 20.79 | 27.4356 | 6.93 | TON | 3.959 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD PVC SDR 06" |  | 7420.97 | 9793.0973 | 100 | LF | 97.931 |  | 0 | 6855.1681 | 70 | 30% | 19 | 1860.6885 | 6855.1681 | 70 | 30% | 11 | 1077.2407 | 8715.8566 | 89 | 11% |  | 0 | 9793.0973 | 100 | 0% |  | 0 | 9793.0973 | 100 | 0%
| 5006 | 6" Storm Drain |  | 5819.31 | 7679.4636 | 100 | LF | 76.7946 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 860.35 | 1135.3625 | 43.56 | TON | 26.0643 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 369.33 | 487.387 | 43.56 | TON | 11.1889 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 274.76 | 362.5876 | 32.41 | TON | 11.1875 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 97.22 | 128.2966 | 32.41 | TON | 3.9585 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD PVC SDR 08" 2020 |  | 52963.82 | 69893.8066 | 695 | LF | 100.5666 |  | 0 | 20012.759 | 199 | 71.37% | 300 | 30169.9885 | 20012.759 | 199 | 71.37% | 186 | 18705.3929 | 50182.7475 | 499 | 28.2% | 10 | 1005.6663 | 68888.1403 | 685 | 1.439% |  | 0 | 69893.8066 | 695 | 0%
| 5008 | 8" Storm Drain |  | 40444.18 | 53372.2397 | 695 | LF | 76.7946 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 6669.25 | 8801.0886 | 337.68 | TON | 26.0634 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 2862.97 | 3778.1239 | 337.68 | TON | 11.1885 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 2206.62 | 2911.9703 | 260.27 | TON | 11.1883 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 780.8 | 1030.3842 | 260.27 | TON | 3.9589 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD PVC SDR 10" |  | 52592.68 | 69404.031 | 672 | LF | 103.2798 |  | 0 | 69404.031 | 672 | 0% |  | 0 | 69404.031 | 672 | 0% |  | 0 | 69404.031 | 672 | 0% |  | 0 | 69404.031 | 672 | 0% |  | 0 | 69404.031 | 672 | 0%
| 5010 | 10" Storm Drain |  | 39105.74 | 51605.9648 | 672 | LF | 76.7946 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 7123.71 | 9400.8176 | 360.69 | TON | 26.0634 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 3058.06 | 4035.5747 | 360.69 | TON | 11.1885 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 2441.32 | 3221.6926 | 287.95 | TON | 11.1884 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 863.85 | 1139.9813 | 287.95 | TON | 3.959 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD PVC SDR 12" 2020 |  | 55701.71 | 73506.8684 | 693 | LF | 106.0705 |  | 0 | 72552.2338 | 684 | 1.299% |  | 0 | 72552.2338 | 684 | 1.299% | 9 | 954.6347 | 72552.2338 | 684 | 1.299% |  | 0 | 73506.8684 | 693 | 0% |  | 0 | 73506.8684 | 693 | 0%
| 5012 | 12" Storm Drain |  | 40327.8 | 53218.6586 | 693 | LF | 76.7946 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 8051.03 | 10624.5572 | 407.65 | TON | 26.0629 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 3456.14 | 4560.9018 | 407.65 | TON | 11.1883 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 2856.11 | 3769.071 | 336.88 | TON | 11.1882 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 1010.63 | 1333.6798 | 336.88 | TON | 3.9589 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD RCP CL III 15" 2020 |  | 3904.42 | 5152.4753 | 40 | LF | 128.8119 |  | 0 | 5152.4753 | 40 | 0% |  | 0 | 5152.4753 | 40 | 0% |  | 0 | 5152.4753 | 40 | 0% |  | 0 | 5152.4753 | 40 | 0% |  | 0 | 5152.4753 | 40 | 0%
| 5015 | 15" Storm Drain |  | 2572.81 | 3395.2137 | 40 | LF | 84.8803 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 547.52 | 722.5358 | 27.72 | TON | 26.0655 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 235.04 | 310.171 | 27.72 | TON | 11.1894 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 5480 | Storm Drain Testing |  | 268 | 353.6667 | 40 | LF | 8.8417 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 207.6 | 273.9597 | 24.49 | TON | 11.1866 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 73.46 | 96.9416 | 24.49 | TON | 3.9584 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD Oil/Water Separator (2000 Gal) 2021 |  | 17720.88 | 23385.3933 | 1 | EACH | 23385.3933 |  | 0 | 23385.3933 | 1 | 0% |  | 0 | 23385.3933 | 1 | 0% |  | 0 | 23385.3933 | 1 | 0% |  | 0 | 23385.3933 | 1 | 0% |  | 0 | 23385.3933 | 1 | 0%
| 4430 | Grease Interceptor |  | 3717.18 | 4905.3837 | 1 | EACH | 4905.3837 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 5490 | Precast Materials |  | 6325 | 8346.7984 | 1 | LS | 8346.7984 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 4740 | 6255.1501 | 12 | TON | 521.2625 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 2034.78 | 2685.2013 | 12 | TON | 223.7668 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 667.66 | 881.0788 | 78.75 | TON | 11.1883 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 236.25 | 311.7678 | 78.75 | TON | 3.959 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD Curb Inlet Box (02x03x04) 2020 |  | 17860.89 | 23570.1577 | 10 | EACH | 2357.0158 |  | 0 | 23570.1577 | 10 | 0% |  | 0 | 23570.1577 | 10 | 0% |  | 0 | 23570.1577 | 10 | 0% |  | 0 | 23570.1577 | 10 | 0% |  | 0 | 23570.1577 | 10 | 0%
| 5110 | Storm Drain Inlet Box |  | 12508.75 | 16507.1959 | 10 | EACH | 1650.7196 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 88.88 | 117.2907 | 4.5 | TON | 26.0646 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 38.15 | 50.3447 | 4.5 | TON | 11.1877 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 5105 | Storm Drain Grout |  | 854.84 | 1128.0912 | 10 | EACH | 112.8091 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 3295 | Inlet Box Tie In |  | 4370.27 | 5767.2352 | 10 | EACH | 576.7235 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD Junction Box (2x2) 2020 |  | 21746.32 | 28697.5729 | 15 | EACH | 1913.1715 |  | 0 | 5739.5146 | 3 | 80% | 6 | 11479.0292 | 5739.5146 | 3 | 80% | 6 | 11479.0292 | 17218.5437 | 9 | 40% |  | 0 | 28697.5729 | 15 | 0% |  | 0 | 28697.5729 | 15 | 0%
| 5110 | Storm Drain Inlet Box |  | 13761.81 | 18160.799 | 15 | EACH | 1210.7199 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 83.25 | 109.861 | 7.5 | TON | 14.6481 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 63.59 | 83.9167 | 7.5 | TON | 11.1889 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 5105 | Storm Drain Grout |  | 1282.26 | 1692.1369 | 15 | EACH | 112.8091 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 3295 | Inlet Box Tie In |  | 6555.41 | 8650.8594 | 15 | EACH | 576.724 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD Catch Basin 4x4 2020 |  | 5876.24 | 7754.5914 | 4 | EACH | 1938.6478 |  | 0 | 3877.2957 | 2 | 50% | 1 | 1938.6478 | 3877.2957 | 2 | 50% |  | 0 | 5815.9435 | 3 | 25% | 1 | 1938.6478 | 5815.9435 | 3 | 25% |  | 0 | 7754.5914 | 4 | 0%
| 5110 | Storm Drain Inlet Box |  | 3780.23 | 4988.5878 | 4 | EACH | 1247.1469 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 4.44 | 5.8593 | 0.4 | TON | 14.6481 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 1.53 | 2.0191 | 0.4 | TON | 5.0477 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 5105 | Storm Drain Grout |  | 341.94 | 451.2418 | 4 | EACH | 112.8104 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 3295 | Inlet Box Tie In |  | 1748.11 | 2306.8967 | 4 | EACH | 576.7242 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD Cleanout 04" 2020 |  | 3721.32 | 4910.8471 | 4 | EACH | 1227.7118 |  | 0 | 3683.1353 | 3 | 25% | 1 | 1227.7118 | 3683.1353 | 3 | 25% |  | 0 | 4910.8471 | 4 | 0% |  | 0 | 4910.8471 | 4 | 0% |  | 0 | 4910.8471 | 4 | 0%
| 5410 | Storm Drain Fittings & Connections |  | 1834.91 | 2421.4425 | 4 | EACH | 605.3606 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 7.9 | 10.4253 | 0.4 | TON | 26.0631 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 3.39 | 4.4736 | 0.4 | TON | 11.1841 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 6480 | Waterworks Materials |  | 275.12 | 363.0626 | 1 | LS | 363.0626 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 3290 | Concrete Collars |  | 1600 | 2111.4431 | 4 | EACH | 527.8608 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | SD Fittings 04" |  | 5294.88 | 6987.3985 | 34 | EACH | 205.5117 |  | 0 | 3904.7227 | 19 | 44.12% | 15 | 3082.6758 | 3904.7227 | 19 | 44.12% | 0 | 0 | 6987.3985 | 34 | 0% |  | 0 | 6987.3985 | 34 | 0% |  | 0 | 6987.3985 | 34 | 0%
| 5410 | Storm Drain Fittings & Connections |  | 5198.91 | 6860.7516 | 34 | EACH | 201.7868 |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 67.15 | 88.6146 | 3.4 | TON | 26.0631 |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 28.83 | 38.0456 | 3.4 | TON | 11.1899 |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Culinary Water & Fire Lines |  | 105902.44 | 139754.358 |  |  |  |  | 0 | 139754.3448 | 0 |  |  | 0 | 139754.3448 | 0 |  |  | 0 | 139754.3448 | 0 |  |  | 0 | 139754.3448 | 0 |  |  | 0 | 139754.3448
|  | CW Connect To Exist 08" Sleeve |  | 3936.54 | 5194.8626 | 2 | EACH | 2597.4313 |  | 0 | 5194.8626 | 2 | 0% |  | 0 | 5194.8626 | 2 | 0% |  | 0 | 5194.8626 | 2 | 0% |  | 0 | 5194.8626 | 2 | 0% |  | 0 | 5194.8626 | 2 | 0%
| 6460 | Waterline Connections |  | 3936.54 | 5194.8626 | 2 | EACH | 2597.4313 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | CW Connect To Exist |  | 2768.27 | 3653.1528 | 2 | EACH | 1826.5764 |  | 0 | 3653.1528 | 2 | 0% |  | 0 | 3653.1528 | 2 | 0% |  | 0 | 3653.1528 | 2 | 0% |  | 0 | 3653.1528 | 2 | 0% |  | 0 | 3653.1528 | 2 | 0%
| 6460 | Waterline Connections |  | 1968.27 | 2597.4313 | 2 | EACH | 1298.7156 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6450 | Hot Tapping |  | 800 | 1055.7215 | 2 | EACH | 527.8608 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Culinary Water Poly 01" (LF) 2020 |  | 8174.72 | 10787.7849 | 434 | LF | 24.8566 |  | 0 | 10787.7849 | 434 | 0% |  | 0 | 10787.7849 | 434 | 0% |  | 0 | 10787.7849 | 434 | 0% |  | 0 | 10787.7849 | 434 | 0% |  | 0 | 10787.7849 | 434 | 0%
| 6001 | 1" Waterline |  | 5247.45 | 6924.8075 | 434 | LF | 15.9558 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2180 | Import Bedding Sand |  | 1507.33 | 1989.1509 | 167.48 | TON | 11.8769 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 1419.94 | 1873.8265 | 167.48 | TON | 11.1884 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Culinary Water Main C900 04" 2020 |  | 1336.85 | 1764.1767 | 30 | LF | 58.8059 |  | 0 | 1764.1767 | 30 | 0% |  | 0 | 1764.1767 | 30 | 0% |  | 0 | 1764.1767 | 30 | 0% |  | 0 | 1764.1767 | 30 | 0% |  | 0 | 1764.1767 | 30 | 0%
| 6004 | 4" Waterline |  | 832.3 | 1098.3463 | 30 | LF | 36.6115 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2180 | Import Bedding Sand |  | 105.3 | 138.9593 | 11.7 | TON | 11.8769 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 99.2 | 130.9095 | 11.7 | TON | 11.1888 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6490 | Waterline Testing |  | 22.98 | 30.3256 | 30 | LF | 1.0109 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2172 | Import Efill |  | 55.2 | 72.8448 | 6.33 | TON | 11.5079 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 53.7 | 70.8653 | 6.33 | TON | 11.1952 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 124.22 | 163.9272 | 14.65 | TON | 11.1896 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 43.95 | 57.9987 | 14.65 | TON | 3.959 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Culinary Water Main C900 06" 2020 |  | 3999.17 | 5277.5124 | 77 | LF | 68.5391 |  | 0 | 5277.5124 | 77 | 0% |  | 0 | 5277.5124 | 77 | 0% |  | 0 | 5277.5124 | 77 | 0% |  | 0 | 5277.5124 | 77 | 0% |  | 0 | 5277.5124 | 77 | 0%
| 6006 | 6" Waterline |  | 2136.25 | 2819.1064 | 77 | LF | 36.6118 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2180 | Import Bedding Sand |  | 301.46 | 397.8223 | 33.5 | TON | 11.8753 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 283.98 | 374.7548 | 33.5 | TON | 11.1867 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6490 | Waterline Testing |  | 58.88 | 77.7011 | 77 | LF | 1.0091 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2172 | Import Efill |  | 283.37 | 373.9498 | 32.51 | TON | 11.5026 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 275.64 | 363.7489 | 32.51 | TON | 11.1888 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 275.64 | 363.7489 | 32.51 | TON | 11.1888 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 97.53 | 128.7057 | 32.51 | TON | 3.959 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 211.56 | 279.1856 | 24.95 | TON | 11.1898 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 74.86 | 98.7891 | 24.95 | TON | 3.9595 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Culinary Water Main C900 08" 2020 |  | 65685.78 | 86682.3655 | 1100 | LF | 78.8022 |  | 0 | 86682.3655 | 1100 | 0% |  | 0 | 86682.3655 | 1100 | 0% |  | 0 | 86682.3655 | 1100 | 0% |  | 0 | 86682.3655 | 1100 | 0% |  | 0 | 86682.3655 | 1100 | 0%
| 6008 | 8" Waterline |  | 30517.84 | 40272.9261 | 1100 | LF | 36.6118 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2180 | Import Bedding Sand |  | 4809.42 | 6346.7603 | 534.38 | TON | 11.8769 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 4530.61 | 5978.8282 | 534.38 | TON | 11.1883 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6490 | Waterline Testing |  | 1124.42 | 1483.843 | 1100 | LF | 1.3489 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2172 | Import Efill |  | 6072.15 | 8013.1244 | 696.67 | TON | 11.502 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 5906.52 | 7794.5504 | 696.67 | TON | 11.1883 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 5906.52 | 7794.5504 | 696.67 | TON | 11.1883 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 2090 | 2758.0725 | 696.67 | TON | 3.9589 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 3492.49 | 4608.8711 | 411.93 | TON | 11.1885 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 1235.8 | 1630.8258 | 411.93 | TON | 3.959 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Culinary Water Main C900 10" 2020 |  | 10347.84 | 13655.5469 | 169 | LF | 80.8021 |  | 0 | 13655.5469 | 169 | 0% |  | 0 | 13655.5469 | 169 | 0% |  | 0 | 13655.5469 | 169 | 0% |  | 0 | 13655.5469 | 169 | 0% |  | 0 | 13655.5469 | 169 | 0%
| 6010 | 10" Waterline |  | 4688.65 | 6187.386 | 169 | LF | 36.6118 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2180 | Import Bedding Sand |  | 816.32 | 1077.2583 | 90.7 | TON | 11.8772 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 769 | 1014.8123 | 90.7 | TON | 11.1887 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6490 | Waterline Testing |  | 173.74 | 229.2763 | 169 | LF | 1.3567 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2172 | Import Efill |  | 932.9 | 1231.1033 | 107.03 | TON | 11.5024 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 907.46 | 1197.5313 | 107.03 | TON | 11.1887 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 907.46 | 1197.5313 | 107.03 | TON | 11.1887 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 321.1 | 423.7402 | 107.03 | TON | 3.9591 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 613.96 | 810.2135 | 72.42 | TON | 11.1877 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 217.25 | 286.6944 | 72.42 | TON | 3.9588 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | TEE DI (08x06x08) 2021 |  | 1429.11 | 1885.9278 | 2 | EACH | 942.9639 |  | 0 | 1885.9278 | 2 | 0% |  | 0 | 1885.9278 | 2 | 0% |  | 0 | 1885.9278 | 2 | 0% |  | 0 | 1885.9278 | 2 | 0% |  | 0 | 1885.9278 | 2 | 0%
| 6410 | Install Water Fittings & Valves |  | 192.33 | 253.8087 | 2 | EACH | 126.9043 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6480 | Waterworks Materials |  | 673.6 | 888.9175 | 2 | EACH | 444.4588 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6415 | Thrust Blocks |  | 563.18 | 743.2016 | 2 | EACH | 371.6008 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | TEE DI (08x04x08) 2021 |  | 599.76 | 791.4744 | 1 | EACH | 791.4744 |  | 0 | 791.4744 | 1 | 0% |  | 0 | 791.4744 | 1 | 0% |  | 0 | 791.4744 | 1 | 0% |  | 0 | 791.4744 | 1 | 0% |  | 0 | 791.4744 | 1 | 0%
| 6410 | Install Water Fittings & Valves |  | 96.17 | 126.9109 | 1 | EACH | 126.9109 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6480 | Waterworks Materials |  | 222 | 292.9627 | 1 | LS | 292.9627 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6415 | Thrust Blocks |  | 281.59 | 371.6008 | 1 | EACH | 371.6008 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Bend 45° 04" 2020 |  | 333.82 | 440.5262 | 1 | EACH | 440.5262 |  | 0 | 440.5262 | 1 | 0% |  | 0 | 440.5262 | 1 | 0% |  | 0 | 440.5262 | 1 | 0% |  | 0 | 440.5262 | 1 | 0% |  | 0 | 440.5262 | 1 | 0%
| 6410 | Install Water Fittings & Valves |  | 120.91 | 159.5591 | 1 | EACH | 159.5591 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6415 | Thrust Blocks |  | 212.91 | 280.9671 | 1 | EACH | 280.9671 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Bend 45° 08" 2020 |  | 1393.52 | 1838.9613 | 3 | EACH | 612.9871 |  | 0 | 1838.9613 | 3 | 0% |  | 0 | 1838.9613 | 3 | 0% |  | 0 | 1838.9613 | 3 | 0% |  | 0 | 1838.9613 | 3 | 0% |  | 0 | 1838.9613 | 3 | 0%
| 6410 | Install Water Fittings & Valves |  | 507.82 | 670.1456 | 3 | EACH | 223.3819 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6415 | Thrust Blocks |  | 885.7 | 1168.8157 | 3 | EACH | 389.6052 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Bend 45° 10" 2020 |  | 1052.49 | 1388.9204 | 2 | EACH | 694.4602 |  | 0 | 1388.9204 | 2 | 0% |  | 0 | 1388.9204 | 2 | 0% |  | 0 | 1388.9204 | 2 | 0% |  | 0 | 1388.9204 | 2 | 0% |  | 0 | 1388.9204 | 2 | 0%
| 6410 | Install Water Fittings & Valves |  | 338.55 | 446.7682 | 2 | EACH | 223.3841 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6415 | Thrust Blocks |  | 713.95 | 942.1655 | 2 | EACH | 471.0827 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Valve Gate (04") 2020 |  | 1635.27 | 2157.9872 | 3 | EACH | 719.3291 |  | 0 | 2157.9872 | 3 | 0% |  | 0 | 2157.9872 | 3 | 0% |  | 0 | 2157.9872 | 3 | 0% |  | 0 | 2157.9872 | 3 | 0% |  | 0 | 2157.9872 | 3 | 0%
| 6410 | Install Water Fittngs & Valves |  | 435.27 | 574.4049 | 3 | EACH | 191.4683 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 3290 | Concrete Collars |  | 1200 | 1583.5823 | 3 | EACH | 527.8608 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Valve Gate (08") 2020 |  | 569.27 | 751.2382 | 1 | EACH | 751.2382 |  | 0 | 751.2382 | 1 | 0% |  | 0 | 751.2382 | 1 | 0% |  | 0 | 751.2382 | 1 | 0% |  | 0 | 751.2382 | 1 | 0% |  | 0 | 751.2382 | 1 | 0%
| 6410 | Install Water Fittings & Valves |  | 169.27 | 223.3775 | 1 | EACH | 223.3775 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 3290 | Concrete Collars |  | 400 | 527.8608 | 1 | EACH | 527.8608 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Fire Hydrant 2020 |  | 2640.02 | 3483.9075 | 2 | EACH | 1741.9537 |  | 0 | 3483.9075 | 2 | 0% |  | 0 | 3483.9075 | 2 | 0% |  | 0 | 3483.9075 | 2 | 0% |  | 0 | 3483.9075 | 2 | 0% |  | 0 | 3483.9075 | 2 | 0%
| 6420 | Fire Hydrant |  | 967.27 | 1276.4597 | 2 | EACH | 638.2299 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 197.5 | 260.6313 | 10 | TON | 26.0631 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 84.78 | 111.8801 | 10 | TON | 11.188 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 3290 | Concrete Collars |  | 800 | 1055.7215 | 2 | EACH | 527.8608 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6415 | Thrust Blocks |  | 590.47 | 779.2149 | 2 | EACH | 389.6074 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Pressure Irrigation |  | 34466.87 | 45484.2711 |  |  |  |  | 0 | 45484.2843 | 0 |  |  | 0 | 45484.2843 | 0 |  |  | 0 | 45484.2843 | 0 |  |  | 0 | 45484.2843 | 0 |  |  | 0 | 45484.2843
|  | PI Connect To Exist |  | 4522.54 | 5968.1786 | 2 | EACH | 2984.0893 |  | 0 | 5968.1786 | 2 | 0% |  | 0 | 5968.1786 | 2 | 0% |  | 0 | 5968.1786 | 2 | 0% |  | 0 | 5968.1786 | 2 | 0% |  | 0 | 5968.1786 | 2 | 0%
| 6460 | Waterline Connections |  | 3936.54 | 5194.8626 | 2 | EACH | 2597.4313 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 6480 | Waterworks Materials |  | 586 | 773.316 | 1 | LS | 773.316 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | PI Main CL200 Purple 04" 2020 |  | 690.58 | 911.3252 | 35 | LF | 26.0379 |  | 0 | 911.3252 | 35 | 0% |  | 0 | 911.3252 | 35 | 0% |  | 0 | 911.3252 | 35 | 0% |  | 0 | 911.3252 | 35 | 0% |  | 0 | 911.3252 | 35 | 0%
| 6004 | 4" Waterline |  | 364.13 | 480.5249 | 35 | LF | 13.7293 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2180 | Import Bedding Sand |  | 121.59 | 160.4565 | 13.51 | TON | 11.8769 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 66.66 | 87.968 | 13.51 | TON | 6.5113 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 6490 | Waterline Testing |  | 26.81 | 35.3799 | 35 | LF | 1.0109 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 82.27 | 108.5678 | 9.7 | TON | 11.1926 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 29.11 | 38.4151 | 9.7 | TON | 3.9603 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | PI Main CL200 Purple 06" 2020 |  | 26628.88 | 35140.8526 | 1170 | LF | 30.0349 |  | 0 | 35140.8526 | 1170 | 0% |  | 0 | 35140.8526 | 1170 | 0% |  | 0 | 35140.8526 | 1170 | 0% |  | 0 | 35140.8526 | 1170 | 0% |  | 0 | 35140.8526 | 1170 | 0%
| 6006 | 6" Waterline |  | 12172.46 | 16063.4102 | 1170 | LF | 13.7294 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2180 | Import Bedding Sand |  | 4587.09 | 6053.3621 | 509.68 | TON | 11.8768 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 4321.17 | 5702.4403 | 509.68 | TON | 11.1883 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 6490 | Waterline Testing |  | 1195.98 | 1578.2773 | 1170 | LF | 1.349 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 3214.67 | 4242.2454 | 379.17 | TON | 11.1882 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 1137.5 | 1501.1041 | 379.17 | TON | 3.9589 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Fittings 06" 2020 |  | 2624.88 | 3463.9279 | 7 | EACH | 494.8468 |  | 0 | 3463.9279 | 7 | 0% |  | 0 | 3463.9279 | 7 | 0% |  | 0 | 3463.9279 | 7 | 0% |  | 0 | 3463.9279 | 7 | 0% |  | 0 | 3463.9279 | 7 | 0%
| 6410 | Install Water Fittings & Valves |  | 846.36 | 1116.9006 | 7 | EACH | 159.5572 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6415 | Thrust Blocks |  | 1778.52 | 2347.0273 | 7 | EACH | 335.2896 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Precast Materials |  | 68734 | 90704.9549 |  |  |  |  | 0 | 52608.8738 | 0 |  |  | 0 | 52608.8738 | 0 |  |  | 4535.2477 | 52608.8738 | 0 |  |  | 33560.8333 | 57144.1216 | 0 |  |  | 0 | 90704.9549
|  | Precast Materials |  | 68734 | 90704.9549 | 1 | LS | 90704.9549 |  | 0 | 52608.8738 | 0.58 | 42% | 0 | 0 | 52608.8738 | 0.58 | 42% | 0.05 | 4535.2477 | 52608.8738 | 0.58 | 42% | 0.37 | 33560.8333 | 57144.1216 | 0.63 | 37% |  | 0 | 90704.9549 | 1 | 0%
| 5490 | Precast Materials |  | 68734 | 90704.9549 | 1 | LS | 90704.9549 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Waterworks Materials |  | 226250 | 298571.2464 |  |  |  |  | 0 | 194071.3101 | 0 |  |  | 0 | 194071.3101 | 0 |  |  | 44785.687 | 194071.3101 | 0 |  |  | 32842.8371 | 238856.9971 | 0 |  |  | 26871.4122 | 271699.8342
|  | Waterworks Materials |  | 226250 | 298571.2464 | 1 | LS | 298571.2464 |  | 0 | 194071.3101 | 0.65 | 35% | 0 | 0 | 194071.3101 | 0.65 | 35% | 0.15 | 44785.687 | 194071.3101 | 0.65 | 35% | 0.11 | 32842.8371 | 238856.9971 | 0.8 | 20% | 0.09 | 26871.4122 | 271699.8342 | 0.91 | 9%
| 6480 | Waterworks Materials |  | 226250 | 298571.2464 | 1 | LS | 298571.2464 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | -583.2 |  | 583.2 |  | 0 | -583.2 |  | 0.09
|  | Concrete Collars |  | 5000 | 6598.2596 | [5 empty] | 6598.2596 | 0 |  |  |  | 6598.2596 | 0 |  |  |  | 6598.2596 | 0 |  |  | 0 | 6598.2596 | 0 |  |  | 0 | 6598.2596
|  | Concrete Collars |  | 5000 | 6598.2596 | 1 | LS | 6598.2596 |  |  | 6598.2596 | 1 | 0% |  |  | 6598.2596 | 1 | 0% |  |  | 6598.2596 | 1 | 0% |  | 0 | 6598.2596 | 1 | 0% |  | 0 | 6598.2596 | 1 | 0%
| 3290 | Concrete Collars |  | 5000 | 6598.2596 | 1 | LS | 6598.2596 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
5 |  | Building Earthwork | 748900 | 567925.57 | [5 empty] | 99267.64 | 261938.4327 | 0 |  |  | 206658.1595 | 361206.0727 | 0 |  |  | 34116.7679 | 567864.2322 | 0 |  |  | 125930.1768 | 601981.0002 | 0 |  |  | 20988.8494 | 727911.177
|  | Excavate Footings |  | 6872.5 | 9062.482 | 1205 | CY | 7.5207 | 200 | 1504.1464 | 4550.0428 | 605 | 49.79% |  | 0 | 6054.1892 | 805 | 33.2% |  | 0 | 6054.1892 | 805 | 33.2% | 200 | 1504.1464 | 6054.1892 | 805 | 33.2% | 200 | 1504.1464 | 7558.3356 | 1005 | 16.6%
| 2132 | Excavate Footings |  | 6872.5 | 9062.482 | 1205 | CY | 7.5207 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 200
|  | Backfill Footings |  | 16485.36 | 21738.5636 | 1024 | CY | 21.2291 | 225 | 4776.5398 | 16962.0237 | 799 | 21.97% |  | 0 | 21738.5636 | 1024 | 0% |  | 0 | 21738.5636 | 1024 | 0% |  | 0 | 21738.5636 | 1024 | 0% |  | 0 | 21738.5636 | 1024 | 0%
| 2133 | Backfill Footings |  | 16485.36 | 21738.5636 | 1024 | CY | 21.2291 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Under-Slab Gravel 4" 2020 |  | 13349.77 | 17603.7905 | 10845 | SF | 1.6232 | 5500 | 8927.6946 | 8676.0959 | 5345 | 50.71% |  | 0 | 17603.7905 | 10845 | 0% |  | 0 | 17603.7905 | 10845 | 0% |  | 0 | 17603.7905 | 10845 | 0% |  | 0 | 17603.7905 | 10845 | 0%
| 2152 | Building Floor Grading |  | 6206.61 | 8184.4003 | 10845 | SF | 0.75467 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2185 | Import Bedding Gravel |  | 4997.74 | 6590.3134 | 253.05 | TON | 26.0435 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 2145.42 | 2829.0768 | 253.05 | TON | 11.1799 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Cut To Waste Export 2020 9' To Remove Peat Beneath Buildings |  | 142572.49 | 188004.4559 | 7015 | CY | 26.8004 | 3000 | 80401.0503 | 45962.6004 | 1715 | 75.55% | 0 | 0 | 126363.6507 | 4715 | 32.79% | 1000 | 26800.3501 | 126363.6507 | 4715 | 32.79% | 1300 | 34840.4551 | 153164.0008 | 5715 | 18.53% |  | 0 | 188004.4559 | 7015 | 0%
| 2131 | Cut To Waste |  | 35517.49 | 46835.4476 | 7015 | CY | 6.6765 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 107055 | 141169.0083 | 12627 | TON | 11.1799 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Import A1A Compacted CY Top 6' Beneath Buildings |  | 162027.5 | 213658.9743 | 4675 | CY | 45.7025 |  | 0 | 76551.6111 | 1675 | 64.17% | 2000 | 91404.9088 | 76551.6111 | 1675 | 64.17% |  | 0 | 167956.5199 | 3675 | 21.39% | 600 | 27421.4726 | 167956.5199 | 3675 | 21.39% | 400 | 18280.9818 | 195377.9925 | 4275 | 8.556%
| 2129 | Place Fill |  | 17337.77 | 22862.6014 | 8415 | TON | 2.7169 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 720
| 2172 | Import Efill |  | 73345.17 | 96717.2473 | 8415 | TON | 11.4934 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 720
| 2149 | Import Trucking |  | 71344.57 | 94079.1387 | 8415 | TON | 11.1799 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 720
|  | Import Rock Compacted CY Bottom 3' Beneath Buildings |  | 191808.59 | 252930.068 | 2340 | CY | 108.0898 |  | 0 | 90795.409 | 840 | 64.1% | 1000 | 108089.7727 | 90795.409 | 840 | 64.1% |  | 0 | 198885.1817 | 1840 | 21.37% | 500 | 54044.8863 | 198885.1817 | 1840 | 21.37% |  | 0 | 252930.068 | 2340 | 0%
| 2129 | Place Fill |  | 8678.15 | 11443.5181 | 4212 | TON | 2.7169 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2188 | Import Rip Rap |  | 147420 | 194396.6672 | 4212 | TON | 46.1531 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 35710.43 | 47089.8696 | 4212 | TON | 11.1799 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Geotextile Separation Fabric (SY) 2020 |  | 10680.2 | 14083.5388 | 4680 | SY | 3.0093 |  | 0 | 10171.4447 | 3380 | 27.78% |  | 0 | 10171.4447 | 3380 | 27.78% |  | 0 | 10171.4447 | 3380 | 27.78% | 900 | 2708.3728 | 10171.4447 | 3380 | 27.78% | 400 | 1203.7213 | 12879.8175 | 4280 | 8.547%
| 2170 | Geo-Fabric |  | 10680.2 | 14083.5388 | 4680 | SY | 3.0093 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 400
|  | Dewatering |  | 13291.04 | 17526.3457 | 10 | DY | 1752.6346 | 1 | 1752.6346 | 3505.2691 | 2 | 80% | 3 | 5257.9037 | 5257.9037 | 3 | 70% | 2 | 3505.2691 | 10515.8074 | 6 | 40% | 2 | 3505.2691 | 14021.0765 | 8 | 20% |  | 0 | 17526.3457 | 10 | 0%
| 2600 | Dewatering |  | 13291.04 | 17526.3457 | 10 | DY | 1752.6346 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Well Point ADS Perf 08" |  | 10838.14 | 14291.8077 | 15 | EACH | 952.7872 | 2 | 1905.5744 | 4763.9359 | 5 | 66.67% | 2 | 1905.5744 | 6669.5103 | 7 | 53.33% | 4 | 3811.1487 | 8575.0846 | 9 | 40% | 2 | 1905.5744 | 12386.2334 | 13 | 13.33% |  | 0 | 14291.8077 | 15 | 0%
| 2105 | Potholing |  | 4671.56 | 6160.1933 | 15 | EACH | 410.6796 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2187 | Import 2" Rock |  | 3060 | 4035.0957 | 15 | EACH | 269.0064 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 1271.74 | 1676.991 | 15 | EACH | 111.7994 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 6480 | Waterworks Materials |  | 113.1 | 149.1403 | 1 | LS | 149.1403 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 1271.74 | 1676.991 | 150 | TON | 11.1799 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 450 | 593.3964 | 150 | TON | 3.956 |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
6 |  | Structural Concrete | 317600 | 240688.13 | [5 empty] | 61201.9613 | 152754.1522 | 0 |  |  | 45457.4302 | 213956.1135 | 0 |  |  | 58186.4827 | 259413.5437 | 0 |  |  | 0 | 317600.0264 | 0 |  |  | 0 | 317600.0264
|  | Structural Concrete - Building A |  | 106236.58 | 140184.4695 |  |  |  |  | 0 | 140184.4826 | 0 |  |  | 0 | 140184.4826 | 0 |  |  | 0 | 140184.4826 | 0 |  |  | 0 | 140184.4826 | 0 |  |  | 0 | 140184.4826
| 3110 | Footings |  | 40233.05 | 53089.5175 | 89 | CY | 596.5114 |  | 0 | 53089.5175 | 89 | 0% |  |  | 53089.5175 | 89 | 0% |  |  | 53089.5175 | 89 | 0% |  | 0 | 53089.5175 | 89 | 0% |  | 0 | 53089.5175 | 89 | 0%
|  | FTS2.0 (2.0') 2025 |  | 19091.46 | 25192.1343 | 560 | LF | 44.986 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | FC2.0 (2.0') 2025 |  | 16568.13 | 21862.4744 | 486 | LF | 44.9845 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | FC3.0 (3.0') 2025 |  | 1531.41 | 2020.7719 | 31 | LF | 65.1862 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | Footing Step 2025 |  | 3042.05 | 4014.1368 | 4 | EACH | 1003.5342 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| 3120 | Foundation Walls |  | 34491.35 | 45513.0577 | 56 | CY | 812.7332 |  | 0 | 45513.0577 | 56 | 0% |  |  | 45513.0577 | 56 | 0% |  |  | 45513.0577 | 56 | 0% |  | 0 | 45513.0577 | 56 | 0% |  | 0 | 45513.0577 | 56 | 0%
|  | CFW-1 (8") X (0.67') Symons 2020 |  | 923.84 | 1219.053 | 48 | LF | 25.3969 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | CFW-1 (8") X (2.50') Symons 2020 |  | 1854.11 | 2446.5907 | 36 | LF | 67.9609 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | CFW-2 (12") X (2.50') Symons 2020 |  | 12092.14 | 15956.1822 | 196 | LF | 81.4091 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | CFW-3 (16") X (2.50') Symons 2020 |  | 19621.25 | 25891.2186 | 284 | LF | 91.1663 |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| 3210 | Slab On Grade |  | 31512.19 | 41581.9074 | 6114 | SF | 6.8011 |  | 0 | 41581.9074 | 6114 | 0% |  |  | 41581.9074 | 6114 | 0% |  |  | 41581.9074 | 6114 | 0% |  | 0 | 41581.9074 | 6114 | 0% |  | 0 | 41581.9074 | 6114 | 0%
|  | Slab On Grade (4") 2025 |  | 30636.47 | 40426.3512 | 6114 | SF | 6.6121 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | Mechanical Concrete Pad (6") 2025 |  | 875.72 | 1155.5562 | 121 | SF | 9.5501 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | Structural Concrete - Building B |  | 48278.48 | 63705.8639 |  |  |  |  | 58389.4105 | 5316.4666 | 0 |  |  | 0 | 63705.8771 | 0 |  |  | 0 | 63705.8771 | 0 |  |  | 0 | 63705.8771 | 0 |  |  | 0 | 63705.8771
| 3110 | Footings |  | 19574.65 | 25829.7276 | 45 | CY | 573.9939 | 45 | 25829.7276 | 0 | 0 | 100% |  |  | 25829.7276 | 45 | 0% |  |  | 25829.7276 | 45 | 0% |  | 0 | 25829.7276 | 45 | 0% |  | 0 | 25829.7276 | 45 | 0%
|  | FTS2.0 (2.0') 2025 |  | 2795.53 | 3688.8414 | 82 | LF | 44.9859 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | FC2.0 (2.0') 2025 |  | 5931.8 | 7827.3061 | 174 | LF | 44.9845 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | FC3.0 (3.0') 2025 |  | 7805.27 | 10299.4433 | 158 | LF | 65.1864 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | Footing Step 2025 |  | 3042.05 | 4014.1368 | 4 | EACH | 1003.5342 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| 3120 | Foundation Walls |  | 14111.92 | 18621.3827 | 24 | CY | 775.8909 | 24 | 18621.3827 | 0 | 0 | 100% |  |  | 18621.3827 | 24 | 0% |  |  | 18621.3827 | 24 | 0% |  | 0 | 18621.3827 | 24 | 0% |  | 0 | 18621.3827 | 24 | 0%
|  | CFW-2 (12") X (2.50') Symons 2020 |  | 3886.76 | 5128.7738 | 63 | LF | 81.4091 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  | CFW-3 (16") X (2.50') Symons 2020 |  | 10225.16 | 13492.6089 | 148 | LF | 91.1663 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| 3210 | Slab On Grade |  | 10562.92 | 13938.3001 | 2108 | SF | 6.6121 | 2108 | 13938.3001 | 0 | 0 | 100% |  |  | 13938.3001 | 2108 | 0% |  |  | 13938.3001 | 2108 | 0% |  | 0 | 13938.3001 | 2108 | 0% |  | 0 | 13938.3001 | 2108 | 0%
| 3220 | Suspended Slabs |  | 3265.68 | 4309.2277 | 528 | SF | 8.1614 |  | 0 | 4309.2277 | 528 | 0% |  |  | 4309.2277 | 528 | 0% |  |  | 4309.2277 | 528 | 0% |  | 0 | 4309.2277 | 528 | 0% |  | 0 | 4309.2277 | 528 | 0%
| 3230 | Stairs & Landings |  | 763.32 | 1007.2388 | 76 | SF | 13.2531 |  | 0 | 1007.2388 | 76 | 0% |  |  | 1007.2388 | 76 | 0% |  |  | 1007.2388 | 76 | 0% |  | 0 | 1007.2388 | 76 | 0% |  | 0 | 1007.2388 | 76 | 0%
|  | Structural Concrete - Building C |  | 52720.01 | 69566.6844 |  |  |  |  | 0 | 0 | 0 |  |  | 34247.2983 | 0 | 0 |  |  | 35319.3861 | 34247.2983 | 0 |  |  | 0 | 69566.6844 | 0 |  |  | 0 | 69566.6844
| 3110 | Footings |  | 17017.22 | 22455.0711 | 38 | CY | 590.9229 |  | 0 | 0 | 0 | 100% | 8 | 4727.3834 | 0 | 0 | 100% | 30 | 17727.6877 | 4727.3834 | 8 | 78.95% |  | 0 | 22455.0711 | 38 | 0% |  | 0 | 22455.0711 | 38 | 0%
|  | FTS2.0 (2.0') 2025 |  | 1329.58 | 1754.4472 | 39 | LF | 44.9858 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | FC2.0 (2.0') 2025 |  | 11488.6 | 15159.7811 | 337 | LF | 44.9845 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | FC3.0 (3.0') 2025 |  | 4199.04 | 5540.8428 | 85 | LF | 65.1864 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
| 3120 | Foundation Walls |  | 26663.18 | 35183.3967 | 44 | CY | 799.6227 |  | 0 | 0 | 0 | 100% | 22 | 17591.6984 | 0 | 0 | 100% | 22 | 17591.6984 | 17591.6984 | 22 | 50% |  | 0 | 35183.3967 | 44 | 0% |  | 0 | 35183.3967 | 44 | 0%
|  | CFW-1 (8") X (2.50') Symons 2020 |  | 6489.22 | 8562.8497 | 126 | LF | 67.9591 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | CFW-3 (16") X (2.50') Symons 2020 |  | 20173.96 | 26620.5471 | 292 | LF | 91.1663 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
| 3210 | Slab On Grade |  | 9039.61 | 11928.2166 | 1804 | SF | 6.6121 |  | 0 | 0 | 0 | 100% | 1804 | 11928.2166 | 0 | 0 | 100% |  | 0 | 11928.2166 | 1804 | 0% |  | 0 | 11928.2166 | 1804 | 0% |  | 0 | 11928.2166 | 1804 | 0%
|  | Structural Concrete - Building D |  | 26669.43 | 35191.6439 |  |  |  |  | 2472.9238 | 0 | 0 |  |  | 10530.8777 | 2472.9238 | 0 |  |  | 22187.8424 | 13003.8015 | 0 |  |  | 0 | 35191.6439 | 0 |  |  | 0 | 35191.6439
| 3110 | Footings |  | 9594.31 | 12660.1709 | 20 | CY | 633.0085 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 20 | 12660.1709 | 0 | 0 | 100% |  | 0 | 12660.1709 | 20 | 0% |  | 0 | 12660.1709 | 20 | 0%
|  | FC2.0 (2.0') 2025 |  | 8249.97 | 10886.2472 | 242 | LF | 44.9845 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  | FS3.0 (3.0') 2025 |  | 1344.33 | 1773.9105 | 6 | EACH | 295.6518 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
| 3120 | Foundation Walls |  | 12353.49 | 16301.0466 | 15 | CY | 1086.7364 |  | 0 | 0 | 0 | 100% | 7.5 | 8150.5233 | 0 | 0 | 100% | 7.5 | 8150.5233 | 8150.5233 | 7.5 | 50% |  | 0 | 16301.0466 | 15 | 0% |  | 0 | 16301.0466 | 15 | 0%
| 3210 | Slab On Grade |  | 3677.98 | 4853.2782 | 734 | SF | 6.6121 | 374 | 2472.9238 | 0 | 0 | 100% | 360 | 2380.3544 | 2472.9238 | 374 | 49.05% |  | 0 | 4853.2782 | 734 | 0% |  | 0 | 4853.2782 | 734 | 0% |  | 0 | 4853.2782 | 734 | 0%
| 3100 | Misc. Structural Concrete |  | 1043.65 | 1377.1483 | 1 | LS | 1377.1483 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 1 | 1377.1483 | 0 | 0 | 100% |  | 0 | 1377.1483 | 1 | 0% |  | 0 | 1377.1483 | 1 | 0%
|  | Structural Concrete - Dumpster |  | 4209.81 | 5555.0544 |  |  |  |  | 0 | 5555.0676 | 0 |  |  | 0 | 5555.0676 | 0 |  |  | 0 | 5555.0676 | 0 |  |  | 0 | 5555.0676 | 0 |  |  | 0 | 5555.0676
| 3110 | Footings |  | 1538.73 | 2030.431 | 4 | CY | 507.6078 |  | 0 | 2030.431 | 4 | 0% |  | 0 | 2030.431 | 4 | 0% |  | 0 | 2030.431 | 4 | 0% |  | 0 | 2030.431 | 4 | 0% |  | 0 | 2030.431 | 4 | 0%
| 3120 | Foundation Walls |  | 1505.98 | 1987.2158 | 2 | CY | 993.6079 |  | 0 | 1987.2158 | 2 | 0% |  | 0 | 1987.2158 | 2 | 0% |  | 0 | 1987.2158 | 2 | 0% |  | 0 | 1987.2158 | 2 | 0% |  | 0 | 1987.2158 | 2 | 0%
| 3210 | Slab On Grade |  | 1165.11 | 1537.4208 | 82 | SF | 18.749 |  | 0 | 1537.4208 | 82 | 0% |  | 0 | 1537.4208 | 82 | 0% |  | 0 | 1537.4208 | 82 | 0% |  | 0 | 1537.4208 | 82 | 0% |  | 0 | 1537.4208 | 82 | 0%
|  | KSC Concrete Washout |  | 2573.81 | 3396.2708 |  |  |  |  | 339.6271 | 1698.1354 | 0 | 50% |  | 679.2542 | 2037.7625 | 0 | 40% |  | 679.2542 | 2717.0166 | 0 | 20% |  | 0 | 3396.2708 | 0 | 0% |  | 0 | 3396.2708 |  | 0%
| 2100 | SWPPP |  | 2573.81 | 3396.2708 | 1 | LS | 3396.2708 | 0.1 | 339.6271 | 1698.1354 | 0.5 | 50% | 0.2 | 679.2542 | 2037.7625 | 0.6 | 40% | 0.2 | 679.2542 | 2717.0166 | 0.8 | 20% |  | 0 | 3396.2708 | 1 | 0% |  | 0 | 3396.2708 | 1 | 0%
7 |  | Site Concrete Prep | 261500 | 182080.3 | [5 empty] | 0 | 250866.7274 | 0 |  |  | 0 | 250866.7274 | 0 |  |  | 1239.3092 | 250866.7274 | 0 |  |  | 9393.9635 | 252106.0365 | 0 |  |  | 0 | 261500
|  | Curb & Gutter Prep 24" (140/323) 2020 |  | 26649.08 | 38272.8632 | 4215 | LF | 9.0802 |  | 0 | 38272.8632 | 4215 | 0% |  | 0 | 38272.8632 | 4215 | 0% |  | 0 | 38272.8632 | 4215 | 0% |  | 0 | 38272.8632 | 4215 | 0% |  | 0 | 38272.8632 | 4215 | 0%
| 2155 | Prep Concrete Curbs |  | 19428.37 | 27902.6273 | 4215 | LF | 6.6198 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 4093.82 | 5879.4605 | 368.81 | TON | 15.9417 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 3126.89 | 4490.7754 | 368.81 | TON | 12.1764 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Concrete Curb Wall Prep 6"x12" |  | 334 | 479.684 | 35 | LF | 13.7053 |  | 0 | 479.684 | 35 | 0% |  | 0 | 479.684 | 35 | 0% |  | 0 | 479.684 | 35 | 0% |  | 0 | 479.684 | 35 | 0% |  | 0 | 479.684 | 35 | 0%
| 2155 | Prep Concrete Curbs |  | 302.02 | 433.7549 | 35 | LF | 12.393 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 18.13 | 26.0379 | 1.63 | TON | 15.9742 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 13.85 | 19.8911 | 1.63 | TON | 12.2031 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Prep Mow Curb 12"x6" |  | 4996.31 | 7175.5982 | 1158 | LF | 6.1965 |  | 0 | 7175.5982 | 1158 | 0% |  | 0 | 7175.5982 | 1158 | 0% |  | 0 | 7175.5982 | 1158 | 0% |  | 0 | 7175.5982 | 1158 | 0% |  | 0 | 7175.5982 | 1158 | 0%
| 2155 | Prep Concrete Curbs |  | 4996.31 | 7175.5982 | 1158 | LF | 6.1965 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Prep Mow Curb 12"x8" |  | 6817.06 | 9790.522 | 1580 | LF | 6.1965 |  | 0 | 9790.522 | 1580 | 0% |  | 0 | 9790.522 | 1580 | 0% |  | 0 | 9790.522 | 1580 | 0% |  | 0 | 9790.522 | 1580 | 0% |  | 0 | 9790.522 | 1580 | 0%
| 2155 | Prep Concrete Curbs |  | 6817.07 | 9790.5364 | 1580 | LF | 6.1965 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Prep Mow Curb 12"x12" |  | 3352.45 | 4814.7201 | 777 | LF | 6.1966 |  | 0 | 4814.7201 | 777 | 0% |  | 0 | 4814.7201 | 777 | 0% |  | 0 | 4814.7201 | 777 | 0% |  | 0 | 4814.7201 | 777 | 0% |  | 0 | 4814.7201 | 777 | 0%
| 2155 | Prep Concrete Curbs |  | 3352.45 | 4814.7201 | 777 | LF | 6.1966 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Prep Mow Curb 18"x6" |  | 7516.04 | 10794.3828 | 1742 | LF | 6.1965 |  | 0 | 161.1102 | 26 | 98.51% |  | 0 | 161.1102 | 26 | 98.51% | 200 | 1239.3092 | 161.1102 | 26 | 98.51% | 1516 | 9393.9635 | 1400.4194 | 226 | 87.03% |  | 0 | 10794.3828 | 1742 | 0%
| 2155 | Prep Concrete Curbs |  | 7516.04 | 10794.3828 | 1742 | LF | 6.1965 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Concrete Flatwork Prep UBC 05"/04" 2020 |  | 85966.2 | 123462.8969 | 53700 | SF | 2.2991 |  | 0 | 123462.8969 | 53700 | 0% |  | 0 | 123462.8969 | 53700 | 0% |  | 0 | 123462.8969 | 53700 | 0% |  | 0 | 123462.8969 | 53700 | 0% |  | 0 | 123462.8969 | 53700 | 0%
| 2156 | Prep Concrete Flatwork |  | 61785.09 | 88734.4816 | 53700 | SF | 1.6524 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 13709.61 | 19689.4613 | 1235.1 | TON | 15.9416 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 10471.5 | 15038.954 | 1235.1 | TON | 12.1763 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Heavy Duty Flatwork Prep UBC 6.5"/04" 2020 |  | 42839.02 | 61524.5237 | 26760 | SF | 2.2991 |  | 0 | 61524.5237 | 26760 | 0% |  | 0 | 61524.5237 | 26760 | 0% |  | 0 | 61524.5237 | 26760 | 0% |  | 0 | 61524.5237 | 26760 | 0% |  | 0 | 61524.5237 | 26760 | 0%
| 2156 | Prep Concrete Flatwork |  | 30788.99 | 44218.5172 | 26760 | SF | 1.6524 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 6831.83 | 9811.7344 | 615.48 | TON | 15.9416 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 5218.2 | 7494.272 | 615.48 | TON | 12.1763 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Raised Crosswalk Prep UBC 6.5"/04" 2020 |  | 1127.01 | 1618.5887 | 704 | SF | 2.2991 |  | 0 | 1618.5887 | 704 | 0% |  | 0 | 1618.5887 | 704 | 0% |  | 0 | 1618.5887 | 704 | 0% |  | 0 | 1618.5887 | 704 | 0% |  | 0 | 1618.5887 | 704 | 0%
| 2156 | Prep Concrete Flatwork |  | 809.99 | 1163.2911 | 704 | SF | 1.6524 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 179.73 | 258.1245 | 16.19 | TON | 15.9435 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 137.28 | 197.1587 | 16.19 | TON | 12.1778 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Pitcher's Mound Flatwork Prep UBC 04"/04" 2020 |  | 406.62 | 583.9793 | 254 | SF | 2.2991 |  | 0 | 583.9793 | 254 | 0% |  | 0 | 583.9793 | 254 | 0% |  | 0 | 583.9793 | 254 | 0% |  | 0 | 583.9793 | 254 | 0% |  | 0 | 583.9793 | 254 | 0%
| 2156 | Prep Concrete Flatwork |  | 292.24 | 419.7091 | 254 | SF | 1.6524 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 64.85 | 93.1362 | 5.84 | TON | 15.948 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 49.53 | 71.134 | 5.84 | TON | 12.1805 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Bollard Base Prep |  | 937.78 | 1346.8204 | 14 | EACH | 96.2015 |  | 0 | 1346.8204 | 14 | 0% |  | 0 | 1346.8204 | 14 | 0% |  | 0 | 1346.8204 | 14 | 0% |  | 0 | 1346.8204 | 14 | 0% |  | 0 | 1346.8204 | 14 | 0%
| 2105 | Bollard Base Prep |  | 937.78 | 1346.8204 | 14 | EACH | 96.2015 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Removable Bollard Base Prep |  | 1071.75 | 1539.2254 | 16 | EACH | 96.2016 |  | 0 | 1539.2254 | 16 | 0% |  | 0 | 1539.2254 | 16 | 0% |  | 0 | 1539.2254 | 16 | 0% |  | 0 | 1539.2254 | 16 | 0% |  | 0 | 1539.2254 | 16 | 0%
| 2105 | Removable Bollard Base Prep |  | 1071.75 | 1539.2254 | 16 | EACH | 96.2016 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Flagpole Base Prep |  | 66.98 | 96.1953 | 1 | EACH | 96.1953 |  | 0 | 96.1953 | 1 | 0% |  | 0 | 96.1953 | 1 | 0% |  | 0 | 96.1953 | 1 | 0% |  | 0 | 96.1953 | 1 | 0% |  | 0 | 96.1953 | 1 | 0%
| 2105 | Flagpole Base Prep |  | 66.98 | 96.1953 | 1 | EACH | 96.1953 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
8 |  | Site Concrete | 1367500 | 1026056.55 | [5 empty] | 0 | 1195393.5635 | 0 |  |  | 126090.6918 | 1195393.5635 | 0 |  |  | 5575.241 | 1321484.2553 | 0 |  |  | 40440.5038 | 1327059.4962 | 0 |  |  | 0 | 1367500
| 3251 | KSC Curb & Gutter 24" Slip Machine 2020 |  | 85070.89 | 113380.1466 | 4215 | LF | 26.8992 |  | 0 | 113380.1466 | 4215 | 0% |  | 0 | 113380.1466 | 4215 | 0% |  | 0 | 113380.1466 | 4215 | 0% |  | 0 | 113380.1466 | 4215 | 0% |  | 0 | 113380.1466 | 4215 | 0%
| 3251 | KSC Concrete Curb Wall 2020 |  | 598.2 | 797.2645 | 35 | LF | 22.779 |  | 0 | 797.2645 | 35 | 0% |  | 0 | 797.2645 | 35 | 0% |  | 0 | 797.2645 | 35 | 0% |  | 0 | 797.2645 | 35 | 0% |  | 0 | 797.2645 | 35 | 0%
| 3251 | Mow Curb 12"x06" 2020 |  | 20578.74 | 27426.7797 | 1158 | LF | 23.6846 |  | 0 | 27426.7797 | 1158 | 0% |  | 0 | 27426.7797 | 1158 | 0% |  | 0 | 27426.7797 | 1158 | 0% |  | 0 | 27426.7797 | 1158 | 0% |  | 0 | 27426.7797 | 1158 | 0%
| 3251 | Mow Curb 12"x08" 2020 |  | 44657.71 | 59518.5698 | 2318 | LF | 25.6767 |  | 0 | 59518.5698 | 2318 | 0% |  | 0 | 59518.5698 | 2318 | 0% |  | 0 | 59518.5698 | 2318 | 0% |  | 0 | 59518.5698 | 2318 | 0% |  | 0 | 59518.5698 | 2318 | 0%
| 3251 | Mow Curb 12"x12" 2020 |  | 17124.81 | 22823.4766 | 770 | LF | 29.6409 |  | 0 | 22823.4766 | 770 | 0% |  | 0 | 22823.4766 | 770 | 0% |  | 0 | 22823.4766 | 770 | 0% |  | 0 | 22823.4766 | 770 | 0% |  | 0 | 22823.4766 | 770 | 0%
| 3251 | Mow Curb 18"x06" 2020 |  | 34526.33 | 46015.7447 | 1725 | LF | 26.6758 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 209 | 5575.241 | 0 | 0 | 100% | 1516 | 40440.5038 | 5575.241 | 209 | 87.88% |  | 0 | 46015.7447 | 1725 | 0%
| 3254 | Concrete Flatwork (05" Thick) 2020 |  | 309399.62 | 412359.3191 | 53250 | SF | 7.7438 |  | 0 | 412359.3191 | 53250 | 0% |  | 0 | 412359.3191 | 53250 | 0% |  | 0 | 412359.3191 | 53250 | 0% |  | 0 | 412359.3191 | 53250 | 0% |  | 0 | 412359.3191 | 53250 | 0%
| 3254 | Heavy Duty Flatwork (06.5" Thick) 2020 |  | 185251.28 | 246897.82 | 26760 | SF | 9.2264 |  | 0 | 246897.82 | 26760 | 0% |  | 0 | 246897.82 | 26760 | 0% |  | 0 | 246897.82 | 26760 | 0% |  | 0 | 246897.82 | 26760 | 0% |  | 0 | 246897.82 | 26760 | 0%
| 3254 | Raised Crosswalk Flatwork (11" Thick) 2020 |  | 7598.37 | 10126.8989 | 704 | SF | 14.3848 |  | 0 | 10126.8989 | 704 | 0% |  | 0 | 10126.8989 | 704 | 0% |  | 0 | 10126.8989 | 704 | 0% |  | 0 | 10126.8989 | 704 | 0% |  | 0 | 10126.8989 | 704 | 0%
| 3251 | KSC Thickened Sidewalk Edge 2020 |  | 1140.91 | 1520.5735 | 68 | LF | 22.3614 |  | 0 | 1520.5735 | 68 | 0% |  | 0 | 1520.5735 | 68 | 0% |  | 0 | 1520.5735 | 68 | 0% |  | 0 | 1520.5735 | 68 | 0% |  | 0 | 1520.5735 | 68 | 0%
| 3251 | KSC Thickened Pitchers Mound Edge 2020 |  | 905.34 | 1206.6123 | 57 | LF | 21.1686 |  | 0 | 1206.6123 | 57 | 0% |  | 0 | 1206.6123 | 57 | 0% |  | 0 | 1206.6123 | 57 | 0% |  | 0 | 1206.6123 | 57 | 0% |  | 0 | 1206.6123 | 57 | 0%
| 3135 | Bollard Base 2020 |  | 5594.32 | 7455.9561 | 14 | EACH | 532.5683 |  | 0 | 7455.9561 | 14 | 0% |  | 0 | 7455.9561 | 14 | 0% |  | 0 | 7455.9561 | 14 | 0% |  | 0 | 7455.9561 | 14 | 0% |  | 0 | 7455.9561 | 14 | 0%
| 3135 | Removable Bollard Base 2020 |  | 6052.63 | 8066.7791 | 16 | EACH | 504.1737 |  | 0 | 8066.7791 | 16 | 0% |  | 0 | 8066.7791 | 16 | 0% |  | 0 | 8066.7791 | 16 | 0% |  | 0 | 8066.7791 | 16 | 0% |  | 0 | 8066.7791 | 16 | 0%
| 3135 | Flagpole Base 2020 |  | 400.2 | 533.3756 | 1 | EACH | 533.3756 |  | 0 | 533.3756 | 1 | 0% |  | 0 | 533.3756 | 1 | 0% |  | 0 | 533.3756 | 1 | 0% |  | 0 | 533.3756 | 1 | 0% |  | 0 | 533.3756 | 1 | 0%
| 3230 | Seating Stairs 2020 |  | 188657.77 | 251437.8964 | 5394 | SF | 46.6144 |  | 0 | 251437.8964 | 5394 | 0% |  | 0 | 251437.8964 | 5394 | 0% |  | 0 | 251437.8964 | 5394 | 0% |  | 0 | 251437.8964 | 5394 | 0% |  | 0 | 251437.8964 | 5394 | 0%
| 3260 | ADA Ramp |  | 23891.62 | 31842.0952 | 26 | EACH | 1224.696 |  | 0 | 31842.0952 | 26 | 0% |  | 0 | 31842.0952 | 26 | 0% |  | 0 | 31842.0952 | 26 | 0% |  | 0 | 31842.0952 | 26 | 0% |  | 0 | 31842.0952 | 26 | 0%
|  | Structural Concrete 2022 |  | 86886.38 | 115799.7818 |  |  |  |  | 0 | 0 | 0 |  |  | 115799.7818 | 0 | 0 |  |  | 0 | 115799.7818 | 0 |  |  | 0 | 115799.7818 | 0 |  |  | 0 | 115799.7818
| 3110 | Footings |  | 14805.47 | 19732.3239 | 29 | CY | 680.425 |  | 0 | 0 | 0 | 100% | 29 | 19732.3239 | 0 | 0 | 100% |  | 0 | 19732.3239 | 29 | 0% |  | 0 | 19732.3239 | 29 | 0% |  | 0 | 19732.3239 | 29 | 0%
|  | Backstop Footing (2.50') 2025 |  | 10655.48 | 14201.3312 | 230 | LF | 61.7449 |  | 0 | -14201.3312 | -230 | 200% | 230 | 14201.3312 | -14201.3312 | -230 | 200% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100%
|  | Steps Wall Waste Footing |  | 4149.98 | 5530.9794 | 175 | LF | 31.6056 |  | 0 | -5530.9794 | -175 |  | 175 | 5530.9794 | -5530.9794 | -175 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
| 3120 | Foundation Walls |  | 72080.91 | 96067.4579 | 85 | CY | 1130.2054 |  | 0 | 0 | 0 | 100% | 85 | 96067.4579 | 0 | 0 | 100% |  | 0 | 96067.4579 | 85 | 0% |  | 0 | 96067.4579 | 85 | 0% |  | 0 | 96067.4579 | 85 | 0%
|  | Backstop Foundation Wall (16") X (4.50') HDO 2020 |  | 39236.31 | 52293.0768 | 228 | LF | 229.3556 |  | 0 | -52293.0768 | -228 |  | 228 | 52293.0768 | -52293.0768 | -228 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
|  | Concrete Steps Wall (12") X (5.0') HDO 2020 |  | 32844.6 | 43774.3811 | 175 | LF | 250.1393 |  | 0 | -43774.3811 | -175 |  | 175 | 43774.3811 | -43774.3811 | -175 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
| 2100 | SWPPP |  | 7721.43 | 10290.9099 | 1 | LS | 10290.9099 |  | 0 | 0 | 0 | 100% | 1 | 10290.9099 | 0 | 0 | 100% |  | 0 | 10290.9099 | 1 | 0% |  | 0 | 10290.9099 | 1 | 0% |  | 0 | 10290.9099 | 1 | 0%
9 |  | Hot-Mix Asphalt (Prep) | 130300 | 100088.95 | [5 empty] | 0 | 130300 | 0 |  |  | 0 | 130300 | 0 |  |  | 0 | 130300 | 0 |  |  | 0 | 130300 | 0 |  |  | 0 | 130300
|  | Place Roadbase Parking 06" Light Duty(140/563/277/WT) |  | 30364.86 | 39530.2504 | 35580 | SF | 1.111 |  | 0 | 39530.2504 | 35580 | 0% |  | 0 | 39530.2504 | 35580 | 0% |  | 0 | 39530.2504 | 35580 | 0% |  | 0 | 39530.2504 | 35580 | 0% |  | 0 | 39530.2504 | 35580 | 0%
| 2157 | Base Under Parking Lot |  | 5908.09 | 7691.3998 | 35580 | SF | 0.21617 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 13822.83 | 17995.1408 | 1245.3 | TON | 14.4504 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 10557.98 | 13744.8219 | 1245.3 | TON | 11.0374 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 1410 | Construction Water |  | 75.96 | 98.8879 | 21.7 | MGAL | 4.557 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Place Roadbase Parking 08" Heavy Duty (140/563/277/WT) |  | 59547 | 77520.7863 | 57294 | SF | 1.353 |  | 0 | 77520.7863 | 57294 | 0% |  | 0 | 77520.7863 | 57294 | 0% |  | 0 | 77520.7863 | 57294 | 0% |  | 0 | 77520.7863 | 57294 | 0% |  | 0 | 77520.7863 | 57294 | 0%
| 2157 | Base Under Parking Lot |  | 11416.46 | 14862.4273 | 57294 | SF | 0.25941 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 29821.38 | 38822.7253 | 2673.72 | TON | 14.5201 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Import Trucking |  | 18309.17 | 23835.6467 | 2673.72 | TON | 8.9148 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
|  | Place Roadbase Trail 06" Asphalt Trail(140/563/277/WT) |  | 10177.09 | 13248.9633 | 11925 | SF | 1.111 |  | 0 | 13248.9633 | 11925 | 0% |  | 0 | 13248.9633 | 11925 | 0% |  | 0 | 13248.9633 | 11925 | 0% |  | 0 | 13248.9633 | 11925 | 0% |  | 0 | 13248.9633 | 11925 | 0%
| 2157 | Base Under Parking Lot |  | 1980.16 | 2577.8555 | 11925 | SF | 0.21617 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 4632.86 | 6031.2518 | 417.38 | TON | 14.4503 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 3538.61 | 4606.7112 | 417.38 | TON | 11.0372 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 1410 | Construction Water |  | 25.46 | 33.1449 | 7.27 | MGAL | 4.5591 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
10 |  | Hot-Mix Asphalt Paving | 230200 | 194782.17 | [5 empty] | 0 | 230200 | 0 |  |  | 0 | 230200 | 0 |  |  | 0 | 230200 | 0 |  |  | 0 | 230200 | 0 |  |  | 0 | 230200
| 7530 | Asphalt Paving Sub |  | 194782.17 | 230200 | 1 | LS | 230200 |  | 0 | 230200 | 1 | 0% |  | 0 | 230200 | 1 | 0% |  | 0 | 230200 | 1 | 0% |  | 0 | 230200 | 1 | 0% |  | 0 | 230200 | 1 | 0%
11 |  | Pavement Markings - Striping | 2910 | 2600 | [5 empty] | 0 | 2910 | 0 |  |  | 0 | 2910 | 0 |  |  | 0 | 2910 | 0 |  |  | 0 | 2910 | 0 |  |  | 0 | 2910
| 7525 | Striping Sub |  | 2600 | 2910 | 1 | LS | 2910 |  | 0 | 2910 | 1 | 0% |  | 0 | 2910 | 1 | 0% |  | 0 | 2910 | 1 | 0% |  | 0 | 2910 | 1 | 0% |  | 0 | 2910 | 1 | 0%
12 |  | Exterior Sports Equipment | 818500 | 643178.31 | [5 empty] | 0 | 693759.1094 | 0 |  |  | 17114.28 | 693759.1094 | 0 |  |  | 75946.1763 | 710873.3894 | 0 |  |  | 31680.4343 | 786819.5657 | 0 |  |  | 0 | 818500
|  | Baseball Sports Equipment Install |  | 284978.66 | 362659.98 |  |  |  |  | 0 | 255312.118 | 0 |  |  | 11356.45 | 255312.118 | 0 |  |  | 75946.1763 | 266668.568 | 0 |  |  | 20045.2558 | 342614.7442 | 0 |  |  | 0 | 362660
|  | Backstop Pads |  | 16090.75 | 20476.87 | 43 | EACH | 476.2063 |  | 0 | 20476.87 | 43 | 0% |  | 0 | 20476.87 | 43 | 0% |  | 0 | 20476.87 | 43 | 0% |  | 0 | 20476.87 | 43 | 0% |  | 0 | 20476.87 | 43 | 0%
| 2705 | Misc. Equipment Install |  | 3862.88 | 4915.85 | 1 | LS | 4915.85 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment |  | 12227.86 | 15561.01 | 1 | LS | 15561.01 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Foul Pole |  | 11188.74 | 14238.64 | 2 | EACH | 7119.32 |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0%
| 2705 | Misc. Equipment Install |  | 2673.7 | 3402.51 | 1 | LS | 3402.51 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 8515.04 | 10836.12 | 1 | LS | 10836.12 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Dugout Sports Equipment |  | 16793.69 | 21371.42 | 2 | EACH | 10685.71 |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0%
| 2705 | Misc. Equipment Install |  | 2575.25 | 3277.23 | 1 | LS | 3277.23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 14218.44 | 18094.19 | 1 | LS | 18094.19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Batting Cage/Netting |  | 68204.11 | 86795.63 | 4 | EACH | 21698.9075 |  | 0 | 10849.4538 | 0.5 | 87.5% |  | 0 | 10849.4538 | 0.5 | 87.5% | 3.5 | 75946.1763 | 10849.4538 | 0.5 | 87.5% |  | 0 | 86795.63 | 4 | 0% |  | 0 | 86795.63 | 4 | 0%
| 2705 | Misc. Equipment Install |  | 4259.27 | 5420.29 | 1 | LS | 5420.29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 63944.84 | 81375.34 | 1 | LS | 81375.34 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Batting Cage Poles |  | 15150.56 | 19280.4 | 10 | EACH | 1928.04 |  | 0 | 19280.4 | 10 | 0% |  | 0 | 19280.4 | 10 | 0% |  | 0 | 19280.4 | 10 | 0% |  | 0 | 19280.4 | 10 | 0% |  | 0 | 19280.4 | 10 | 0%
| 2705 | Misc. Equipment Install |  | 8031.56 | 10220.85 | 1 | LS | 10220.85 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 7119 | 9059.54 | 1 | LS | 9059.54 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Dugout Leaning Pole Padding |  | 3936.39 | 5009.4 | 100 | LF | 50.094 |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0%
| 2705 | Misc. Equipment Install |  | 643.81 | 819.3 | 1 | LS | 819.3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 3292.58 | 4190.09 | 1 | LS | 4190.09 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Fence Top Guard Cap W/Ties |  | 3518.26 | 4477.29 | 1054 | LF | 4.2479 |  | 0 | 4477.29 | 1054 | 0% |  | 0 | 4477.29 | 1054 | 0% |  | 0 | 4477.29 | 1054 | 0% |  | 0 | 4477.29 | 1054 | 0% |  | 0 | 4477.29 | 1054 | 0%
| 2705 | Misc. Equipment Install |  | 1221.52 | 1554.49 | 1 | LS | 1554.49 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 2296.74 | 2922.8 | 1 | LS | 2922.8 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Batters Box |  | 1579.09 | 2009.53 | 100 | SF | 20.0953 |  | 0 | 0 | 0 | 100% | 100 | 2009.53 | 0 | 0 | 100% |  | 0 | 2009.53 | 100 | 0% |  | 0 | 2009.53 | 100 | 0% |  | 0 | 2009.53 | 100 | 0%
| 2156 | Prep Concrete Flatwork |  | 287.64 | 366.05 | 100 | SF | 3.6605 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 38.85 | 49.44 | 3.5 | TON | 14.1257 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 19.78 | 25.17 | 3.5 | TON | 7.1914 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 3254 | Concrete Flatwork |  | 780.81 | 993.65 | 100 | SF | 9.9365 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 3710 | Nailer Board |  | 452.02 | 575.23 | 50 | LF | 11.5046 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Pitchers Mound |  | 6027.36 | 7670.34 | 1 | EACH | 7670.34 |  | 0 | 0 | 0 | 100% | 1 | 7670.34 | 0 | 0 | 100% |  | 0 | 7670.34 | 1 | 0% |  | 0 | 7670.34 | 1 | 0% |  | 0 | 7670.34 | 1 | 0%
| 2156 | Prep Concrete Flatwork |  | 1052.07 | 1338.85 | 254 | SF | 5.2711 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 180.91 | 230.22 | 16.3 | TON | 14.1239 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 92.12 | 117.23 | 16.3 | TON | 7.192 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 3254 | Concrete Flatwork |  | 2218.94 | 2823.79 | 254 | SF | 11.1173 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 3710 | Nailer Board |  | 1012.52 | 1288.52 | 112 | LF | 11.5046 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 3251 | Concrete Curbs |  | 1470.79 | 1871.71 | 60 | LF | 31.1952 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Pitchers Rubber |  | 1317.46 | 1676.58 | 4 | EACH | 419.145 |  | 0 | 0 | 0 | 100% | 4 | 1676.58 | 0 | 0 | 100% |  | 0 | 1676.58 | 4 | 0% |  | 0 | 1676.58 | 4 | 0% |  | 0 | 1676.58 | 4 | 0%
| 2705 | Misc. Equipment Install |  | 356.49 | 453.66 | 1 | LS | 453.66 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 960.97 | 1222.92 | 1 | LS | 1222.92 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Home Plates |  | 2609.75 | 3321.13 | 4 | EACH | 830.2825 |  | 0 | 3321.13 | 4 | 0% |  | 0 | 3321.13 | 4 | 0% |  | 0 | 3321.13 | 4 | 0% |  | 0 | 3321.13 | 4 | 0% |  | 0 | 3321.13 | 4 | 0%
| 2705 | Misc. Equipment Install |  | 1487.75 | 1893.29 | 1 | LS | 1893.29 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 1122 | 1427.84 | 1 | LS | 1427.84 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Bases (W/ In-ground Mounting Sleeves) |  | 2048.76 | 2607.22 | 3 | EACH | 869.0733 |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0%
| 2705 | Misc. Equipment Install |  | 1115.81 | 1419.96 | 1 | LS | 1419.96 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 932.95 | 1187.26 | 1 | LS | 1187.26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Baseball Backstop Netting |  | 136513.75 | 173725.55 | 156 | LF | 1113.6253 |  | 0 | 153680.2942 | 138 | 11.54% |  | 0 | 153680.2942 | 138 | 11.54% |  | 0 | 153680.2942 | 138 | 11.54% | 18 | 20045.2558 | 153680.2942 | 138 | 11.54% |  | 0 | 173725.55 | 156 | 0%
| 2705 | Misc. Equipment Install |  | 31877.07 | 40566.33 | 1 | LS | 40566.33 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 104636.68 | 133159.22 | 1 | LS | 133159.22 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Softball Sports Equipment Install |  | 130965.25 | 166664.6 |  |  |  |  | 0 | 149271.5915 | 0 |  |  | 5757.83 | 149271.5915 | 0 |  |  | 0 | 155029.4215 | 0 |  |  | 11635.1785 | 155029.4215 | 0 |  |  | 0 | 166664.6
|  | Backstop Pads |  | 9355.08 | 11905.15 | 25 | EACH | 476.206 |  | 0 | 11905.15 | 25 | 0% |  | 0 | 11905.15 | 25 | 0% |  | 0 | 11905.15 | 25 | 0% |  | 0 | 11905.15 | 25 | 0% |  | 0 | 11905.15 | 25 | 0%
| 2705 | Misc. Equipment Install |  | 2245.86 | 2858.05 | 1 | LS | 2858.05 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 7109.22 | 9047.1 | 1 | LS | 9047.1 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Foul Pole |  | 11188.74 | 14238.64 | 2 | EACH | 7119.32 |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0% |  | 0 | 14238.64 | 2 | 0%
| 2705 | Misc. Equipment Install |  | 2673.7 | 3402.51 | 1 | LS | 3402.51 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 8515.04 | 10836.12 | 1 | LS | 10836.12 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Dugout Sports Equipment |  | 16793.69 | 21371.42 | 2 | EACH | 10685.71 |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0% |  | 0 | 21371.42 | 2 | 0%
| 2705 | Misc. Equipment Install |  | 2575.25 | 3277.23 | 1 | LS | 3277.23 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 14218.44 | 18094.19 | 1 | LS | 18094.19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Dugout Leaning Pole Padding |  | 3936.39 | 5009.4 | 100 | LF | 50.094 |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0% |  | 0 | 5009.4 | 100 | 0%
| 2705 | Misc. Equipment Install |  | 643.81 | 819.3 | 1 | LS | 819.3 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 3292.58 | 4190.09 | 1 | LS | 4190.09 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Fence Top Guard Cap W/Ties |  | 2203.08 | 2803.61 | 660 | LF | 4.2479 |  | 0 | 2803.61 | 660 | 0% |  | 0 | 2803.61 | 660 | 0% |  | 0 | 2803.61 | 660 | 0% |  | 0 | 2803.61 | 660 | 0% |  | 0 | 2803.61 | 660 | 0%
| 2705 | Misc. Equipment Install |  | 764.9 | 973.4 | 1 | LS | 973.4 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 1438.19 | 1830.22 | 1 | LS | 1830.22 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Batters Box |  | 1579.09 | 2009.53 | 100 | SF | 20.0953 |  | 0 | 0 | 0 | 100% | 100 | 2009.53 | 0 | 0 | 100% |  | 0 | 2009.53 | 100 | 0% |  | 0 | 2009.53 | 100 | 0% |  | 0 | 2009.53 | 100 | 0%
| 2156 | Prep Concrete Flatwork |  | 287.64 | 366.05 | 100 | SF | 3.6605 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 38.85 | 49.44 | 3.5 | TON | 14.1257 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 19.78 | 25.17 | 3.5 | TON | 7.1914 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 3254 | Concrete Flatwork |  | 780.81 | 993.65 | 100 | SF | 9.9365 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 3710 | Nailer Board |  | 452.02 | 575.23 | 50 | LF | 11.5046 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | Pitchers Rubber |  | 988.1 | 1257.44 | 3 | EACH | 419.1467 |  | 0 | 0 | 0 | 100% | 3 | 1257.44 | 0 | 0 | 100% |  | 0 | 1257.44 | 3 | 0% |  | 0 | 1257.44 | 3 | 0% |  | 0 | 1257.44 | 3 | 0%
| 2705 | Misc. Equipment Install |  | 267.37 | 340.25 | 1 | LS | 340.25 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 720.73 | 917.19 | 1 | LS | 917.19 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Home Plates |  | 1957.32 | 2490.86 | 3 | EACH | 830.2867 |  | 0 | 0 | 0 | 100% | 3 | 2490.86 | 0 | 0 | 100% |  | 0 | 2490.86 | 3 | 0% |  | 0 | 2490.86 | 3 | 0% |  | 0 | 2490.86 | 3 | 0%
| 2705 | Misc. Equipment Install |  | 1115.81 | 1419.96 | 1 | LS | 1419.96 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 841.5 | 1070.88 | 1 | LS | 1070.88 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Bases (W/ In-ground Mounting Sleeves) |  | 2048.76 | 2607.22 | 3 | EACH | 869.0733 |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0% |  | 0 | 2607.22 | 3 | 0%
| 2705 | Misc. Equipment Install |  | 1115.81 | 1419.96 | 1 | LS | 1419.96 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
| 2700 | Athletic Field Equipment Materials |  | 932.95 | 1187.26 | 1 | LS | 1187.26 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Softball Backstop Netting |  | 80915 | 102971.33 | 177 | LF | 581.7589 |  | 0 | 91336.1515 | 157 | 11.3% |  | 0 | 91336.1515 | 157 | 11.3% |  | 0 | 91336.1515 | 157 | 11.3% | 20 | 11635.1785 | 91336.1515 | 157 | 11.3% |  | 0 | 102971.33 | 177 | 0%
| 2700 | Athletic Field Equipment Materials |  | 54897.99 | 69862.44 | 1 | LS | 69862.44 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
| 2705 | Misc. Equipment Install |  | 26017.01 | 33108.89 | 1 | LS | 33108.89 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Soccer Sports Equipment Install |  | 227234.39 | 289175.4 |  |  |  |  | 0 | 289175.4 | 0 |  |  | 0 | 289175.4 | 0 |  |  | 0 | 289175.4 | 0 |  |  | 0 | 289175.4 | 0 |  |  | 0 | 289175.4
|  | Soccer Field 20' Netting |  | 191976.83 | 244307.11 | 740 | LF | 330.1447 |  | 0 | 244307.11 | 740 | 0% |  | 0 | 244307.11 | 740 | 0% |  | 0 | 244307.11 | 740 | 0% |  | 0 | 244307.11 | 740 | 0% |  | 0 | 244307.11 | 740 | 0%
| 2700 | Athletic Field Equipment Materials |  | 78195.79 | 99510.9 | 1 | LS | 99510.9 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
| 2705 | Misc. Equipment Install |  | 113781.03 | 144796.2 | 1 | LS | 144796.2 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Soccer Goals |  | 23465.82 | 29862.28 | 4 | EACH | 7465.57 |  | 0 | 29862.28 | 4 | 0% |  | 0 | 29862.28 | 4 | 0% |  | 0 | 29862.28 | 4 | 0% |  | 0 | 29862.28 | 4 | 0% |  | 0 | 29862.28 | 4 | 0%
| 2700 | Athletic Field Equipment Materials |  | 22435.72 | 28551.39 | 1 | LS | 28551.39 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
| 2705 | Misc. Equipment Install |  | 1030.1 | 1310.89 | 1 | LS | 1310.89 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Lacrosse Goals |  | 11791.74 | 15006.01 | 4 | EACH | 3751.5025 |  | 0 | 15006.01 | 4 | 0% |  | 0 | 15006.01 | 4 | 0% |  | 0 | 15006.01 | 4 | 0% |  | 0 | 15006.01 | 4 | 0% |  | 0 | 15006.01 | 4 | 0%
| 2700 | Athletic Field Equipment Materials |  | 11276.69 | 14350.5629 | 1 | LS | 14350.5629 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
| 2705 | Misc. Equipment Install |  | 515.05 | 655.4456 | 1 | LS | 655.4456 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
13 |  | Turf Field Prep | 2424100 | 1467853.7 | 2424100.02 |  |  |  |  | 0 | 1478973.3574 | 0 | 38.99% |  | 50000 | 1478973.3574 | 0 | 38.99% |  | 332329.4684 | 1478973.3574 | 0 | 38.99% |  | 506215.8685 | 1714302.8259 | 0 |  |  | 203581.3257 | 2220518.6943
|  | 6" Blended Gravel Under Turf |  | 485168.44 | 801235.72 | 347206 | SF | 2.3077 |  | 0 | 523463.2197 | 226836.5802 | 34.67% |  | 0 | 523463.2197 | 226836.5802 | 34.67% | 1000 | 2307.6667 | 523463.2197 | 226836.5802 | 34.67% | 31149.8659 | 71883.5079 | 525770.8864 | 227836.5802 | 34.38% | 88219.5539 | 203581.3257 | 597654.3943 | 258986.4461 | 25.41%
| 2732 | Place Field Drainage Gravel |  | 144134.58 | 238032.3294 | 347206 | SF | 0.68557 | 20000 | 13711.3028 | -14187.1933 | 238292.2881 |  |  | 0 | -475.8905 | 258292.2881 |  |  | 0 | -475.8905 | 258292.2881 |  | 694.158 | 475.8905 | -475.8905 | 258292.2881 |  | 88219.5539 |  |  | 258986.4461
| 2734 | Field Drainage Material |  | 137870.87 | 227688.07 | 347206 | SF | 0.65577 | 0 | 0 | 0 | 179206 |  | 0 | 0 | 0 | 179206 |  | 0 | 0 | 0 | 179206 |  |  | 0 | 0 | 179206 |  | 168000 | 110169.7429 |  | 179206
| 2149 | Import Trucking |  | 176039.98 | 290722.7849 | 12213.94 | TON | 23.8025 |  | 0 | -71407.6174 | 6213.94 |  |  | 0 | -71407.6174 | 6213.94 |  |  | 0 | -71407.6174 | 6213.94 |  | 3000 | 71407.6174 | -71407.6174 | 6213.94 |  | 3000 | 71407.6174 |  | 9213.94
| 2220 | Screen Processing |  | 27123 | 44792.5187 | 12213.94 | TON | 3.6673 |  | 0 | 0 | 6213.94 |  |  | 0 | 0 | 6213.94 |  |  | 0 | 0 | 6213.94 |  |  | 0 | 0 | 6213.94 |  | 6000 | 22003.9653 |  | 6213.94
|  | FENCE - NO CO YET SO BILLING IT HERE FOR NOW | [8 empty] | -147000 | 0 |  |  | 50000 | -147000 | 0 |  |  | 54000 | -97000 | 0 |  |  | 43000 | -43000 | 0
|  | Roadbase Football Field 08" |  | 367577.76 | 607039.55 | 347206 | SF | 1.7484 |  | 0 | 344786.2119 | 197206 | 43.2% |  | 0 | 344786.2119 | 197206 | 43.2% | 20000 | 34967.1117 | 344786.2119 | 197206 | 43.2% | 130000 | 227286.2263 | 379753.3237 | 217206 | 37.44% |  | 0 | 607039.55 | 347206 | 0%
| 2165 | Place Base Under Field |  | 50805.42 | 83903.06 | 347206 | SF | 0.24165 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2183 | Import Road Base |  | 179595.78 | 296595.04 | 16179.8 | TON | 18.3312 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 2149 | Import Trucking |  | 137176.56 | 226541.45 | 16179.8 | TON | 14.0015 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | HDPE Liner Football Field |  | 183832.69 | 303592.12 | 347206 | SF | 0.87439 |  | 0 | 303592.12 | 347206 | 0% |  | 0 | 303592.12 | 347206 | 0% |  | 0 | 303592.12 | 347206 | 0% |  | 0 | 303592.12 | 347206 | 0% |  | 0 | 303592.12 | 347206 | 0%
| 2733 | Place Field Liner |  | 183832.69 | 303592.12 | 46525.6 | SY | 6.5253 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
|  | Geotextile Football Field Below Liner |  | 35278.15 | 58260.41 | 347206 | SF | 0.1678 |  | 0 | 33929.7261 | 202206 | 41.76% |  | 0 | 33929.7261 | 202206 | 41.76% |  | 0 | 33929.7261 | 202206 | 41.76% | 145000 | 24330.6839 | 33929.7261 | 202206 | 41.76% |  | 0 | 58260.41 | 347206 | 0%
| 2731 | Place Field Geotextile |  | 35278.15 | 58260.41 | 46525.6 | SY | 1.2522 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Geotextile Football Field Above Liner |  | 35278.15 | 58260.41 | 347206 | SF | 0.1678 |  | 0 | 32889.3796 | 196006 | 43.55% |  | 0 | 32889.3796 | 196006 | 43.55% | 151200 | 25371.0304 | 32889.3796 | 196006 | 43.55% |  | 0 | 58260.41 | 347206 | 0% |  | 0 | 58260.41 | 347206 | 0%
| 2731 | Place Field Geotextile |  | 35278.15 | 58260.41 | 46525.6 | SY | 1.2522 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Geotextile Filter Fabric Below Road Base |  | 35278.15 | 58260.41 | 347206 | SF | 0.1678 |  | 0 | 32889.3796 | 196006 | 43.55% |  | 0 | 32889.3796 | 196006 | 43.55% | 151200 | 25371.0304 | 32889.3796 | 196006 | 43.55% |  | 0 | 58260.41 | 347206 | 0% |  | 0 | 58260.41 | 347206 | 0%
| 2731 | Place Field Geotextile |  | 35278.15 | 58260.41 | 46525.6 | SY | 1.2522 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Football Field Drainage |  | 277418.24 | 458144.81 | 1 | LS | 458144.81 |  | 0 | 153497.2282 | 0.43 | 66.5% |  | 0 | 153497.2282 | 0.43 | 66.5% | 0.36 | 164932.1316 | 153497.2282 | 0.43 | 66.5% | 0.21 | 139715.4502 | 318429.3598 | 0.79 | 30.5% |  | 0 | 458144.81 | 1 | 0%
| 5012 | 12" Storm Drain |  | 164220.84 | 271203.96 | 4233 | LF | 64.069 |  | 0 | -166130.8453 | -2593 | 161.3% |  | 0 | -166130.8453 | -2593 | 161.3% | 900 | 57662.0751 | -166130.8453 | -2593 | 161.3% | 1693 | 108468.7702 | -108468.7702 | -1693 |  | 0
| 2185 | Import Bedding Gravel |  | 44869.06 | 74099.41 | 2271.85 | TON | 32.6163 |  | 0 | -13046.5321 | -400 | 117.6% |  | 0 | -13046.5321 | -400 | 117.6% |  | 0 | -13046.5321 | -400 | 117.6% | 400 | 13046.5321 | -13046.5321 | -400 |  | 0
| 2149 | Import Trucking |  | 19261.35 | 31809.33 | 2271.85 | TON | 14.0015 |  | 0 | -5600.6039 | -400 | 117.6% |  | 0 | -5600.6039 | -400 | 117.6% |  | 0 | -5600.6039 | -400 | 117.6% | 400 | 5600.6039 | -5600.6039 | -400 |  | 0
| 2735 | Field Flat Panel Drain |  | 10920.28 | 18034.39 | 9518 | LF | 1.8948 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 |  | 0
| 6480 | Waterworks Materials |  | 38146.71 | 62997.72 | 1 | LS | 62997.72 |  | 0 | -12599.544 | -0.2 | 120% |  | 0 | -12599.544 | -0.2 | 120% |  | 0 | -12599.544 | -0.2 | 120% | 0.2 | 12599.544 | -12599.544 | -0.2 |  | 0
|  | Nailer Board |  | 48022.14 | 79306.59 | 5312 | LF | 14.9297 |  | 0 | 53926.0924 | 3612 | 32% |  | 0 | 53926.0924 | 3612 | 32% | 1700 | 25380.4976 | 53926.0924 | 3612 | 32% |  | 0 | 79306.59 | 5312 | 0% |  | 0 | 79306.59 | 5312 | 0%
| 2736 | Nailer Board |  | 48022.14 | 79306.59 | 5312 | LF | 14.9297 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
14 |  | Segmented Retaining Wall | 63300 | 55729.67 | [5 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 63300 | 0 | 0 |  |  | 0 | 63300
| 2185 | Import Bedding Gravel |  | 1975 | 2243.28 | 100 | TON | 22.4328 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 100 | 2243.28 | 0 | 0 | 100% |  | 0 | 2243.28 | 100 | 0%
| 2149 | Import Trucking |  | 847.83 | 963 | 100 | TON | 9.63 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 100 | 963 | 0 | 0 | 100% |  | 0 | 963 | 100 | 0%
|  | Leveling Pad |  | 1731.85 | 1967.1 | 100 | LF | 19.671 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 100 | 1967.1 | 0 | 0 | 100% |  | 0 | 1967.1 | 100 | 0%
| 2156 | Prep Concrete Flatwork |  | 1139.05 | 1293.78 | 600 | SF | 2.1563 |  | 0 | -1293.78 | -600 |  |  | 0 | -1293.78 | -600 |  |  | 0 | -1293.78 | -600 |  | 600 | 1293.78 | -1293.78 | -600 |  | 0
| 2183 | Import Road Base |  | 414.75 | 471.09 | 21 | TON | 22.4329 |  | 0 | -471.09 | -21 |  |  | 0 | -471.09 | -21 |  |  | 0 | -471.09 | -21 |  | 21 | 471.09 | -471.09 | -21 |  | 0
| 2149 | Import Trucking |  | 178.04 | 202.22 | 21 | TON | 9.6295 |  | 0 | -202.22 | -21 |  |  | 0 | -202.22 | -21 |  |  | 0 | -202.22 | -21 |  | 21 | 202.22 | -202.22 | -21 |  | 0
| 7875 | Retaining Wall Sub |  | 51175 | 58126.62 | 1 | LS | 58126.62 |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% |  | 0 | 0 | 0 | 100% | 1 | 58126.62 | 0 | 0 | 100% |  | 0 | 58126.62 | 1 | 0%
15 |  | Concrete Sign Wall - Tilt Panel | 24700 | 18826.44 | [5 empty] | 0 | 24700 | 0 |  |  | 0 | 24700 | 0 |  |  | 0 | 24700 | 0 |  |  | 0 | 24700 | 0 |  |  | 0 | 24700
| 3250 | Misc. Site Concrete |  | 16537.44 | 21696.8672 | 406 | SF | 53.4406 |  | 0 | 21696.8672 | 406 | 0% |  | 0 | 21696.8672 | 406 | 0% |  | 0 | 21696.8672 | 406 | 0% |  | 0 | 21696.8672 | 406 | 0% |  | 0 | 21696.8672 | 406 | 0%
| 3254 | Concrete Flatwork |  | 2289 | 3003.1328 | 450 | SF | 6.6736 |  | 0 | 3003.1328 | 450 | 0% |  | 0 | 3003.1328 | 450 | 0% |  | 0 | 3003.1328 | 450 | 0% |  | 0 | 3003.1328 | 450 | 0% |  | 0 | 3003.1328 | 450 | 0%
16 |  | Baseball & Softball Scoreboards | 63000 | 48008.81 | [5 empty] | 0 | 63000 | 0 |  |  | 0 | 63000 | 0 |  |  | 0 | 63000 | 0 |  |  | 0 | 63000 | 0 |  |  | 0 | 63000
| 2105 | Potholing |  | 5003.99 | 6566.5316 | 4 | EACH | 1641.6329 |  | 0 | 6566.5316 | 4 | 0% |  | 0 | 6566.5316 | 4 | 0% |  | 0 | 6566.5316 | 4 | 0% |  | 0 | 6566.5316 | 4 | 0% |  | 0 | 6566.5316 | 4 | 0%
| 3130 | Concrete Pole Base |  | 11723.72 | 15384.5588 | 4 | EACH | 3846.1397 |  | 0 | 15384.5588 | 4 | 0% |  | 0 | 15384.5588 | 4 | 0% |  | 0 | 15384.5588 | 4 | 0% |  | 0 | 15384.5588 | 4 | 0% |  | 0 | 15384.5588 | 4 | 0%
| 2705 | Misc. Equipment Install |  | 5353.9 | 7025.7042 | 1 | LS | 7025.7042 |  | 0 | 7025.7042 | 1 | 0% |  | 0 | 7025.7042 | 1 | 0% |  | 0 | 7025.7042 | 1 | 0% |  | 0 | 7025.7042 | 1 | 0% |  | 0 | 7025.7042 | 1 | 0%
| 2700 | Athletic Field Equipment Materials |  | 25927.2 | 34023.2053 | 1 | LS | 34023.2053 |  | 0 | 34023.2053 | 1 | 0% |  | 0 | 34023.2053 | 1 | 0% |  | 0 | 34023.2053 | 1 | 0% |  | 0 | 34023.2053 | 1 | 0% |  | 0 | 34023.2053 | 1 | 0%
17 |  | Soccer Scoreboards | 65000 | 50561.79 | [5 empty] | 0 | 65000 | 0 |  |  | 0 | 65000 | 0 |  |  | 0 | 65000 | 0 |  |  | 0 | 65000 | 0 |  |  | 0 | 65000
| 2105 | Potholing |  | 5003.99 | 6432.9081 | 4 | EACH | 1608.227 |  | 0 | 6432.9081 | 4 | 0% |  | 0 | 6432.9081 | 4 | 0% |  | 0 | 6432.9081 | 4 | 0% |  | 0 | 6432.9081 | 4 | 0% |  | 0 | 6432.9081 | 4 | 0%
| 3130 | Concrete Pole Base |  | 11723.72 | 15071.4957 | 4 | EACH | 3767.8739 |  | 0 | 15071.4957 | 4 | 0% |  | 0 | 15071.4957 | 4 | 0% |  | 0 | 15071.4957 | 4 | 0% |  | 0 | 15071.4957 | 4 | 0% |  | 0 | 15071.4957 | 4 | 0%
| 2705 | Misc. Equipment Install |  | 5353.9 | 6882.7369 | 2 | EACH | 3441.3685 |  | 0 | 6882.7369 | 2 | 0% |  | 0 | 6882.7369 | 2 | 0% |  | 0 | 6882.7369 | 2 | 0% |  | 0 | 6882.7369 | 2 | 0% |  | 0 | 6882.7369 | 2 | 0%
| 2700 | Athletic Field Equipment Materials |  | 28480.18 | 36612.8592 | 1 | LS | 36612.8592 |  | 0 | 36612.8592 | 1 | 0% |  | 0 | 36612.8592 | 1 | 0% |  | 0 | 36612.8592 | 1 | 0% |  | 0 | 36612.8592 | 1 | 0% |  | 0 | 36612.8592 | 1 | 0%
18 |  | Building Demo (Concrete Slabs And Footings) | 398000 | 320945.35 | [5 empty] | 9045.4545 | 388954.5455 | 0 |  |  | 0 | 398000 | 0 |  |  | 0 | 398000 | 0 |  |  | 0 | 398000 | 0 |  |  | 0 | 398000
|  | Demolition Building & Foundation (SF) 2020 |  | 320945.35 | 398000 | 8800 | CY | 45.2273 | 200 | 9045.4545 | 388954.5455 | 8600 | 2.273% |  | 0 | 398000 | 8800 | 0% |  | 0 | 398000 | 8800 | 0% |  | 0 | 398000 | 8800 | 0% |  | 0 | 398000 | 8800 | 0%
| 2470 | Building Demolition |  | 62586.24 | 77612.3521 | 8800 | CY | 8.8196 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2490 | Dump Fees |  | 208890 | 259041.6717 | 18568 | TON | 13.951 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
| 2150 | Export Trucking |  | 49469.11 | 61345.9761 | 18568 | TON | 3.3039 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
19 |  | Hazwoper Training | 100000 | 81601.06 | [5 empty] | 10000 | 55000 | 0 |  |  | 5000 | 65000 | 0 |  |  | 10000 | 70000 | 0 |  |  | 10000 | 80000 | 0 |  |  | 10000 | 90000
| 1400 | Training |  | 81601.06 | 100000 | 1 | LS | 100000 | 0.1 | 10000 | 55000 | 0.55 | 45% | 0.05 | 5000 | 65000 | 0.65 | 35% | 0.1 | 10000 | 70000 | 0.7 | 30% | 0.1 | 10000 | 80000 | 0.8 | 20% | 0.1 | 10000 | 90000 | 0.9 | 10%
0

## Sheet1 (hidden)
Item # | Job Cost ID | Description | Total Direct Cost | Quantity | UM | Total Bid Price | Total Plug | Total Labor | Total Equip. | Total Material | Total Subcontracted | Total Trucking
1 |  | Temporary Erosion & Sediment Control | 29138.0845 | 1 | LS | 40400 | 0 | 9053.2677 | 5871.251 | 9278.9553 | 0 | 4934.6105
| 2100 | SWPPP | 29138.0845 | 1 | LS |  | 0 | 9053.2677 | 5871.251 | 9278.9553 | 0 | 4934.6105
2 |  | Site Demolition | 422513.3554 | 1 | LS | 582300 | 0 | 124610.3209 | 152212.8239 | 44681.6308 | 16900 | 84108.5799
| 2402 | Tree Removal | 16900 | 1 | LS |  | 0 | 0 | 0 | 0 | 16900 | 0
|  | Remove Concrete Flatwork 04" | 16075.1163 | 17303 | SF |  | 0 | 3351.4377 | 3312.2886 | 2850.6692 | 0 | 6560.7208
| 2420 | Remove Concrete Flatwork | 6663.7263 | 17303 | SF |  | 0 | 3351.4377 | 3312.2886 | 0 | 0 | 0
| 2490 | Dump Fees | 2850.6692 | 432.575 | TON |  | 0 | 0 | 0 | 2850.6692 | 0 | 0
| 2150 | Export Trucking | 6560.7208 | 432.575 | TON |  | 0 | 0 | 0 | 0 | 0 | 6560.7208
|  | Remove Asphalt SF (03") | 98784.182 | 147064 | SF |  | 0 | 19939.495 | 19706.576 | 17316.786 | 0 | 41821.325
| 2410 | Remove Asphalt | 39646.071 | 147064 | SF |  | 0 | 19939.495 | 19706.576 | 0 | 0 | 0
| 2490 | Dump Fees | 17316.786 | 2757.45 | TON |  | 0 | 0 | 0 | 17316.786 | 0 | 0
| 2150 | Export Trucking | 41821.325 | 2757.45 | TON |  | 0 | 0 | 0 | 0 | 0 | 41821.325
|  | Remove Curb/Gutter 24" | 11787.9046 | 1634 | LF |  | 0 | 3164.9131 | 4356.9443 | 1292.1672 | 0 | 2973.88
| 2421 | Remove Curb And Gutter | 7521.8574 | 1634 | LF |  | 0 | 3164.9131 | 4356.9443 | 0 | 0 | 0
| 2490 | Dump Fees | 1292.1672 | 196.08 | TON |  | 0 | 0 | 0 | 1292.1672 | 0 | 0
| 2150 | Export Trucking | 2973.88 | 196.08 | TON |  | 0 | 0 | 0 | 0 | 0 | 2973.88
|  | Remove Chain Link Fence | 2487.3841 | 811 | LF |  | 0 | 1721.9898 | 700 | 50.6875 | 0 | 14.7067
| 2401 | Remove Fence | 2421.9898 | 811 | LF |  | 0 | 1721.9898 | 700 | 0 | 0 | 0
| 2490 | Dump Fees | 50.6875 | 2.0275 | TON |  | 0 | 0 | 0 | 50.6875 | 0 | 0
| 2150 | Export Trucking | 14.7067 | 2.0275 | TON |  | 0 | 0 | 0 | 0 | 0 | 14.7067
|  | Remove PVC Pipe (08") WATER | 159088.0209 | 3367 | LF |  | 0 | 56348.0178 | 74276.02 | 11858.0498 | 0 | 16605.9333
| 2450 | Remove Pipe | 130624.0378 | 3367 | LF |  | 0 | 56348.0178 | 74276.02 | 0 | 0 | 0
| 2490 | Dump Fees | 480.6393 | 19.2256 | TON |  | 0 | 0 | 0 | 480.6393 | 0 | 0
| 2150 | Export Trucking | 139.455 | 19.2256 | TON |  | 0 | 0 | 0 | 0 | 0 | 139.455
| 2172 | Import Efill | 8464.1105 | 971.1 | TON |  | 0 | 0 | 0 | 8464.1105 | 0 | 0
| 2149 | Import Trucking | 8233.2391 | 971.1 | TON |  | 0 | 0 | 0 | 0 | 0 | 8233.2391
| 2150 | Export Trucking | 8233.2391 | 971.1 | TON |  | 0 | 0 | 0 | 0 | 0 | 8233.2391
| 2490 | Dump Fees | 2913.3 | 971.1 | TON |  | 0 | 0 | 0 | 2913.3 | 0 | 0
|  | Remove PVC Pipe (08") SEWER | 63206.4417 | 691 | LF |  | 0 | 17346.2193 | 22865.19 | 9442.7384 | 0 | 13552.2939
| 2450 | Remove Pipe | 40211.4093 | 691 | LF |  | 0 | 17346.2193 | 22865.19 | 0 | 0 | 0
| 2490 | Dump Fees | 98.6402 | 3.9456 | TON |  | 0 | 0 | 0 | 98.6402 | 0 | 0
| 2150 | Export Trucking | 28.62 | 3.9456 | TON |  | 0 | 0 | 0 | 0 | 0 | 28.62
| 2172 | Import Efill | 6951.4482 | 797.55 | TON |  | 0 | 0 | 0 | 6951.4482 | 0 | 0
| 2149 | Import Trucking | 6761.837 | 797.55 | TON |  | 0 | 0 | 0 | 0 | 0 | 6761.837
| 2150 | Export Trucking | 6761.837 | 797.55 | TON |  | 0 | 0 | 0 | 0 | 0 | 6761.837
| 2490 | Dump Fees | 2392.65 | 797.55 | TON |  | 0 | 0 | 0 | 2392.65 | 0 | 0
|  | Remove Pipe RCP 15" | 32781.9987 | 1069 | LF |  | 0 | 13417.5893 | 17686.605 | 648.2683 | 0 | 1029.5361
| 2450 | Remove Pipe | 31104.1943 | 1069 | LF |  | 0 | 13417.5893 | 17686.605 | 0 | 0 | 0
| 2490 | Dump Fees | 648.2683 | 67.8815 | TON |  | 0 | 0 | 0 | 648.2683 | 0 | 0
| 2150 | Export Trucking | 1029.5361 | 67.8815 | TON |  | 0 | 0 | 0 | 0 | 0 | 1029.5361
|  | Remove Light Pole/Base | 2652.0203 | 12 | EACH |  | 0 | 1084.6703 | 1493.2 | 28.65 | 0 | 45.5
| 2435 | Remove Pole Base | 2577.8703 | 12 | EACH |  | 0 | 1084.6703 | 1493.2 | 0 | 0 | 0
| 2490 | Dump Fees | 28.65 | 3 | TON |  | 0 | 0 | 0 | 28.65 | 0 | 0
| 2150 | Export Trucking | 45.5 | 3 | TON |  | 0 | 0 | 0 | 0 | 0 | 45.5
|  | Remove Fire Hydrant | 2446.8078 | 5 | EACH |  | 0 | 1850.681 | 567.5 | 25 | 0 | 3.6268
| 2400 | Misc. Demolition | 2418.181 | 1 | LS |  | 0 | 1850.681 | 567.5 | 0 | 0 | 0
| 2490 | Dump Fees | 25 | 0.5 | TON |  | 0 | 0 | 0 | 25 | 0 | 0
| 2150 | Export Trucking | 3.6268 | 0.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 3.6268
|  | Remove Concrete Greast Trap | 1253.0033 | 1 | EACH |  | 0 | 406.7514 | 402 | 170.0272 | 0 | 274.2246
| 2456 | Remove Catch Basin | 808.7514 | 1 | EACH |  | 0 | 406.7514 | 402 | 0 | 0 | 0
| 2490 | Dump Fees | 32.95 | 5 | TON |  | 0 | 0 | 0 | 32.95 | 0 | 0
| 2150 | Export Trucking | 75.8333 | 5 | TON |  | 0 | 0 | 0 | 0 | 0 | 75.8333
| 2172 | Import Efill | 101.9772 | 11.7 | TON |  | 0 | 0 | 0 | 101.9772 | 0 | 0
| 2149 | Import Trucking | 99.1957 | 11.7 | TON |  | 0 | 0 | 0 | 0 | 0 | 99.1957
| 2150 | Export Trucking | 99.1957 | 11.7 | TON |  | 0 | 0 | 0 | 0 | 0 | 99.1957
| 2490 | Dump Fees | 35.1 | 11.7 | TON |  | 0 | 0 | 0 | 35.1 | 0 | 0
|  | Remove Catch Basin 2020 | 2601.6699 | 7 | EACH |  | 0 | 949.0866 | 1306.55 | 133.7 | 0 | 212.3333
| 2456 | Remove Catch Basin | 2255.6366 | 7 | EACH |  | 0 | 949.0866 | 1306.55 | 0 | 0 | 0
| 2490 | Dump Fees | 133.7 | 7 | TON |  | 0 | 0 | 0 | 133.7 | 0 | 0
| 2150 | Export Trucking | 212.3333 | 7 | TON |  | 0 | 0 | 0 | 0 | 0 | 212.3333
|  | Remove Manhole 60" | 5217.7986 | 5 | EACH |  | 0 | 2033.7569 | 2010 | 453.625 | 0 | 720.4167
| 2455 | Remove Manhole | 4043.7569 | 5 | EACH |  | 0 | 2033.7569 | 2010 | 0 | 0 | 0
| 2490 | Dump Fees | 453.625 | 47.5 | TON |  | 0 | 0 | 0 | 453.625 | 0 | 0
| 2150 | Export Trucking | 720.4167 | 47.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 720.4167
|  | Remove Water Meter 2020 | 1298.5391 | 2 | EACH |  | 0 | 555.2043 | 170.25 | 340.592 | 0 | 232.4928
| 2400 | Misc. Demolition | 725.4543 | 1 | LS |  | 0 | 555.2043 | 170.25 | 0 | 0 | 0
| 2490 | Dump Fees | 200 | 4 | TON |  | 0 | 0 | 0 | 200 | 0 | 0
| 2150 | Export Trucking | 29.0145 | 4 | TON |  | 0 | 0 | 0 | 0 | 0 | 29.0145
| 2172 | Import Efill | 104.592 | 12 | TON |  | 0 | 0 | 0 | 104.592 | 0 | 0
| 2149 | Import Trucking | 101.7391 | 12 | TON |  | 0 | 0 | 0 | 0 | 0 | 101.7391
| 2150 | Export Trucking | 101.7391 | 12 | TON |  | 0 | 0 | 0 | 0 | 0 | 101.7391
| 2490 | Dump Fees | 36 | 12 | TON |  | 0 | 0 | 0 | 36 | 0 | 0
|  | Remove Basketball Standard | 991.418 | 4 | EACH |  | 0 | 406.7514 | 559.95 | 9.55 | 0 | 15.1667
| 2435 | Remove Pole Base | 966.7014 | 4 | EACH |  | 0 | 406.7514 | 559.95 | 0 | 0 | 0
| 2490 | Dump Fees | 9.55 | 1 | TON |  | 0 | 0 | 0 | 9.55 | 0 | 0
| 2150 | Export Trucking | 15.1667 | 1 | TON |  | 0 | 0 | 0 | 0 | 0 | 15.1667
|  | Demo Bollard | 4941.0501 | 32 | EACH |  | 0 | 2033.7569 | 2799.75 | 61.12 | 0 | 46.4232
| 2400 | Misc. Demolition | 4833.5069 | 1 | LS |  | 0 | 2033.7569 | 2799.75 | 0 | 0 | 0
| 2490 | Dump Fees | 61.12 | 6.4 | TON |  | 0 | 0 | 0 | 61.12 | 0 | 0
| 2150 | Export Trucking | 46.4232 | 6.4 | TON |  | 0 | 0 | 0 | 0 | 0 | 46.4232
3 |  | Site Earthwork | 912203.6686 | 1 | LS | 1267100 | 0 | 100773.1758 | 227535.1592 | 156571.4858 | 0 | 427323.8478
|  | Strip & Stockpile Topsoil Onsite Phase 1 | 16412.9402 | 4500 | CY |  | 0 | 4241.5116 | 12171.4286 | 0 | 0 | 0
| 2120 | Strip Topsoil | 16412.9402 | 4500 | CY |  | 0 | 4241.5116 | 12171.4286 | 0 | 0 | 0
|  | KSC Cut To Fill (D8/D6/621/563) Phase 1 | 29598.1138 | 3033 | CY |  | 0 | 6927.8023 | 22320 | 350.3115 | 0 | 0
| 2130 | Cut To Fill | 29598.1138 | 3033 | CY |  | 0 | 6927.8023 | 22320 | 350.3115 | 0 | 0
|  | Import A1A Compacted CY Phase 1 | 336393.3416 | 9706 | CY |  | 0 | 16166.4384 | 19829.358 | 152275.5452 | 0 | 148122
| 2129 | Place Fill | 35995.7964 | 17470.8 | TON |  | 0 | 16166.4384 | 19829.358 | 0 | 0 | 0
| 2172 | Import Efill | 152275.5452 | 17470.8 | TON |  | 0 | 0 | 0 | 152275.5452 | 0 | 0
| 2149 | Import Trucking | 148122 | 17470.8 | TON |  | 0 | 0 | 0 | 0 | 0 | 148122
|  | Fine Grade Roadway (140/563) Phase 1 | 28753.2354 | 309531 | SF |  | 0 | 12729.8473 | 15373.373 | 650.0151 | 0 | 0
| 2135 | Fine Grade | 28103.2203 | 309531 | SF |  | 0 | 12729.8473 | 15373.373 | 0 | 0 | 0
| 1410 | Construction Water | 650.0151 | 185.7186 | MGAL |  | 0 | 0 | 0 | 650.0151 | 0 | 0
|  | KSC Cut To Fill (D8/D6/621/563) Phase 2 | 14824.0626 | 1733 | CY |  | 0 | 3463.9011 | 11160 | 200.1615 | 0 | 0
| 2130 | Cut To Fill | 14824.0626 | 1733 | CY |  | 0 | 3463.9011 | 11160 | 200.1615 | 0 | 0
|  | KSC Cut To Stockpile Phase 2 | 143821.3544 | 18818 | CY |  | 0 | 31039.8532 | 110608.0222 | 2173.479 | 0 | 0
| 2130 | Cut To Fill | 143821.3544 | 18818 | CY |  | 0 | 31039.8532 | 110608.0222 | 2173.479 | 0 | 0
|  | Load & Export Spoils | 301617.3817 | 18818 | CY |  | 0 | 8147.9615 | 14267.5724 | 0 | 0 | 279201.8478
| 2500 | Loading Trucks | 22415.5338 | 32931.5 | TON |  | 0 | 8147.9615 | 14267.5724 | 0 | 0 | 0
| 2150 | Export Trucking | 279201.8478 | 32931.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 279201.8478
|  | Fine Grade Roadway (140/563) Phase 2 | 40783.2388 | 439035 | SF |  | 0 | 18055.8603 | 21805.405 | 921.9735 | 0 | 0
| 2135 | Fine Grade | 39861.2653 | 439035 | SF |  | 0 | 18055.8603 | 21805.405 | 0 | 0 | 0
| 1410 | Construction Water | 921.9735 | 263.421 | MGAL |  | 0 | 0 | 0 | 921.9735 | 0 | 0
4 |  | Utilities (CW,FL,SD,SS,IRR) | 921076.2191 | 1 | LS | 1215500 | 580 | 209804.4095 | 197248.9083 | 424193.7437 | 19671.4 | 69577.7576
|  | Sewer | 234127.9529 | 1 | LS |  | 0 | 75531.4352 | 79530.82 | 54378.4406 | 9603.4 | 15083.857
|  | Sewer Wye Connection 24 FT Deep | 14472.0378 | 1 | EACH |  | 0 | 6413.0378 | 8059 | 0 | 0 | 0
| 4410 | Sewer Fittings & Connections | 14472.0378 | 1 | EACH |  | 0 | 6413.0378 | 8059 | 0 | 0 | 0
|  | SS Lateral Pipe SDR-35 06" | 110918.5531 | 732 | LF |  | 0 | 31295.6244 | 39327.92 | 35009.4453 | 570.96 | 4714.6034
| 4006 | 6" Sanitary Sewer | 98623.5444 | 732 | LF |  | 0 | 31295.6244 | 39327.92 | 28000 | 0 | 0
| 2185 | Import Bedding Gravel | 6297.7787 | 318.8749 | TON |  | 0 | 0 | 0 | 6297.7787 | 0 | 0
| 2149 | Import Trucking | 2703.3715 | 318.8592 | TON |  | 0 | 0 | 0 | 0 | 0 | 2703.3715
| 4490 | Sewer Line Testing | 570.96 | 732 | LF |  | 0 | 0 | 0 | 0 | 570.96 | 0
| 2150 | Export Trucking | 2011.2319 | 237.2222 | TON |  | 0 | 0 | 0 | 0 | 0 | 2011.2319
| 2490 | Dump Fees | 711.6667 | 237.2222 | TON |  | 0 | 0 | 0 | 711.6667 | 0 | 0
|  | SS Lateral Pipe SDR-35 04" | 23177.3365 | 298 | LF |  | 0 | 8521.101 | 10228.5 | 2519.5853 | 232.44 | 1675.7102
| 4404 | 4" Sanitary Sewer | 18749.601 | 298 | LF |  | 0 | 8521.101 | 10228.5 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 2271.7119 | 115.0234 | TON |  | 0 | 0 | 0 | 2271.7119 | 0 | 0
| 2185 | Import Trucking | 975.1983 | 115.0234 | TON |  | 0 | 0 | 0 | 0 | 0 | 975.1983
| 4490 | Sewer Line Testing | 232.44 | 298 | LF |  | 0 | 0 | 0 | 0 | 232.44 | 0
| 2150 | Export Trucking | 700.5119 | 82.6245 | TON |  | 0 | 0 | 0 | 0 | 0 | 700.5119
| 2490 | Dump Fees | 247.8735 | 82.6245 | TON |  | 0 | 0 | 0 | 247.8735 | 0 | 0
|  | SD Cleanout 06" | 10584.2511 | 12 | EACH |  | 0 | 2220.8171 | 1449 | 2104.26 | 4800 | 10.1739
| 4410 | Sewer Fittings & Connections | 3669.8171 | 12 | EACH |  | 0 | 2220.8171 | 1449 | 0 | 0 | 0
| 2185 | Iimport Bedding Gravel | 23.7 | 1.2 | TON |  | 0 | 0 | 0 | 23.7 | 0 | 0
| 2149 | Import Trucking | 10.1739 | 1.2 | TON |  | 0 | 0 | 0 | 0 | 0 | 10.1739
| 6480 | Waterworks Materials | 2080.56 | 1 | LS |  | 0 | 0 | 0 | 2080.56 | 0 | 0
| 3290 | Concrete Collars | 4800 | 12 | EACH |  | 0 | 0 | 0 | 0 | 4800 | 0
|  | SD Cleanout 04" | 7774.2092 | 10 | EACH |  | 0 | 1850.681 | 1207.5 | 707.55 | 4000 | 8.4783
| 4410 | Sewer Fittings & Connections | 3058.181 | 10 | EACH |  | 0 | 1850.681 | 1207.5 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 19.75 | 1 | TON |  | 0 | 0 | 0 | 19.75 | 0 | 0
| 2149 | Import Trucking | 8.4783 | 1 | TON |  | 0 | 0 | 0 | 0 | 0 | 8.4783
| 6480 | Waterworks Materials | 687.8 | 1 | LS |  | 0 | 0 | 0 | 687.8 | 0 | 0
| 3290 | Concrete Collars | 4000 | 10 | EACH |  | 0 | 0 | 0 | 0 | 4000 | 0
|  | SS (WYE) 06x04" | 315.6317 | 4 | EACH |  | 0 | 141.6317 | 134 | 40 | 0 | 0
| 4410 | Sewer Fittings & Connections | 275.6317 | 4 | EACH |  | 0 | 141.6317 | 134 | 0 | 0 | 0
| 6480 | Waterworks Materials | 40 | 1 | EACH |  | 0 | 0 | 0 | 40 | 0 | 0
|  | SS (WYE) 04x04" 2021 | 216.7237 | 3 | EACH |  | 0 | 106.2237 | 100.5 | 10 | 0 | 0
| 4410 | Sewer Fittings & Connections | 206.7237 | 3 | EACH |  | 0 | 106.2237 | 100.5 | 0 | 0 | 0
| 6480 | Waterworks Materials | 10 | 1 | EACH |  | 0 | 0 | 0 | 10 | 0 | 0
|  | SS Connect To Exist Stub | 1249.9734 | 2 | EACH |  | 0 | 568.0734 | 681.9 | 0 | 0 | 0
| 4410 | Sewer Fittings & Connections | 1249.9734 | 2 | EACH |  | 0 | 568.0734 | 681.9 | 0 | 0 | 0
|  | SS Grease Interceptor (600 Gal) | 10123.9636 | 1 | EACH |  | 0 | 1850.681 | 1866.5 | 4514.5 | 0 | 1892.2826
| 4430 | Grease Interceptor | 3717.181 | 1 | EACH |  | 0 | 1850.681 | 1866.5 | 0 | 0 | 0
| 5490 | Precast Materials | 4370 | 1 | LS |  | 0 | 0 | 0 | 4220 | 0 | 150
| 2185 | Import Bedding Gravel | 158 | 8 | TON |  | 0 | 0 | 0 | 158 | 0 | 0
| 2149 | Import Trucking | 1356.5217 | 8 | TON |  | 0 | 0 | 0 | 0 | 0 | 1356.5217
| 2150 | Export Trucking | 385.7609 | 45.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 385.7609
| 2490 | Dump Fees | 136.5 | 45.5 | TON |  | 0 | 0 | 0 | 136.5 | 0 | 0
| 2600 | Dewatering (4in Submersible Pump At Wellpoint 24/7) | 26582.0758 | 20 | DY |  | 0 | 14646.0758 | 11936 | 0 | 0 | 0
|  | Well Point ADS Perf 08" | 28713.197 | 40 | EACH |  | 0 | 7917.4883 | 4540 | 9473.1 | 0 | 6782.6087
| 2105 | Potholing | 12457.4883 | 40 | EACH |  | 0 | 7917.4883 | 4540 | 0 | 0 | 0
| 2187 | Import 2" Rock | 8160 | 40 | EACH |  | 0 | 0 | 0 | 8160 | 0 | 0
| 2149 | Import Trucking | 3391.3043 | 40 | EACH |  | 0 | 0 | 0 | 0 | 0 | 3391.3043
| 6480 | Waterworks Materials | 113.1 | 1 | LS |  | 0 | 0 | 0 | 113.1 | 0 | 0
| 2150 | Export Trucking | 3391.3043 | 400 | TON |  | 0 | 0 | 0 | 0 | 0 | 3391.3043
| 2490 | Dump Fees | 1200 | 400 | TON |  | 0 | 0 | 0 | 1200 | 0 | 0
|  | Storm Drain | 246594.955 | 1 | LS |  | 580 | 88555.5228 | 88067.85 | 46577.1333 | 1868 | 20946.4489
|  | SD PVC SDR 04" | 1790.834 | 25 | LF |  | 0 | 801.6297 | 637.25 | 211.3746 | 0 | 140.5797
| 5004 | 4" Storm Drain | 1438.8797 | 25 | LF |  | 0 | 801.6297 | 637.25 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 190.5799 | 9.6496 | TON |  | 0 | 0 | 0 | 190.5799 | 0 | 0
| 2149 | Import Trucking | 81.8119 | 9.6496 | TON |  | 0 | 0 | 0 | 0 | 0 | 81.8119
| 2150 | Export Trucking | 58.7678 | 6.9316 | TON |  | 0 | 0 | 0 | 0 | 0 | 58.7678
| 2490 | Dump Fees | 20.7948 | 6.9316 | TON |  | 0 | 0 | 0 | 20.7948 | 0 | 0
|  | SD PVC SDR 06" | 7420.9708 | 100 | LF |  | 0 | 2510.3067 | 3309 | 957.5745 | 0 | 644.0896
| 5006 | 6" Storm Drain | 5819.3067 | 100 | LF |  | 0 | 2510.3067 | 3309 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 860.3523 | 43.5621 | TON |  | 0 | 0 | 0 | 860.3523 | 0 | 0
| 2149 | Import Trucking | 369.3312 | 43.5621 | TON |  | 0 | 0 | 0 | 0 | 0 | 369.3312
| 2150 | Export Trucking | 274.7585 | 32.4074 | TON |  | 0 | 0 | 0 | 0 | 0 | 274.7585
| 2490 | Dump Fees | 97.2222 | 32.4074 | TON |  | 0 | 0 | 0 | 97.2222 | 0 | 0
|  | SD PVC SDR 08" 2020 | 52963.818 | 695 | LF |  | 0 | 17446.6316 | 22997.55 | 7450.0518 | 0 | 5069.5846
| 5008 | 8" Storm Drain | 40444.1816 | 695 | LF |  | 0 | 17446.6316 | 22997.55 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 6669.2493 | 337.6835 | TON |  | 0 | 0 | 0 | 6669.2493 | 0 | 0
| 2149 | Import Trucking | 2862.9689 | 337.6835 | TON |  | 0 | 0 | 0 | 0 | 0 | 2862.9689
| 2150 | Export Trucking | 2206.6157 | 260.2675 | TON |  | 0 | 0 | 0 | 0 | 0 | 2206.6157
| 2490 | Dump Fees | 780.8025 | 260.2675 | TON |  | 0 | 0 | 0 | 780.8025 | 0 | 0
|  | SD PVC SDR 10" | 52592.6765 | 672 | LF |  | 0 | 16869.2611 | 22236.48 | 7987.5575 | 0 | 5499.3779
| 5010 | 10" Storm Drain | 39105.7411 | 672 | LF |  | 0 | 16869.2611 | 22236.48 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 7123.7057 | 360.694 | TON |  | 0 | 0 | 0 | 7123.7057 | 0 | 0
| 2149 | Import Trucking | 3058.0575 | 360.694 | TON |  | 0 | 0 | 0 | 0 | 0 | 3058.0575
| 2150 | Export Trucking | 2441.3205 | 287.9506 | TON |  | 0 | 0 | 0 | 0 | 0 | 2441.3205
| 2490 | Dump Fees | 863.8519 | 287.9506 | TON |  | 0 | 0 | 0 | 863.8519 | 0 | 0
|  | SD PVC SDR 12" 2020 | 55701.7086 | 693 | LF |  | 0 | 17396.4255 | 22931.37 | 9061.6589 | 0 | 6312.2542
| 5012 | 12" Storm Drain | 40327.7955 | 693 | LF |  | 0 | 17396.4255 | 22931.37 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 8051.0339 | 407.6473 | TON |  | 0 | 0 | 0 | 8051.0339 | 0 | 0
| 2149 | Import Trucking | 3456.14 | 407.6473 | TON |  | 0 | 0 | 0 | 0 | 0 | 3456.14
| 2150 | Export Trucking | 2856.1141 | 336.875 | TON |  | 0 | 0 | 0 | 0 | 0 | 2856.1141
| 2490 | Dump Fees | 1010.625 | 336.875 | TON |  | 0 | 0 | 0 | 1010.625 | 0 | 0
|  | SD RCP CL III 15" 2020 | 3904.4201 | 40 | LF |  | 0 | 1282.6076 | 1290.2 | 620.9779 | 268 | 442.6346
| 5015 | 15" Storm Drain | 2572.8076 | 40 | LF |  | 0 | 1282.6076 | 1290.2 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 547.5211 | 27.7226 | TON |  | 0 | 0 | 0 | 547.5211 | 0 | 0
| 2149 | Import Trucking | 235.0393 | 27.7226 | TON |  | 0 | 0 | 0 | 0 | 0 | 235.0393
| 5480 | Storm Drain Testing | 268 | 40 | LF |  | 0 | 0 | 0 | 0 | 268 | 0
| 2150 | Export Trucking | 207.5953 | 24.4856 | TON |  | 0 | 0 | 0 | 0 | 0 | 207.5953
| 2490 | Dump Fees | 73.4568 | 24.4856 | TON |  | 0 | 0 | 0 | 73.4568 | 0 | 0
|  | SD Oil/Water Separator (2000 Gal) 2021 | 17720.8766 | 1 | EACH |  | 0 | 1850.681 | 1866.5 | 11301.25 | 0 | 2702.4457
| 4430 | Grease Interceptor | 3717.181 | 1 | EACH |  | 0 | 1850.681 | 1866.5 | 0 | 0 | 0
| 5490 | Precast Materials | 6325 | 1 | LS |  | 0 | 0 | 0 | 6325 | 0 | 0
| 2185 | Import Bedding Gravel | 4740 | 12 | TON |  | 0 | 0 | 0 | 4740 | 0 | 0
| 2149 | Import Trucking | 2034.7826 | 12 | TON |  | 0 | 0 | 0 | 0 | 0 | 2034.7826
| 2150 | Export Trucking | 667.663 | 78.75 | TON |  | 0 | 0 | 0 | 0 | 0 | 667.663
| 2490 | Dump Fees | 236.25 | 78.75 | TON |  | 0 | 0 | 0 | 236.25 | 0 | 0
|  | SD Curb Inlet Box (02x03x04) 2020 | 17860.8866 | 10 | EACH |  | 200 | 9525.5001 | 3622.5 | 4474.7343 | 0 | 38.1522
| 5110 | Storm Drain Inlet Box | 12508.7452 | 10 | EACH |  | 0 | 6046.8859 | 3622.5 | 2839.3593 | 0 | 0
| 2185 | Import Bedding Gravel | 88.875 | 4.5 | TON |  | 0 | 0 | 0 | 88.875 | 0 | 0
| 2149 | Import Trucking | 38.1522 | 4.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 38.1522
| 5105 | Storm Drain Grout | 854.843 | 10 | EACH |  | 0 | 494.843 | 0 | 360 | 0 | 0
| 3295 | Inlet Box Tie In | 4370.2712 | 10 | EACH |  | 200 | 2983.7712 | 0 | 1186.5 | 0 | 0
|  | SD Junction Box (2x2) 2020 | 21746.3226 | 15 | EACH |  | 300 | 13545.9857 | 5433.75 | 2403 | 0 | 63.587
| 5110 | Storm Drain Inlet Box | 13761.8143 | 15 | EACH |  | 0 | 8328.0643 | 5433.75 | 0 | 0 | 0
| 2183 | Import Road Base | 83.25 | 7.5 | TON |  | 0 | 0 | 0 | 83.25 | 0 | 0
| 2149 | Import Trucking | 63.587 | 7.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 63.587
| 5105 | Storm Drain Grout | 1282.2645 | 15 | EACH |  | 0 | 742.2645 | 0 | 540 | 0 | 0
| 3295 | Inlet Box Tie In | 6555.4068 | 15 | EACH |  | 300 | 4475.6568 | 0 | 1779.75 | 0 | 0
|  | SD Catch Basin 4x4 2020 | 5876.2375 | 4 | EACH |  | 80 | 3069.9277 | 966 | 1758.7837 | 0 | 1.5261
| 5110 | Storm Drain Inlet Box | 3780.2257 | 4 | EACH |  | 0 | 1678.482 | 966 | 1135.7437 | 0 | 0
| 2183 | Import Road Base | 4.44 | 0.4 | TON |  | 0 | 0 | 0 | 4.44 | 0 | 0
| 2149 | Import Trucking | 1.5261 | 0.4 | TON |  | 0 | 0 | 0 | 0 | 0 | 1.5261
| 5105 | Storm Drain Grout | 341.9372 | 4 | EACH |  | 0 | 197.9372 | 0 | 144 | 0 | 0
| 3295 | Inlet Box Tie In | 1748.1085 | 4 | EACH |  | 80 | 1193.5085 | 0 | 474.6 | 0 | 0
|  | SD Cleanout 04" 2020 | 3721.3199 | 4 | EACH |  | 0 | 1110.4086 | 724.5 | 283.02 | 1600 | 3.3913
| 5410 | Storm Drain Fittings & Connections | 1834.9086 | 4 | EACH |  | 0 | 1110.4086 | 724.5 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 7.9 | 0.4 | TON |  | 0 | 0 | 0 | 7.9 | 0 | 0
| 2149 | Import Trucking | 3.3913 | 0.4 | TON |  | 0 | 0 | 0 | 0 | 0 | 3.3913
| 6480 | Waterworks Materials | 275.12 | 1 | LS |  | 0 | 0 | 0 | 275.12 | 0 | 0
| 3290 | Concrete Collars | 1600 | 4 | EACH |  | 0 | 0 | 0 | 0 | 1600 | 0
|  | SD Fittings 04" | 5294.8837 | 34 | EACH |  | 0 | 3146.1576 | 2052.75 | 67.15 | 0 | 28.8261
| 5410 | Storm Drain Fittings & Connections | 5198.9076 | 34 | EACH |  | 0 | 3146.1576 | 2052.75 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 67.15 | 3.4 | TON |  | 0 | 0 | 0 | 67.15 | 0 | 0
| 2149 | Import Trucking | 28.8261 | 3.4 | TON |  | 0 | 0 | 0 | 0 | 0 | 28.8261
|  | Culinary Water & Fire Lines | 105902.4385 | 1 | LS |  | 0 | 33681.0109 | 21810.4821 | 21348.2761 | 3200 | 25862.6694
|  | CW Connect To Exist 08" Sleeve | 3936.5407 | 2 | EACH |  | 0 | 2169.3407 | 1767.2 | 0 | 0 | 0
| 6460 | Waterline Connections | 3936.5407 | 2 | EACH |  | 0 | 2169.3407 | 1767.2 | 0 | 0 | 0
|  | CW Connect To Exist | 2768.2703 | 2 | EACH |  | 0 | 1084.6703 | 883.6 | 0 | 800 | 0
| 6460 | Waterline Connections | 1968.2703 | 2 | EACH |  | 0 | 1084.6703 | 883.6 | 0 | 0 | 0
| 6450 | Hot Tapping | 800 | 2 | EACH |  | 0 | 0 | 0 | 0 | 800 | 0
|  | Culinary Water Poly 01" (LF) 2020 | 8174.7223 | 434 | LF |  | 0 | 4015.9777 | 1231.475 | 1507.3254 | 0 | 1419.9442
| 6001 | 1" Waterline | 5247.4527 | 434 | LF |  | 0 | 4015.9777 | 1231.475 | 0 | 0 | 0
| 2180 | Import Bedding Sand | 1507.3254 | 167.4806 | TON |  | 0 | 0 | 0 | 1507.3254 | 0 | 0
| 2149 | Import Trucking | 1419.9442 | 167.4806 | TON |  | 0 | 0 | 0 | 0 | 0 | 1419.9442
|  | Culinary Water Main C900 04" 2020 | 1336.8487 | 30 | LF |  | 0 | 491.7578 | 363.3125 | 204.6702 | 0 | 277.1083
| 6004 | 4" Waterline | 832.3048 | 30 | LF |  | 0 | 469.1048 | 363.2 | 0 | 0 | 0
| 2180 | Import Bedding Sand | 105.3 | 11.7 | TON |  | 0 | 0 | 0 | 105.3 | 0 | 0
| 2149 | Import Trucking | 99.1957 | 11.7 | TON |  | 0 | 0 | 0 | 0 | 0 | 99.1957
| 6490 | Waterline Testing | 22.9806 | 30 | LF |  | 0 | 22.653 | 0.1125 | 0.2151 | 0 | 0
| 2172 | Import Efill | 55.2014 | 6.3333 | TON |  | 0 | 0 | 0 | 55.2014 | 0 | 0
| 2149 | Import Trucking | 53.6957 | 6.3333 | TON |  | 0 | 0 | 0 | 0 | 0 | 53.6957
| 2150 | Export Trucking | 124.22 | 14.6512 | TON |  | 0 | 0 | 0 | 0 | 0 | 124.22
| 2490 | Dump Fees | 43.95 | 14.6512 | TON |  | 0 | 0 | 0 | 43.95 | 0 | 0
|  | Culinary Water Main C900 06" 2020 | 3999.1661 | 77 | LF |  | 0 | 1262.1783 | 932.5021 | 757.667 | 0 | 1046.8187
| 6006 | 6" Waterline | 2136.249 | 77 | LF |  | 0 | 1204.0356 | 932.2133 | 0 | 0 | 0
| 2180 | Import Bedding Sand | 301.455 | 33.495 | TON |  | 0 | 0 | 0 | 301.455 | 0 | 0
| 2149 | Import Trucking | 283.9793 | 33.495 | TON |  | 0 | 0 | 0 | 0 | 0 | 283.9793
| 6490 | Waterline Testing | 58.882 | 77 | LF |  | 0 | 58.1427 | 0.28875 | 0.45058 | 0 | 0
| 2172 | Import Efill | 283.3669 | 32.5111 | TON |  | 0 | 0 | 0 | 283.3669 | 0 | 0
| 2149 | Import Trucking | 275.6377 | 32.5111 | TON |  | 0 | 0 | 0 | 0 | 0 | 275.6377
| 2150 | Export Trucking | 275.6377 | 32.5111 | TON |  | 0 | 0 | 0 | 0 | 0 | 275.6377
| 2490 | Dump Fees | 97.5333 | 32.5111 | TON |  | 0 | 0 | 0 | 97.5333 | 0 | 0
| 2150 | Export Trucking | 211.564 | 24.9537 | TON |  | 0 | 0 | 0 | 0 | 0 | 211.564
| 2490 | Dump Fees | 74.8611 | 24.9537 | TON |  | 0 | 0 | 0 | 74.8611 | 0 | 0
|  | Culinary Water Main C900 08" 2020 | 65685.7783 | 1100 | LF |  | 0 | 18307.9887 | 13322.8333 | 14218.8145 | 0 | 19836.1418
| 6008 | 8" Waterline | 30517.8425 | 1100 | LF |  | 0 | 17200.5092 | 13317.3333 | 0 | 0 | 0
| 2180 | Import Bedding Sand | 4809.42 | 534.38 | TON |  | 0 | 0 | 0 | 4809.42 | 0 | 0
| 2149 | Import Trucking | 4530.613 | 534.38 | TON |  | 0 | 0 | 0 | 0 | 0 | 4530.613
| 6490 | Waterline Testing | 1124.4228 | 1100 | LF |  | 0 | 1107.4795 | 5.5 | 11.4433 | 0 | 0
| 2172 | Import Efill | 6072.1488 | 696.6667 | TON |  | 0 | 0 | 0 | 6072.1488 | 0 | 0
| 2149 | Import Trucking | 5906.5217 | 696.6667 | TON |  | 0 | 0 | 0 | 0 | 0 | 5906.5217
| 2150 | Export Trucking | 5906.5217 | 696.6667 | TON |  | 0 | 0 | 0 | 0 | 0 | 5906.5217
| 2490 | Dump Fees | 2090 | 696.6667 | TON |  | 0 | 0 | 0 | 2090 | 0 | 0
| 2150 | Export Trucking | 3492.4852 | 411.9342 | TON |  | 0 | 0 | 0 | 0 | 0 | 3492.4852
| 2490 | Dump Fees | 1235.8025 | 411.9342 | TON |  | 0 | 0 | 0 | 1235.8025 | 0 | 0
|  | Culinary Water Main C900 10" 2020 | 10347.8374 | 169 | LF |  | 0 | 2812.7728 | 2046.8717 | 2290.3191 | 0 | 3197.8738
| 6010 | 10" Waterline | 4688.6503 | 169 | LF |  | 0 | 2642.6237 | 2046.0267 | 0 | 0 | 0
| 2180 | Import Bedding Sand | 816.3207 | 90.7023 | TON |  | 0 | 0 | 0 | 816.3207 | 0 | 0
| 2149 | Import Trucking | 768.9978 | 90.7023 | TON |  | 0 | 0 | 0 | 0 | 0 | 768.9978
| 6490 | Waterline Testing | 173.7412 | 169 | LF |  | 0 | 170.1491 | 0.845 | 2.747 | 0 | 0
| 2172 | Import Efill | 932.9029 | 107.0333 | TON |  | 0 | 0 | 0 | 932.9029 | 0 | 0
| 2149 | Import Trucking | 907.4565 | 107.0333 | TON |  | 0 | 0 | 0 | 0 | 0 | 907.4565
| 2150 | Export Trucking | 907.4565 | 107.0333 | TON |  | 0 | 0 | 0 | 0 | 0 | 907.4565
| 2490 | Dump Fees | 321.1 | 107.0333 | TON |  | 0 | 0 | 0 | 321.1 | 0 | 0
| 2150 | Export Trucking | 613.963 | 72.4162 | TON |  | 0 | 0 | 0 | 0 | 0 | 613.963
| 2490 | Dump Fees | 217.2485 | 72.4162 | TON |  | 0 | 0 | 0 | 217.2485 | 0 | 0
|  | TEE DI (08x06x08) 2021 | 1429.1145 | 2 | EACH |  | 0 | 338.9595 | 141.875 | 948.28 | 0 | 0
| 6410 | Install Water Fittings & Valves | 192.3338 | 2 | EACH |  | 0 | 135.5838 | 56.75 | 0 | 0 | 0
| 6480 | Waterworks Materials | 673.6 | 2 | EACH |  | 0 | 0 | 0 | 673.6 | 0 | 0
| 6415 | Thrust Blocks | 563.1807 | 2 | EACH |  | 0 | 203.3757 | 85.125 | 274.68 | 0 | 0
|  | TEE DI (08x04x08) 2021 | 599.7572 | 1 | EACH |  | 0 | 169.4797 | 70.9375 | 359.34 | 0 | 0
| 6410 | Install Water Fittings & Valves | 96.1669 | 1 | EACH |  | 0 | 67.7919 | 28.375 | 0 | 0 | 0
| 6480 | Waterworks Materials | 222 | 1 | LS |  | 0 | 0 | 0 | 222 | 0 | 0
| 6415 | Thrust Blocks | 281.5903 | 1 | EACH |  | 0 | 101.6878 | 42.5625 | 137.34 | 0 | 0
|  | Bend 45° 04" 2020 | 333.8228 | 1 | EACH |  | 0 | 228.1178 | 85.125 | 20.58 | 0 | 0
| 6410 | Install Water Fittings & Valves | 120.909 | 1 | EACH |  | 0 | 92.534 | 28.375 | 0 | 0 | 0
| 6415 | Thrust Blocks | 212.9138 | 1 | EACH |  | 0 | 135.5838 | 56.75 | 20.58 | 0 | 0
|  | Bend 45° 08" 2020 | 1393.5194 | 3 | EACH |  | 0 | 795.3944 | 289.425 | 308.7 | 0 | 0
| 6410 | Install Water Fittings & Valves | 507.818 | 3 | EACH |  | 0 | 388.643 | 119.175 | 0 | 0 | 0
| 6415 | Thrust Blocks | 885.7014 | 3 | EACH |  | 0 | 406.7514 | 170.25 | 308.7 | 0 | 0
|  | Bend 45° 10" 2020 | 1052.4929 | 2 | EACH |  | 0 | 530.2629 | 192.95 | 329.28 | 0 | 0
| 6410 | Install Water Fittings & Valves | 338.5453 | 2 | EACH |  | 0 | 259.0953 | 79.45 | 0 | 0 | 0
| 6415 | Thrust Blocks | 713.9476 | 2 | EACH |  | 0 | 271.1676 | 113.5 | 329.28 | 0 | 0
|  | Valve Gate (04") 2020 | 1635.2726 | 3 | EACH |  | 0 | 333.1226 | 102.15 | 0 | 1200 | 0
| 6410 | Install Water Fittngs & Valves | 435.2726 | 3 | EACH |  | 0 | 333.1226 | 102.15 | 0 | 0 | 0
| 3290 | Concrete Collars | 1200 | 3 | EACH |  | 0 | 0 | 0 | 0 | 1200 | 0
|  | Valve Gate (08") 2020 | 569.2727 | 1 | EACH |  | 0 | 129.5477 | 39.725 | 0 | 400 | 0
| 6410 | Install Water Fittings & Valves | 169.2727 | 1 | EACH |  | 0 | 129.5477 | 39.725 | 0 | 0 | 0
| 3290 | Concrete Collars | 400 | 1 | EACH |  | 0 | 0 | 0 | 0 | 400 | 0
|  | Fire Hydrant 2020 | 2640.0226 | 2 | EACH |  | 0 | 1011.44 | 340.5 | 403.3 | 800 | 84.7826
| 6420 | Fire Hydrant | 967.2724 | 2 | EACH |  | 0 | 740.2724 | 227 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 197.5 | 10 | TON |  | 0 | 0 | 0 | 197.5 | 0 | 0
| 2149 | Import Trucking | 84.7826 | 10 | TON |  | 0 | 0 | 0 | 0 | 0 | 84.7826
| 3290 | Concrete Collars | 800 | 2 | EACH |  | 0 | 0 | 0 | 0 | 800 | 0
| 6415 | Thrust Blocks | 590.4676 | 2 | EACH |  | 0 | 271.1676 | 113.5 | 205.8 | 0 | 0
|  | Pressure Irrigation | 34466.8727 | 1 | LS |  | 0 | 12036.4406 | 7839.7563 | 6905.8936 | 0 | 7684.7823
|  | PI Connect To Exist | 4522.5407 | 2 | EACH |  | 0 | 2169.3407 | 1767.2 | 586 | 0 | 0
| 6460 | Waterline Connections | 3936.5407 | 2 | EACH |  | 0 | 2169.3407 | 1767.2 | 0 | 0 | 0
| 6480 | Waterworks Materials | 586 | 1 | LS |  | 0 | 0 | 0 | 586 | 0 | 0
|  | PI Main CL200 Purple 04" 2020 | 690.5752 | 35 | LF |  | 0 | 231.6618 | 159.0312 | 150.9487 | 0 | 148.9334
| 6004 | 4" Waterline | 364.1333 | 35 | LF |  | 0 | 205.2333 | 158.9 | 0 | 0 | 0
| 2180 | Import Bedding Sand | 121.5851 | 13.5095 | TON |  | 0 | 0 | 0 | 121.5851 | 0 | 0
| 2149 | Import Trucking | 66.6585 | 13.5095 | TON |  | 0 | 0 | 0 | 0 | 0 | 66.6585
| 6490 | Waterline Testing | 26.8107 | 35 | LF |  | 0 | 26.4285 | 0.13125 | 0.25095 | 0 | 0
| 2150 | Export Trucking | 82.2749 | 9.7042 | TON |  | 0 | 0 | 0 | 0 | 0 | 82.2749
| 2490 | Dump Fees | 29.1127 | 9.7042 | TON |  | 0 | 0 | 0 | 29.1127 | 0 | 0
|  | PI Main CL200 Purple 06" 2020 | 26628.8769 | 1170 | LF |  | 0 | 8038.6131 | 5317.65 | 5736.7649 | 0 | 7535.8489
| 6006 | 6" Waterline | 12172.4576 | 1170 | LF |  | 0 | 6860.6576 | 5311.8 | 0 | 0 | 0
| 2180 | Import Bedding Sand | 4587.0934 | 509.677 | TON |  | 0 | 0 | 0 | 4587.0934 | 0 | 0
| 2149 | Import Trucking | 4321.1749 | 509.677 | TON |  | 0 | 0 | 0 | 0 | 0 | 4321.1749
| 6490 | Waterline Testing | 1195.977 | 1170 | LF |  | 0 | 1177.9555 | 5.85 | 12.1715 | 0 | 0
| 2150 | Export Trucking | 3214.6739 | 379.1667 | TON |  | 0 | 0 | 0 | 0 | 0 | 3214.6739
| 2490 | Dump Fees | 1137.5 | 379.1667 | TON |  | 0 | 0 | 0 | 1137.5 | 0 | 0
|  | Fittings 06" 2020 | 2624.8799 | 7 | EACH |  | 0 | 1596.8249 | 595.875 | 432.18 | 0 | 0
| 6410 | Install Water Fittings & Valves | 846.3633 | 7 | EACH |  | 0 | 647.7383 | 198.625 | 0 | 0 | 0
| 6415 | Thrust Blocks | 1778.5166 | 7 | EACH |  | 0 | 949.0866 | 397.25 | 432.18 | 0 | 0
| 5490 | Precast Materials | 68734 | 1 | LS |  | 0 | 0 | 0 | 68734 | 0 | 0
| 6480 | Waterworks Materials | 226250 | 1 | LS |  | 0 | 0 | 0 | 226250 | 0 | 0
| 3290 | Concrete Collars | 5000 | 1 | LS |  | 0 | 0 | 0 | 0 | 5000 | 0
5 |  | Building Earthwork | 567925.5711 | 1 | LS | 748900 | 0 | 46606.5916 | 64710.0747 | 237810.0027 | 0 | 218798.9021
| 2132 | Excavate Footings | 6872.4962 | 1205 | CY |  | 0 | 3458.3296 | 3414.1667 | 0 | 0 | 0
| 2133 | Backfill Footings | 16485.3628 | 1024 | CY |  | 0 | 8677.3628 | 7808 | 0 | 0 | 0
|  | Under-Slab Gravel 4" 2020 | 13349.768 | 10845 | SF |  | 0 | 2983.7437 | 3222.863 | 4997.7374 | 0 | 2145.4239
| 2152 | Building Floor Grading | 6206.6067 | 10845 | SF |  | 0 | 2983.7437 | 3222.863 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 4997.7374 | 253.05 | TON |  | 0 | 0 | 0 | 4997.7374 | 0 | 0
| 2149 | Import Trucking | 2145.4239 | 253.05 | TON |  | 0 | 0 | 0 | 0 | 0 | 2145.4239
|  | Cut To Waste Export 2020 9' To Remove Peat Beneath Buildings | 142572.4883 | 7015 | CY |  | 0 | 7917.4883 | 27600 | 0 | 0 | 107055
| 2131 | Cut To Waste | 35517.4883 | 7015 | CY |  | 0 | 7917.4883 | 27600 | 0 | 0 | 0
| 2150 | Export Trucking | 107055 | 12627 | TON |  | 0 | 0 | 0 | 0 | 0 | 107055
|  | Import A1A Compacted CY Top 6' Beneath Buildings | 162027.4956 | 4675 | CY |  | 0 | 7786.7401 | 9551.025 | 73345.1652 | 0 | 71344.5652
| 2129 | Place Fill | 17337.7651 | 8415 | TON |  | 0 | 7786.7401 | 9551.025 | 0 | 0 | 0
| 2172 | Import Efill | 73345.1652 | 8415 | TON |  | 0 | 0 | 0 | 73345.1652 | 0 | 0
| 2149 | Import Trucking | 71344.5652 | 8415 | TON |  | 0 | 0 | 0 | 0 | 0 | 71344.5652
|  | Import Rock Compacted CY Bottom 3' Beneath Buildings | 191808.5889 | 2340 | CY |  | 0 | 3897.5341 | 4780.62 | 147420 | 0 | 35710.4348
| 2129 | Place Fill | 8678.1541 | 4212 | TON |  | 0 | 3897.5341 | 4780.62 | 0 | 0 | 0
| 2188 | Import Rip Rap | 147420 | 4212 | TON |  | 0 | 0 | 0 | 147420 | 0 | 0
| 2149 | Import Trucking | 35710.4348 | 4212 | TON |  | 0 | 0 | 0 | 0 | 0 | 35710.4348
|  | Geotextile Separation Fabric (SY) 2020 | 10680.197 | 4680 | SY |  | 0 | 1593.297 | 662.9 | 8424 | 0 | 0
| 2170 | Geo-Fabric | 10680.197 | 4680 | SY |  | 0 | 1593.297 | 662.9 | 8424 | 0 | 0
| 2600 | Dewatering | 13291.0379 | 10 | DY |  | 0 | 7323.0379 | 5968 | 0 | 0 | 0
|  | Well Point ADS Perf 08" | 10838.1364 | 15 | EACH |  | 0 | 2969.0581 | 1702.5 | 3623.1 | 0 | 2543.4783
| 2105 | Potholing | 4671.5581 | 15 | EACH |  | 0 | 2969.0581 | 1702.5 | 0 | 0 | 0
| 2187 | Import 2" Rock | 3060 | 15 | EACH |  | 0 | 0 | 0 | 3060 | 0 | 0
| 2149 | Import Trucking | 1271.7391 | 15 | EACH |  | 0 | 0 | 0 | 0 | 0 | 1271.7391
| 6480 | Waterworks Materials | 113.1 | 1 | LS |  | 0 | 0 | 0 | 113.1 | 0 | 0
| 2150 | Export Trucking | 1271.7391 | 150 | TON |  | 0 | 0 | 0 | 0 | 0 | 1271.7391
| 2490 | Dump Fees | 450 | 150 | TON |  | 0 | 0 | 0 | 450 | 0 | 0
6 |  | Structural Concrete | 240688.1314 | 1 | LS | 317600 | 0 | 98960.2357 | 4969.47 | 128412.3397 | 8346.0859 | 0
|  | Structural Concrete - Building A | 106236.5823 | 1 | LS |  | 0 | 41944.9093 | 1891.9455 | 58622.5297 | 3777.1978 | 0
| 3110 | Footings | 40233.0468 | 89 | CY |  | 0 | 15673.3326 | 451.7819 | 22507.2175 | 1600.7149 | 0
|  | FTS2.0 (2.0') 2025 | 19091.4555 | 560 | LF |  | 0 | 7550.483 | 212.805 | 10581.5016 | 746.6659 | 0
|  | FC2.0 (2.0') 2025 | 16568.1292 | 486 | LF |  | 0 | 6552.2408 | 184.6574 | 9183.2318 | 647.9994 | 0
|  | FC3.0 (3.0') 2025 | 1531.4141 | 31 | LF |  | 0 | 600.5833 | 19.5772 | 849.2041 | 62.0496 | 0
|  | Footing Step 2025 | 3042.0479 | 4 | EACH |  | 0 | 970.0255 | 34.7424 | 1893.28 | 144 | 0
| 3120 | Foundation Walls | 34491.3466 | 56 | CY |  | 0 | 17422.4839 | 566.1402 | 15492.073 | 1010.6496 | 0
|  | CFW-1 (8") X (0.67') Symons 2020 | 923.8444 | 48 | LF |  | 0 | 648.2525 | 18.201 | 242.9621 | 14.4288 | 0
|  | CFW-1 (8") X (2.50') Symons 2020 | 1854.1103 | 36 | LF |  | 0 | 1098.5118 | 37.2499 | 678.1079 | 40.2408 | 0
|  | CFW-2 (12") X (2.50') Symons 2020 | 12092.1426 | 196 | LF |  | 0 | 6438.123 | 216.8268 | 5110.5001 | 326.6928 | 0
|  | CFW-3 (16") X (2.50') Symons 2020 | 19621.2493 | 284 | LF |  | 0 | 9237.5966 | 293.8626 | 9460.5029 | 629.2872 | 0
| 3210 | Slab On Grade | 31512.1888 | 6114 | SF |  | 0 | 8849.0928 | 874.0234 | 20623.2393 | 1165.8333 | 0
|  | Slab On Grade (4") 2025 | 30636.4701 | 6114 | SF |  | 0 | 8607.596 | 847.4419 | 20049.2099 | 1132.2222 | 0
|  | Mechanical Concrete Pad (6") 2025 | 875.7188 | 121 | SF |  | 0 | 241.4968 | 26.5815 | 574.0294 | 33.6111 | 0
|  | Structural Concrete - Building B | 48278.4834 | 1 | LS |  | 0 | 18712.3731 | 865.4337 | 26815.6264 | 1885.0502 | 0
| 3110 | Footings | 19574.6538 | 45 | CY |  | 0 | 7482.5332 | 231.7954 | 11058.7393 | 801.5858 | 0
|  | FTS2.0 (2.0') 2025 | 2795.5346 | 82 | LF |  | 0 | 1105.6064 | 31.1607 | 1549.4342 | 109.3332 | 0
|  | FC2.0 (2.0') 2025 | 5931.7994 | 174 | LF |  | 0 | 2345.864 | 66.1119 | 3287.8237 | 231.9998 | 0
|  | FC3.0 (3.0') 2025 | 7805.2719 | 158 | LF |  | 0 | 3061.0373 | 99.7804 | 4328.2014 | 316.2528 | 0
|  | Footing Step 2025 | 3042.0479 | 4 | EACH |  | 0 | 970.0255 | 34.7424 | 1893.28 | 144 | 0
| 3120 | Foundation Walls | 14111.9182 | 24 | CY |  | 0 | 6883.3555 | 222.834 | 6572.782 | 432.9468 | 0
|  | CFW-2 (12") X (2.50') Symons 2020 | 3886.7601 | 63 | LF |  | 0 | 2069.3967 | 69.6943 | 1642.6607 | 105.0084 | 0
|  | CFW-3 (16") X (2.50') Symons 2020 | 10225.1581 | 148 | LF |  | 0 | 4813.9588 | 153.1397 | 4930.1212 | 327.9384 | 0
| 3210 | Slab On Grade | 10562.9177 | 2108 | SF |  | 0 | 2967.7482 | 292.1831 | 6912.6161 | 390.3704 | 0
| 3220 | Suspended Slabs | 3265.677 | 528 | SF |  | 0 | 888.0155 | 114.7126 | 2124.4017 | 138.5472 | 0
| 3230 | Stairs & Landings | 763.3167 | 76 | SF |  | 0 | 490.7207 | 3.9086 | 147.0874 | 121.6 | 0
|  | Structural Concrete - Building C | 52720.0107 | 1 | LS |  | 0 | 22598.2254 | 879.0969 | 27449.2891 | 1793.3993 | 0
| 3110 | Footings | 17017.2221 | 38 | CY |  | 0 | 6716.024 | 196.544 | 9433.1853 | 671.4688 | 0
|  | FTS2.0 (2.0') 2025 | 1329.5835 | 39 | LF |  | 0 | 525.8372 | 14.8203 | 736.926 | 51.9999 | 0
|  | FC2.0 (2.0') 2025 | 11488.5999 | 337 | LF |  | 0 | 4543.4262 | 128.0443 | 6367.7965 | 449.3329 | 0
|  | FC3.0 (3.0') 2025 | 4199.0387 | 85 | LF |  | 0 | 1646.7606 | 53.6793 | 2328.4628 | 170.136 | 0
| 3120 | Foundation Walls | 26663.1759 | 44 | CY |  | 0 | 13342.4397 | 432.5062 | 12100.3735 | 787.8564 | 0
|  | CFW-1 (8") X (2.50') Symons 2020 | 6489.2153 | 126 | LF |  | 0 | 3844.6292 | 130.3658 | 2373.3776 | 140.8428 | 0
|  | CFW-3 (16") X (2.50') Symons 2020 | 20173.9606 | 292 | LF |  | 0 | 9497.8106 | 302.1404 | 9726.996 | 647.0136 | 0
| 3210 | Slab On Grade | 9039.6127 | 1804 | SF |  | 0 | 2539.7617 | 250.0466 | 5915.7302 | 334.0741 | 0
|  | Structural Concrete - Building D | 26669.4298 | 1 | LS |  | 0 | 13230.4988 | 492.2093 | 12184.2931 | 762.4287 | 0
| 3110 | Footings | 9594.307 | 20 | CY |  | 0 | 4018.8146 | 116.5151 | 5100.3146 | 358.6627 | 0
|  | FC2.0 (2.0') 2025 | 8249.9738 | 242 | LF |  | 0 | 3262.6384 | 91.9487 | 4572.7203 | 322.6663 | 0
|  | FS3.0 (3.0') 2025 | 1344.3332 | 6 | EACH |  | 0 | 756.1762 | 24.5664 | 527.5942 | 35.9964 | 0
| 3120 | Foundation Walls | 12353.4912 | 15 | CY |  | 0 | 7322.3114 | 248.3158 | 4515.024 | 267.84 | 0
| 3210 | Slab On Grade | 3677.9799 | 734 | SF |  | 0 | 1033.362 | 101.7374 | 2406.9545 | 135.9259 | 0
| 3100 | Misc. Structural Concrete | 1043.6517 | 1 | LS |  | 0 | 856.0107 | 25.641 | 162 | 0 | 0
|  | Structural Concrete - Dumpster | 4209.8136 | 1 | LS |  | 0 | 1880.4176 | 60.7847 | 2140.6014 | 128.01 | 0
| 3110 | Footings | 1538.733 | 4 | CY |  | 0 | 499.1555 | 12.471 | 957.1765 | 69.93 | 0
| 3120 | Foundation Walls | 1505.9754 | 2 | CY |  | 0 | 879.0324 | 29.0851 | 564.378 | 33.48 | 0
| 3210 | Slab On Grade | 1165.1052 | 82 | SF |  | 0 | 502.2296 | 19.2287 | 619.0469 | 24.6 | 0
| 2100 | SWPPP | 2573.8116 | 1 | LS |  | 0 | 593.8116 | 780 | 1200 | 0 | 0
7 |  | Site Concrete Prep | 182080.2954 | 1 | LS | 261500 | 0 | 73227.2536 | 64937.8314 | 24897.9642 | 0 | 19017.2462
|  | Curb & Gutter Prep 24" (140/323) 2020 | 26649.0784 | 4215 | LF |  | 0 | 9143.771 | 10284.6 | 4093.8187 | 0 | 3126.8886
| 2155 | Prep Concrete Curbs | 19428.371 | 4215 | LF |  | 0 | 9143.771 | 10284.6 | 0 | 0 | 0
| 2183 | Import Road Base | 4093.8187 | 368.8125 | TON |  | 0 | 0 | 0 | 4093.8187 | 0 | 0
| 2149 | Import Trucking | 3126.8886 | 368.8125 | TON |  | 0 | 0 | 0 | 0 | 0 | 3126.8886
|  | Concrete Curb Wall Prep 6"x12" | 333.9997 | 35 | LF |  | 0 | 161.9346 | 140.0875 | 18.13 | 0 | 13.8476
| 2155 | Prep Concrete Curbs | 302.0221 | 35 | LF |  | 0 | 161.9346 | 140.0875 | 0 | 0 | 0
| 2183 | Import Road Base | 18.13 | 1.6333 | TON |  | 0 | 0 | 0 | 18.13 | 0 | 0
| 2149 | Import Trucking | 13.8476 | 1.6333 | TON |  | 0 | 0 | 0 | 0 | 0 | 13.8476
| 2155 | Prep Mow Curb 12"x6" | 4996.3082 | 1158 | LF |  | 0 | 2678.8607 | 2317.4475 | 0 | 0 | 0
| 2155 | Prep Mow Curb 12"x8" | 6817.0699 | 1580 | LF |  | 0 | 3655.0949 | 3161.975 | 0 | 0 | 0
| 2155 | Prep Mow Curb 12"x12" | 3352.4451 | 777 | LF |  | 0 | 1797.4739 | 1554.9713 | 0 | 0 | 0
| 2155 | Prep Mow Curb 18"x6" | 7516.0353 | 1742 | LF |  | 0 | 4029.8578 | 3486.1775 | 0 | 0 | 0
|  | Concrete Flatwork Prep UBC 05"/04" 2020 | 85966.1991 | 53700 | SF |  | 0 | 33127.1891 | 28657.9 | 13709.61 | 0 | 10471.5
| 2156 | Prep Concrete Flatwork | 61785.0891 | 53700 | SF |  | 0 | 33127.1891 | 28657.9 | 0 | 0 | 0
| 2183 | Import Road Base | 13709.61 | 1235.1 | TON |  | 0 | 0 | 0 | 13709.61 | 0 | 0
| 2149 | Import Trucking | 10471.5 | 1235.1 | TON |  | 0 | 0 | 0 | 0 | 0 | 10471.5
|  | Heavy Duty Flatwork Prep UBC 6.5"/04" 2020 | 42839.0221 | 26760 | SF |  | 0 | 16508.0741 | 14280.92 | 6831.828 | 0 | 5218.2
| 2156 | Prep Concrete Flatwork | 30788.9941 | 26760 | SF |  | 0 | 16508.0741 | 14280.92 | 0 | 0 | 0
| 2183 | Import Road Base | 6831.828 | 615.48 | TON |  | 0 | 0 | 0 | 6831.828 | 0 | 0
| 2149 | Import Trucking | 5218.2 | 615.48 | TON |  | 0 | 0 | 0 | 0 | 0 | 5218.2
|  | Raised Crosswalk Prep UBC 6.5"/04" 2020 | 1127.0057 | 704 | SF |  | 0 | 434.2931 | 375.7013 | 179.7312 | 0 | 137.28
| 2156 | Prep Concrete Flatwork | 809.9945 | 704 | SF |  | 0 | 434.2931 | 375.7013 | 0 | 0 | 0
| 2183 | Import Road Base | 179.7312 | 16.192 | TON |  | 0 | 0 | 0 | 179.7312 | 0 | 0
| 2149 | Import Trucking | 137.28 | 16.192 | TON |  | 0 | 0 | 0 | 0 | 0 | 137.28
|  | Pitcher's Mound Flatwork Prep UBC 04"/04" 2020 | 406.6185 | 254 | SF |  | 0 | 156.691 | 135.5513 | 64.8462 | 0 | 49.53
| 2156 | Prep Concrete Flatwork | 292.2423 | 254 | SF |  | 0 | 156.691 | 135.5513 | 0 | 0 | 0
| 2183 | Import Road Base | 64.8462 | 5.842 | TON |  | 0 | 0 | 0 | 64.8462 | 0 | 0
| 2149 | Import Trucking | 49.53 | 5.842 | TON |  | 0 | 0 | 0 | 0 | 0 | 49.53
| 2105 | Bollard Base Prep | 937.7802 | 14 | EACH |  | 0 | 692.7802 | 245 | 0 | 0 | 0
| 2105 | Removable Bollard Base Prep | 1071.7488 | 16 | EACH |  | 0 | 791.7488 | 280 | 0 | 0 | 0
| 2105 | Flagpole Base Prep | 66.9843 | 1 | EACH |  | 0 | 49.4843 | 17.5 | 0 | 0 | 0
8 |  | Site Concrete | 1026056.55 | 1 | LS | 1367500 | 0 | 461280.2734 | 9931.1017 | 547854.0365 | 6991.1383 | 0
| 3251 | KSC Curb & Gutter 24" Slip Machine 2020 | 85070.8928 | 4215 | LF |  | 0 | 23641.786 | 4757.6226 | 56671.4843 | 0 | 0
| 3251 | KSC Concrete Curb Wall 2020 | 598.1976 | 35 | LF |  | 0 | 371.1801 | 0 | 227.0176 | 0 | 0
| 3251 | Mow Curb 12"x06" 2020 | 20578.7415 | 1158 | LF |  | 0 | 14327.5511 | 0 | 6251.1904 | 0 | 0
| 3251 | Mow Curb 12"x08" 2020 | 44657.715 | 2318 | LF |  | 0 | 28679.8476 | 0 | 15977.8674 | 0 | 0
| 3251 | Mow Curb 12"x12" 2020 | 17124.8072 | 770 | LF |  | 0 | 9526.9554 | 0 | 7597.8518 | 0 | 0
| 3251 | Mow Curb 18"x06" 2020 | 34526.3328 | 1725 | LF |  | 0 | 21342.8547 | 0 | 13183.4781 | 0 | 0
| 3254 | Concrete Flatwork (05" Thick) 2020 | 309399.6232 | 53250 | SF |  | 0 | 109807.4407 | 0 | 199592.1825 | 0 | 0
| 3254 | Heavy Duty Flatwork (06.5" Thick) 2020 | 185251.2797 | 26760 | SF |  | 0 | 55182.1054 | 0 | 130069.1743 | 0 | 0
| 3254 | Raised Crosswalk Flatwork (11" Thick) 2020 | 7598.3719 | 704 | SF |  | 0 | 1742.0718 | 0 | 5856.3 | 0 | 0
| 3251 | KSC Thickened Sidewalk Edge 2020 | 1140.8954 | 68 | LF |  | 0 | 841.3415 | 0 | 299.5539 | 0 | 0
| 3251 | KSC Thickened Pitchers Mound Edge 2020 | 905.3389 | 57 | LF |  | 0 | 705.2422 | 0 | 200.0968 | 0 | 0
| 3135 | Bollard Base 2020 | 5594.315 | 14 | EACH |  | 0 | 5196.5211 | 0 | 397.7939 | 0 | 0
| 3135 | Removable Bollard Base 2020 | 6052.6334 | 16 | EACH |  | 0 | 5938.8813 | 0 | 113.7521 | 0 | 0
| 3135 | Flagpole Base 2020 | 400.1985 | 1 | EACH |  | 0 | 371.1801 | 0 | 29.0184 | 0 | 0
| 3230 | Seating Stairs 2020 | 188657.7712 | 5394 | SF |  | 0 | 119339.0535 | 1036.6836 | 63786.9657 | 4495.0683 | 0
| 3260 | ADA Ramp | 23891.6248 | 26 | EACH |  | 0 | 15571.6248 | 0 | 8320 | 0 | 0
|  | Structural Concrete 2022 | 86886.3761 | 1 | LS |  | 0 | 46913.2012 | 1796.7955 | 35680.3094 | 2496.07 | 0
| 3110 | Footings | 14805.4656 | 29 | CY |  | 0 | 6805.354 | 208.1718 | 7142.9397 | 649 | 0
|  | Backstop Footing (2.50') 2025 | 10655.4847 | 230 | LF |  | 0 | 4660.0425 | 141.68 | 5321.3122 | 532.45 | 0
|  | Steps Wall Waste Footing | 4149.9808 | 175 | LF |  | 0 | 2145.3115 | 66.4918 | 1821.6275 | 116.55 | 0
| 3120 | Foundation Walls | 72080.9105 | 85 | CY |  | 0 | 40107.8471 | 1588.6236 | 28537.3697 | 1847.07 | 0
|  | Backstop Foundation Wall (16") X (4.50') HDO 2020 | 39236.3081 | 228 | LF |  | 0 | 20426.7788 | 773.5813 | 16772.258 | 1263.69 | 0
|  | Concrete Steps Wall (12") X (5.0') HDO 2020 | 32844.6024 | 175 | LF |  | 0 | 19681.0683 | 815.0424 | 11765.1118 | 583.38 | 0
| 2100 | SWPPP | 7721.4349 | 1 | LS |  | 0 | 1781.4349 | 2340 | 3600 | 0 | 0
9 |  | Hot-Mix Asphalt (Prep) | 100088.9547 | 1 | LS | 130300 | 0 | 9089.5153 | 10215.1854 | 48378.492 | 0 | 32405.7621
|  | Place Roadbase Parking 06" Light Duty(140/563/277/WT) 2020 | 30364.859 | 35580 | SF |  | 0 | 2781.7914 | 3126.296 | 13898.7933 | 0 | 10557.9783
| 2157 | Base Under Parking Lot | 5908.0874 | 35580 | SF |  | 0 | 2781.7914 | 3126.296 | 0 | 0 | 0
| 2183 | Import Road Base | 13822.83 | 1245.3 | TON |  | 0 | 0 | 0 | 13822.83 | 0 | 0
| 2149 | Import Trucking | 10557.9783 | 1245.3 | TON |  | 0 | 0 | 0 | 0 | 0 | 10557.9783
| 1410 | Construction Water | 75.9633 | 21.7038 | MGAL |  | 0 | 0 | 0 | 75.9633 | 0 | 0
|  | Place Roadbase Parking 08" Heavy Duty (140/563/277/WT) 2020 | 59547.0034 | 57294 | SF |  | 0 | 5375.378 | 6041.0794 | 29821.3763 | 0 | 18309.1697
| 2157 | Base Under Parking Lot | 11416.4574 | 57294 | SF |  | 0 | 5375.378 | 6041.0794 | 0 | 0 | 0
| 2183 | Import Road Base | 29821.3763 | 2673.72 | TON |  | 0 | 0 | 0 | 29821.3763 | 0 | 0
| 2150 | Import Trucking | 18309.1697 | 2673.72 | TON |  | 0 | 0 | 0 | 0 | 0 | 18309.1697
|  | Place Roadbase Trail 06" Asphalt Trail(140/563/277/WT) 2020 | 10177.0923 | 11925 | SF |  | 0 | 932.3458 | 1047.81 | 4658.3224 | 0 | 3538.6141
| 2157 | Base Under Parking Lot | 1980.1558 | 11925 | SF |  | 0 | 932.3458 | 1047.81 | 0 | 0 | 0
| 2183 | Import Road Base | 4632.8625 | 417.375 | TON |  | 0 | 0 | 0 | 4632.8625 | 0 | 0
| 2149 | Import Trucking | 3538.6141 | 417.375 | TON |  | 0 | 0 | 0 | 0 | 0 | 3538.6141
| 1410 | Construction Water | 25.4599 | 7.2742 | MGAL |  | 0 | 0 | 0 | 25.4599 | 0 | 0
10 |  | Hot-Mix Asphalt Paving | 194782.17 | 1 | LS | 230200 | 0 | 0 | 0 | 0 | 194782.17 | 0
| 7530 | Asphalt Paving Sub | 194782.17 | 1 | LS |  | 0 | 0 | 0 | 0 | 194782.17 | 0
11 |  | Pavement Markings - Striping | 2600 | 1 | LS | 2910 | 0 | 0 | 0 | 0 | 2600 | 0
| 7525 | Striping Sub | 2600 | 1 | LS |  | 0 | 0 | 0 | 0 | 2600 | 0
12 |  | Exterior Sports Equipment | 643178.3057 | 1 | LS | 818500 | 0 | 153282.0193 | 63021.1578 | 426743.4424 | 0 | 131.6862
|  | Baseball Sports Equipment Install | 284978.6615 | 1 | LS |  | 0 | 48785.0121 | 13933.3977 | 222148.3481 | 0 | 111.9036
|  | Backstop Pads | 16090.7341 | 43 | EACH |  | 0 | 3862.8764 | 0 | 12227.8577 | 0 | 0
| 2705 | Misc. Equipment Install | 3862.8764 | 1 | LS |  | 0 | 3862.8764 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment | 12227.8577 | 1 | LS |  | 0 | 0 | 0 | 12227.8577 | 0 | 0
|  | Foul Pole | 11188.7414 | 2 | EACH |  | 0 | 2673.7027 | 0 | 8515.0387 | 0 | 0
| 2705 | Misc. Equipment Install | 2673.7027 | 1 | LS |  | 0 | 2673.7027 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 8515.0387 | 1 | LS |  | 0 | 0 | 0 | 8515.0387 | 0 | 0
|  | Dugout Sports Equipment | 16793.6901 | 2 | EACH |  | 0 | 2575.251 | 0 | 14218.4392 | 0 | 0
| 2705 | Misc. Equipment Install | 2575.251 | 1 | LS |  | 0 | 2575.251 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 14218.4392 | 1 | LS |  | 0 | 0 | 0 | 14218.4392 | 0 | 0
|  | Batting Cage/Netting | 68204.1086 | 4 | EACH |  | 0 | 4259.2662 | 0 | 63944.8425 | 0 | 0
| 2705 | Misc. Equipment Install | 4259.2662 | 1 | LS |  | 0 | 4259.2662 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 63944.8425 | 1 | LS |  | 0 | 0 | 0 | 63944.8425 | 0 | 0
|  | Batting Cage Poles | 15150.5617 | 10 | EACH |  | 0 | 5941.5617 | 2090 | 7119 | 0 | 0
| 2705 | Misc. Equipment Install | 8031.5617 | 1 | LS |  | 0 | 5941.5617 | 2090 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 7119 | 1 | LS |  | 0 | 0 | 0 | 7119 | 0 | 0
|  | Dugout Leaning Pole Padding | 3936.3892 | 100 | LF |  | 0 | 643.8127 | 0 | 3292.5765 | 0 | 0
| 2705 | Misc. Equipment Install | 643.8127 | 1 | LS |  | 0 | 643.8127 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 3292.5765 | 1 | LS |  | 0 | 0 | 0 | 3292.5765 | 0 | 0
|  | Fence Top Guard Cap W/Ties | 3518.2578 | 1054 | LF |  | 0 | 1221.5168 | 0 | 2296.741 | 0 | 0
| 2705 | Misc. Equipment Install | 1221.5168 | 1 | LS |  | 0 | 1221.5168 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 2296.741 | 1 | LS |  | 0 | 0 | 0 | 2296.741 | 0 | 0
|  | Batters Box | 1579.0937 | 100 | SF |  | 0 | 705.6329 | 133.4167 | 720.2615 | 0 | 19.7826
|  | Concrete Flatwork Prep UBC 06" 2020 | 346.2727 | 100 | SF |  | 0 | 154.2234 | 133.4167 | 38.85 | 0 | 19.7826
| 2156 | Prep Concrete Flatwork | 287.6401 | 100 | SF |  | 0 | 154.2234 | 133.4167 | 0 | 0 | 0
| 2183 | Import Road Base | 38.85 | 3.5 | TON |  | 0 | 0 | 0 | 38.85 | 0 | 0
| 2149 | Import Trucking | 19.7826 | 3.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 19.7826
|  | Reinforced Concrete Flatwork (04" Thick) 2020 | 780.8053 | 100 | SF |  | 0 | 459.2621 | 0 | 321.5432 | 0 | 0
| 3254 | Concrete Flatwork | 780.8053 | 100 | SF |  | 0 | 459.2621 | 0 | 321.5432 | 0 | 0
| 3710 | Nailer Board | 452.0157 | 50 | LF |  | 0 | 92.1474 | 0 | 359.8683 | 0 | 0
|  | Pitchers Mound | 6027.3578 | 1 | EACH |  | 0 | 3286.2631 | 487.9848 | 2160.989 | 0 | 92.121
|  | Concrete Flatwork Prep UBC 11" 2020 | 1325.1049 | 254 | SF |  | 0 | 564.0876 | 487.9848 | 180.9115 | 0 | 92.121
| 2156 | Prep Concrete Flatwork | 1052.0724 | 254 | SF |  | 0 | 564.0876 | 487.9848 | 0 | 0 | 0
| 2183 | Import Road Base | 180.9115 | 16.2983 | TON |  | 0 | 0 | 0 | 180.9115 | 0 | 0
| 2149 | Import Trucking | 92.121 | 16.2983 | TON |  | 0 | 0 | 0 | 0 | 0 | 92.121
|  | Reinforced Concrete Flatwork (04" Thick) 2020 | 2218.9449 | 254 | SF |  | 0 | 1402.2252 | 0 | 816.7198 | 0 | 0
| 3254 | Concrete Flatwork | 2218.9449 | 254 | SF |  | 0 | 1402.2252 | 0 | 816.7198 | 0 | 0
| 3710 | Nailer Board | 1012.5151 | 112 | LF |  | 0 | 206.4101 | 0 | 806.105 | 0 | 0
|  | Pitchers Mound Curb Wall 8" X 8" | 1470.793 | 60 | LF |  | 0 | 1113.5402 | 0 | 357.2527 | 0 | 0
| 3251 | Concrete Curbs | 1470.793 | 60 | LF |  | 0 | 1113.5402 | 0 | 357.2527 | 0 | 0
|  | Pitchers Rubber | 1317.4641 | 4 | EACH |  | 0 | 356.4937 | 0 | 960.9704 | 0 | 0
| 2705 | Misc. Equipment Install | 356.4937 | 1 | LS |  | 0 | 356.4937 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 960.9704 | 1 | LS |  | 0 | 0 | 0 | 960.9704 | 0 | 0
|  | Home Plates | 2609.7537 | 4 | EACH |  | 0 | 1487.7508 | 0 | 1122.0029 | 0 | 0
| 2705 | Misc. Equipment Install | 1487.7508 | 1 | LS |  | 0 | 1487.7508 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 1122.0029 | 1 | LS |  | 0 | 0 | 0 | 1122.0029 | 0 | 0
|  | Bases (W/ In-ground Mounting Sleeves) | 2048.7583 | 3 | EACH |  | 0 | 1115.8131 | 0 | 932.9452 | 0 | 0
| 2705 | Misc. Equipment Install | 1115.8131 | 1 | LS |  | 0 | 1115.8131 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 932.9452 | 1 | LS |  | 0 | 0 | 0 | 932.9452 | 0 | 0
|  | Baseball Backstop Netting | 136513.751 | 156 | LF |  | 0 | 20655.071 | 11221.9962 | 104636.6837 | 0 | 0
|  | Pole To Pole Tensioned Baseball Netting | 6915.7374 | 2 | LS |  | 0 | 4635.7374 | 2280 | 0 | 0 | 0
| 2705 | Misc. Equipment Install | 6915.7374 | 1 | LS |  | 0 | 4635.7374 | 2280 | 0 | 0 | 0
|  | Netting Poles | 19543.7925 | 8 | EACH |  | 0 | 11383.5962 | 5741.9962 | 2418.2 | 0 | 0
| 2705 | Misc. Equipment Install | 17125.5925 | 1 | LS |  | 0 | 11383.5962 | 5741.9962 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 2418.2 | 1 | LS |  | 0 | 0 | 0 | 2418.2 | 0 | 0
|  | Baseball Backstop Netting Install | 110054.2211 | 156 | LF |  | 0 | 4635.7374 | 3200 | 102218.4837 | 0 | 0
| 2705 | Misc. Equipment Install | 7835.7374 | 1 | LS |  | 0 | 4635.7374 | 3200 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 102218.4837 | 1 | LS |  | 0 | 0 | 0 | 102218.4837 | 0 | 0
|  | Softball Sports Equipment Install | 130965.2541 | 1 | LS |  | 0 | 28752.1059 | 9506.473 | 92686.8926 | 0 | 19.7826
|  | Backstop Pads | 9355.078 | 25 | EACH |  | 0 | 2245.8584 | 0 | 7109.2196 | 0 | 0
| 2705 | Misc. Equipment Install | 2245.8584 | 1 | LS |  | 0 | 2245.8584 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 7109.2196 | 1 | LS |  | 0 | 0 | 0 | 7109.2196 | 0 | 0
|  | Foul Pole | 11188.745 | 2 | EACH |  | 0 | 2673.7027 | 0 | 8515.0422 | 0 | 0
| 2705 | Misc. Equipment Install | 2673.7027 | 1 | LS |  | 0 | 2673.7027 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 8515.0422 | 1 | LS |  | 0 | 0 | 0 | 8515.0422 | 0 | 0
|  | Dugout Sports Equipment | 16793.6901 | 2 | EACH |  | 0 | 2575.251 | 0 | 14218.4392 | 0 | 0
| 2705 | Misc. Equipment Install | 2575.251 | 1 | LS |  | 0 | 2575.251 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 14218.4392 | 1 | LS |  | 0 | 0 | 0 | 14218.4392 | 0 | 0
|  | Dugout Leaning Pole Padding | 3936.3892 | 100 | LF |  | 0 | 643.8127 | 0 | 3292.5765 | 0 | 0
| 2705 | Misc. Equipment Install | 643.8127 | 1 | LS |  | 0 | 643.8127 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 3292.5765 | 1 | LS |  | 0 | 0 | 0 | 3292.5765 | 0 | 0
|  | Fence Top Guard Cap W/Ties | 2203.0836 | 660 | LF |  | 0 | 764.8967 | 0 | 1438.1869 | 0 | 0
| 2705 | Misc. Equipment Install | 764.8967 | 1 | LS |  | 0 | 764.8967 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 1438.1869 | 1 | LS |  | 0 | 0 | 0 | 1438.1869 | 0 | 0
|  | Batters Box | 1579.0937 | 100 | SF |  | 0 | 705.6329 | 133.4167 | 720.2615 | 0 | 19.7826
|  | Concrete Flatwork Prep UBC 06" 2020 | 346.2727 | 100 | SF |  | 0 | 154.2234 | 133.4167 | 38.85 | 0 | 19.7826
| 2156 | Prep Concrete Flatwork | 287.6401 | 100 | SF |  | 0 | 154.2234 | 133.4167 | 0 | 0 | 0
| 2183 | Import Road Base | 38.85 | 3.5 | TON |  | 0 | 0 | 0 | 38.85 | 0 | 0
| 2149 | Import Trucking | 19.7826 | 3.5 | TON |  | 0 | 0 | 0 | 0 | 0 | 19.7826
|  | Reinforced Concrete Flatwork (04" Thick) 2020 | 780.8053 | 100 | SF |  | 0 | 459.2621 | 0 | 321.5432 | 0 | 0
| 3254 | Concrete Flatwork | 780.8053 | 100 | SF |  | 0 | 459.2621 | 0 | 321.5432 | 0 | 0
| 3710 | Nailer Board | 452.0157 | 50 | LF |  | 0 | 92.1474 | 0 | 359.8683 | 0 | 0
|  | Pitchers Rubber | 988.0981 | 3 | EACH |  | 0 | 267.3703 | 0 | 720.7278 | 0 | 0
| 2705 | Misc. Equipment Install | 267.3703 | 1 | LS |  | 0 | 267.3703 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 720.7278 | 1 | LS |  | 0 | 0 | 0 | 720.7278 | 0 | 0
|  | Home Plates | 1957.3153 | 3 | EACH |  | 0 | 1115.8131 | 0 | 841.5022 | 0 | 0
| 2705 | Misc. Equipment Install | 1115.8131 | 1 | LS |  | 0 | 1115.8131 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 841.5022 | 1 | LS |  | 0 | 0 | 0 | 841.5022 | 0 | 0
|  | Bases (W/ In-ground Mounting Sleeves) | 2048.7583 | 3 | EACH |  | 0 | 1115.8131 | 0 | 932.9452 | 0 | 0
| 2705 | Misc. Equipment Install | 1115.8131 | 1 | LS |  | 0 | 1115.8131 | 0 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 932.9452 | 1 | LS |  | 0 | 0 | 0 | 932.9452 | 0 | 0
|  | Softball Backstop Netting | 80915.0029 | 177 | LF |  | 0 | 16643.9551 | 9373.0563 | 54897.9915 | 0 | 0
|  | Netting Poles | 19544.7841 | 8 | EACH |  | 0 | 11384.1761 | 5742.2871 | 2418.3209 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 2418.3209 | 1 | LS |  | 0 | 0 | 0 | 2418.3209 | 0 | 0
| 2705 | Misc. Equipment Install | 17126.4632 | 1 | LS |  | 0 | 11384.1761 | 5742.2871 | 0 | 0 | 0
|  | Softball Backstop Netting Install | 61370.2188 | 177 | LF |  | 0 | 5259.779 | 3630.7692 | 52479.6706 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 52479.6706 | 1 | LS |  | 0 | 0 | 0 | 52479.6706 | 0 | 0
| 2705 | Misc. Equipment Install | 8890.5482 | 1 | LS |  | 0 | 5259.779 | 3630.7692 | 0 | 0 | 0
|  | Soccer Sports Equipment Install | 227234.3901 | 1 | LS |  | 0 | 75744.9013 | 39581.2871 | 111908.2017 | 0 | 0
|  | Soccer Field 20' Netting | 191976.83 | 740 | LF |  | 0 | 74199.7507 | 39581.2871 | 78195.7921 | 0 | 0
|  | Netting Poles | 107491.9152 | 44.0004 | EACH |  | 0 | 62610.4072 | 31581.2871 | 13300.2209 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 13300.2209 | 1 | LS |  | 0 | 0 | 0 | 13300.2209 | 0 | 0
| 2705 | Misc. Equipment Install | 94191.6943 | 1 | LS |  | 0 | 62610.4072 | 31581.2871 | 0 | 0 | 0
|  | Soccer Field Netting Install | 84484.9147 | 740 | LF |  | 0 | 11589.3435 | 8000 | 64895.5712 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 64895.5712 | 1 | LS |  | 0 | 0 | 0 | 64895.5712 | 0 | 0
| 2705 | Misc. Equipment Install | 19589.3435 | 1 | LS |  | 0 | 11589.3435 | 8000 | 0 | 0 | 0
|  | Soccer Goals | 23465.8168 | 4 | EACH |  | 0 | 1030.1004 | 0 | 22435.7164 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 22435.7164 | 1 | LS |  | 0 | 0 | 0 | 22435.7164 | 0 | 0
| 2705 | Misc. Equipment Install | 1030.1004 | 1 | LS |  | 0 | 1030.1004 | 0 | 0 | 0 | 0
|  | Lacrosse Goals | 11791.7433 | 4 | EACH |  | 0 | 515.0502 | 0 | 11276.6931 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 11276.6931 | 1 | LS |  | 0 | 0 | 0 | 11276.6931 | 0 | 0
| 2705 | Misc. Equipment Install | 515.0502 | 1 | LS |  | 0 | 515.0502 | 0 | 0 | 0 | 0
13 |  | Turf Field Prep | 1467853.7039 | 1 | LS | 2424100 | 0 | 219001.5358 | 225841.3852 | 690532.8912 | 0 | 332477.8917
|  | Turf Field (Complete) 2020 | 1467853.7039 | 1 | LS |  | 0 | 219001.5358 | 225841.3852 | 690532.8912 | 0 | 332477.8917
|  | 6" Blended Gravel Under Turf | 485168.4391 | 347206 | SF |  | 0 | 79789.7905 | 91467.7919 | 137870.8732 | 0 | 176039.9836
|  | Gravel Football Field 06" | 485168.4391 | 347206 | SF |  | 0 | 79789.7905 | 91467.7919 | 137870.8732 | 0 | 176039.9836
| 2732 | Place Field Drainage Gravel | 144134.5845 | 347206 | SF |  | 0 | 67864.9999 | 76269.5847 | 0 | 0 | 0
| 2734 | Field Drainage Material | 137870.8732 | 347206 | SF |  | 0 | 0 | 0 | 137870.8732 | 0 | 0
| 2149 | Import Trucking | 176039.9836 | 12213.9355 | TON |  | 0 | 0 | 0 | 0 | 0 | 176039.9836
|  | Pugmill Materials 2020 (ONSITE PER VANCE) | 27122.9978 | 12213.9356 | TON |  | 0 | 11924.7906 | 15198.2072 | 0 | 0 | 0
| 2220 | Screen Processing | 27122.9978 | 12213.9356 | TON |  | 0 | 11924.7906 | 15198.2072 | 0 | 0 | 0
|  | Roadbase Football Field 08" | 367577.7575 | 347206 | SF |  | 0 | 23455.2398 | 26360 | 180585.9559 | 0 | 137176.5618
| 2165 | Place Base Under Field | 50805.4201 | 347206 | SF |  | 0 | 23455.2398 | 26360 | 990.1803 | 0 | 0
| 2183 | Import Road Base | 179595.7756 | 16179.7996 | TON |  | 0 | 0 | 0 | 179595.7756 | 0 | 0
| 2149 | Import Trucking | 137176.5618 | 16179.7996 | TON |  | 0 | 0 | 0 | 0 | 0 | 137176.5618
|  | HDPE Liner Football Field | 183832.6856 | 347206 | SF |  | 0 | 8895.4925 | 3701.0187 | 171236.1744 | 0 | 0
| 2733 | Place Field Liner | 183832.6856 | 46525.604 | SY |  | 0 | 8895.4925 | 3701.0187 | 171236.1744 | 0 | 0
|  | Geotextile Football Field Below Liner | 35278.1474 | 347206 | SF |  | 0 | 6177.4253 | 2570.1519 | 26530.5701 | 0 | 0
| 2731 | Place Field Geotextile | 35278.1474 | 46525.604 | SY |  | 0 | 6177.4253 | 2570.1519 | 26530.5701 | 0 | 0
|  | Geotextile Football Field Above Liner | 35278.1474 | 347206 | SF |  | 0 | 6177.4253 | 2570.1519 | 26530.5701 | 0 | 0
| 2731 | Place Field Geotextile | 35278.1474 | 46525.604 | SY |  | 0 | 6177.4253 | 2570.1519 | 26530.5701 | 0 | 0
|  | Geotextile Filter Fabric Below Road Base | 35278.1474 | 347206 | SF |  | 0 | 6177.4253 | 2570.1519 | 26530.5701 | 0 | 0
| 2731 | Place Field Geotextile | 35278.1474 | 46525.604 | SY |  | 0 | 6177.4253 | 2570.1519 | 26530.5701 | 0 | 0
|  | Football Field Drainage | 277418.2361 | 1 | LS |  | 0 | 78539.0017 | 96602.1189 | 83015.7692 | 0 | 19261.3463
|  | LD Field PERF ADS 12" | 228351.2407 | 4233 | LF |  | 0 | 70840.8552 | 93379.98 | 44869.0592 | 0 | 19261.3463
| 5012 | 12" Storm Drain | 164220.8352 | 4233 | LF |  | 0 | 70840.8552 | 93379.98 | 0 | 0 | 0
| 2185 | Import Bedding Gravel | 44869.0592 | 2271.8511 | TON |  | 0 | 0 | 0 | 44869.0592 | 0 | 0
| 2149 | Import Trucking | 19261.3463 | 2271.8511 | TON |  | 0 | 0 | 0 | 0 | 0 | 19261.3463
|  | LD Field ADS Flat Drain 01"x12" | 39390.4436 | 9518 | LF |  | 0 | 7169.3697 | 3000.8139 | 29220.26 | 0 | 0
| 2735 | Field Flat Panel Drain | 10170.1836 | 9518 | LF |  | 0 | 7169.3697 | 3000.8139 | 0 | 0 | 0
| 6480 | Waterworks Materials | 29220.26 | 1 | LS |  | 0 | 0 | 0 | 29220.26 | 0 | 0
|  | LD Field ADS Flat Drain Connection 12x04 | 9676.5518 | 65 | EACH |  | 0 | 528.7768 | 221.325 | 8926.45 | 0 | 0
| 2735 | Field Flat Panel Drain | 750.1018 | 65 | LF |  | 0 | 528.7768 | 221.325 | 0 | 0 | 0
| 6480 | Waterworks Materials | 8926.45 | 1 | LS |  | 0 | 0 | 0 | 8926.45 | 0 | 0
|  | Nailer Board | 48022.1435 | 5312 | LF |  | 0 | 9789.7353 | 0 | 38232.4082 | 0 | 0
| 2736 | Nailer Board | 48022.1435 | 5312 | LF |  | 0 | 9789.7353 | 0 | 38232.4082 | 0 | 0
14 |  | Segmented Retaining Wall | 55729.6743 | 1 | LS | 63300 | 0 | 610.7247 | 528.33 | 2389.75 | 51175 | 1025.8696
| 2185 | Import Bedding Gravel | 1975 | 100 | TON |  | 0 | 0 | 0 | 1975 | 0 | 0
| 2149 | Import Trucking | 847.8261 | 100 | TON |  | 0 | 0 | 0 | 0 | 0 | 847.8261
|  | Leveling Pad | 1731.8482 | 100 | LF |  | 0 | 610.7247 | 528.33 | 414.75 | 0 | 178.0435
|  | Concrete Flatwork Prep UBC 06" 2020 | 1731.8482 | 600 | SF |  | 0 | 610.7247 | 528.33 | 414.75 | 0 | 178.0435
| 2156 | Prep Concrete Flatwork | 1139.0547 | 600 | SF |  | 0 | 610.7247 | 528.33 | 0 | 0 | 0
| 2183 | Import Road Base | 414.75 | 21 | TON |  | 0 | 0 | 0 | 414.75 | 0 | 0
| 2149 | Import Trucking | 178.0435 | 21 | TON |  | 0 | 0 | 0 | 0 | 0 | 178.0435
| 7875 | Retaining Wall Sub | 51175 | 1 | LS |  | 0 | 0 | 0 | 0 | 51175 | 0
15 |  | Concrete Sign Wall - Tilt Panel | 18826.4385 | 1 | LS | 24700 | 577.01 | 5737.8484 | 147.3446 | 9488.3096 | 2875.9259 | 0
| 3250 | Misc. Site Concrete | 16537.4354 | 406 | SF |  | 577.01 | 4624.3081 | 147.3446 | 8312.8467 | 2875.9259 | 0
|  | Concrete Flatwork (03.5" Thick) 2020 | 2289.0031 | 450 | SF |  | 0 | 1113.5402 | 0 | 1175.4628 | 0 | 0
| 3254 | Concrete Flatwork | 2289.0031 | 450 | SF |  | 0 | 1113.5402 | 0 | 1175.4628 | 0 | 0
16 |  | Baseball & Softball Scoreboards | 48008.8116 | 1 | LS | 63000 | 0 | 11005.3596 | 6187.5 | 4888.752 | 25927.2 | 0
|  | Pothole (VacTruck) | 5003.9924 | 4 | EACH |  | 0 | 1291.4924 | 3712.5 | 0 | 0 | 0
| 2105 | Potholing | 5003.9924 | 4 | EACH |  | 0 | 1291.4924 | 3712.5 | 0 | 0 | 0
| 3130 | Concrete Pole Base | 11723.7177 | 4 | EACH |  | 0 | 6309.9657 | 525 | 4888.752 | 0 | 0
| 2705 | Misc. Equipment Install | 5353.9014 | 1 | LS |  | 0 | 3403.9014 | 1950 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 25927.2 | 1 | LS |  | 0 | 0 | 0 | 0 | 25927.2 | 0
17 |  | Soccer Scoreboards | 50561.7916 | 1 | LS | 65000 | 0 | 11005.3596 | 6187.5 | 4888.752 | 28480.18 | 0
|  | Pothole (VacTruck) | 5003.9924 | 4 | EACH |  | 0 | 1291.4924 | 3712.5 | 0 | 0 | 0
| 2105 | Potholing | 5003.9924 | 4 | EACH |  | 0 | 1291.4924 | 3712.5 | 0 | 0 | 0
| 3130 | Concrete Pole Base | 11723.7177 | 4 | EACH |  | 0 | 6309.9657 | 525 | 4888.752 | 0 | 0
| 2705 | Misc. Equipment Install | 5353.9014 | 2 | EACH |  | 0 | 3403.9014 | 1950 | 0 | 0 | 0
| 2700 | Athletic Field Equipment Materials | 28480.18 | 1 | LS |  | 0 | 0 | 0 | 0 | 28480.18 | 0
18 |  | Building Demo (Concrete Slabs And Footings) | 320945.3461 | 1 | LS | 398000 | 0 | 23455.2398 | 39131 | 208890 | 0 | 49469.1063
|  | Demolition Building & Foundation (SF) 2020 | 320945.3461 | 8800 | CY |  | 0 | 23455.2398 | 39131 | 208890 | 0 | 49469.1063
| 2470 | Building Demolition | 62586.2398 | 8800 | CY |  | 0 | 23455.2398 | 39131 | 0 | 0 | 0
| 2490 | Dump Fees | 208890 | 18568 | TON |  | 0 | 0 | 0 | 208890 | 0 | 0
| 2150 | Export Trucking | 49469.1063 | 18568 | TON |  | 0 | 0 | 0 | 0 | 0 | 49469.1063
19 |  | Hazwoper Training | 81601.0608 | 1 | LS | 100000 | 0 | 76601.0608 | 0 | 0 | 0 | 0
| 1400 | Training | 81601.0608 | 1 | LS |  | 0 | 76601.0608 | 0 | 0 | 0 | 0